## Sheet1
2026 STEP Report Appendix 1
COMPLETE |  |  |  | Complete and in-service
CLOSED OUT |  |  |  | In-service and all required project close-out documentation supplied by TO. Per BP 7060, Section 13, upgrades reported as closed out this quarter will not be included in subsequent reports.
DELAY - MITIGATION |  |  |  | Behind schedule, interim mitigation provided or project may change but time permits the implementation of project; asterisk (*) indicates interim mitigation plan provided by SPP
IDENTIFIED |  |  |  | Upgrade identified and included in Board approved study results
IN SERVICE |  |  |  | Upgrade is in service, but not all project activities are complete
NTC - COMMITMENT WINDOW |  |  |  | NTC/NTC-C issued, still within the 90 day written commitment to construct window and no commitment received
NTC-C PROJECT ESTIMATE WINDOW |  |  |  | Within the NTC-C Project Estimate (CPE) window
ON SCHEDULE < 4 |  |  |  | On Schedule within 4-year horizon
ON SCHEDULE > 4 |  |  |  | On Schedule beyond 4-year horizon
REEVALUATION |  |  |  | NTC/NTC-C active; pending re-evaluation
RFP RESPONSE WINDOW |  |  |  | RFP Issued
SUSPENDED |  |  |  | NTC/GIA suspended
NTC ID | Project ID | Upgrade ID | Project Owner | State(s) | Project Name | Upgrade Name | Project Type | Project Owner Indicated In-Service Date | RTO Determined Need Date | Letter of Notification to Construct Issue Date | Source Study | Baseline Cost Estimate | Baseline Cost Estimate Year | Baseline Cost Estimate with Escalation | Current Cost Estimate | Final Cost | Project Status | From Bus Number | From Bus Name | To Bus Number | To Bus Name | Project Description/ Comments | Voltages (kV) | Number of New | Number of Rebuild/Reconductor | Number of Voltage Conversion
200220 | 30375 | 50442 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. - Gentleman 345 kV Ckt 1 | Regional Reliability | 2028-09-30 | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 296697797 | 2025 | 304115241.925 | 296697797 |  | Delay - Mitigation | 640500 | Cherry County 345 kV | 640183 | Gerald Gentleman Station | Build new 110-mile 345 kV line from Gerald Gentleman Station substation to new Cherry County substation. This upgrade is contingent upon approval from Western Area Power Administration ("WAPA") to tap the Grand Island - Fort Thompson 345 kV line. | 345 | 100.7
200220 | 30375 | 50444 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. Substation 345 kV | Regional Reliability | 2028-09-30 | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 15479072 | 2025 | 15866048.8 | 15479072 |  | Delay - Mitigation | 640500 | Cherry County 345 kV |  |  | Build new Cherry County 345 kV substation and install necessary terminal equipment. This upgrade is contingent upon approval from WAPA to tap the Grand Island - Fort Thompson 345 kV line. | 345
200220 | 30375 | 50445 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Cherry Co. - Holt Co. 345 kV Ckt 1 | Regional Reliability | 2028-09-30 | 2018-01-01 | 2013-03-11 | 2012 ITP10 | 357216674 | 2025 | 366147090.85 | 357216674 |  | Delay - Mitigation | 640500 | Cherry County 345 kV | 640503 | Holt County 345 kV | Build new 117-mile 345 kV line from new Cherry County substation to new Holt County substation. This upgrade is contingent upon approval from WAPA to tap the Grand Island - Fort Thompson 345 kV line. | 345 | 124.3
210618 | 30375 | 50446 | NPPD | NE | Multi - Gentleman - Cherry Co. - Holt Co. 345 kV | Holt Co. Substation 345 kV | Regional Reliability | 2028-09-30 | 2018-01-01 | 2021-11-04 | 2012 ITP10 | 579745 | 2025 | 594238.625 | 579745 |  | Delay - Mitigation | 640503 | Holt County 345 kV |  |  | Add line bay terminal equipment as necessary to connect, commission and operate the 345 kV line from Thedford to Holt County Substation. | 345
200277 | 30678 | 50889 | NPPD | NE | XFR - Thedford 345/115 kV | Thedford 345/115 kV Transformer | High Priority | 2027-12-31 | 2016-06-01 | 2014-05-19 | HPILS | 9306000 | 2014 | 12515535.3589 | 9928833 |  | Delay - Mitigation Window | 640500 | Cherry County 345 kV | 640381 | Thedford | Install new 345/115 kV 400 MVA transformer at Thedford substation. Install any necessary 115 kV terminal equipment. | 345/115
200277 | 30678 | 51002 | NPPD | NE | XFR - Thedford 345/115 kV | Thedford 345 kV Terminal Upgrades | High Priority | 2027-12-31 | 2016-06-01 | 2014-05-19 | HPILS | 930800 | 2014 | 1251822.5137 | 1326679 |  | Delay - Mitigation Window | 640500 | Cherry County 345 kV |  |  | Install any necessary 345 kV terminal equipment at Thedford associated with new 345/115 kV transformer. | 345
200397 | 31065 | 51484 | WFEC | OK | Sub - Cleo Junction 138 kV Terminal Upgrades | Cleo Junction 138 kV Terminal Upgrades | Regional Reliability | 2026-04-30 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 4000000 | 2016 | 5120338.16 | 4500000 |  | Delay - Mitigation | 520855 | CLEO JCT |  |  | Install 3-breaker ring bus at Cleo Junction to allow load to be moved from 69 kV to 138 kV. | 138
200390 | 31025 | 51487 | GRDA | OK | Sub - Sallisaw 161 kV Terminal Upgrades | Sallisaw 161 kV Terminal Upgrades | Regional Reliability | 2017-12-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 2266000 | 2016 | 2322650 | 2266000 |  | Re-evaluation | 505550 | Sallisaw |  |  | Install ring bus at Sallisaw 161 kV substation. | 161
200397 | 31041 | 51526 | WFEC | OK | Multi - Driftwood 138/69 kV Substation and Transformer | Driftwood 138 kV Substation | Regional Reliability | 2023-07-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 550000 | 2016 | 653777.1625 | 600000 |  | Complete | 520203 |  |  |  | Tap the 138 kV line from Byron to Cherokee City to construct new Driftwood substation. Install any required 138 kV terminal upgrades required to install 138/69 kV transformer. | 138
200397 | 31041 | 51527 | WFEC | OK | Multi - Driftwood 138/69 kV Substation and Transformer | Driftwood 138/69 kV Transformer | Regional Reliability | 2023-07-31 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 3000000 | 2016 | 3566057.25 | 3600000 |  | Complete |  |  | 520938 | HAZELTON JCT | Install new 138/69 kV transformer at new Driftwood substation. Install new 69 kV terminal for 69 kV line from Hazelton Junction. | 138/69
200386 | 31057 | 51560 | AEP | OK | Line - Atoka - Atoka Pump - Pittsburg - Savanna - Army Ammo - McAlester City 69 kV Ckt 1 Rebuild | Atoka - Atoka Pump - Pittsburg 69 kV Ckt 1 Rebuild | Zonal Reliability | 2024-12-19 | 2017-06-01 | 2016-05-17 | 2016 ITPNT | 21668581.75 | 2016 | 26401062.8431 | 24066136 |  | Complete | 510882 | ATOKA 69KV | 510885 | PITTSBURG 69KV | Rebuild 27.1-mile 69 kV line from Atoka to Atoka Pump to Pittsburg. | 69
| 51239 | 71933 | NPPD | NE/ | Sub - Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition | Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition (TOIF) | Generation Interconnection | 2022-09-30 |  |  | GI STUDIES |  |  | 0 | 4700000 |  | In Service | 640503 | Holt County 345 kV |  |  | Holt County 345kV Substation - Install 345kV line terminal to connect to the Interconnection Customer Interconnection Facilities. Work to include line switch, dead-end towers, metering, current transformers, potential transformers, and associated and miscellaneous material.; One (1) approximately five (5) mile 345 kV overhead transmission line from the Interconnection Customer's collector substation to the Transmission Owner's Holt County 345 kV substation.
| 51239 | 71934 | NPPD | NE | Sub - Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition | Holt County 345kV (Tap Grand Prairie - Grand Island 345kV) - GEN-2015-023 Addition (NU) | Generation Interconnection | 2022-09-30 |  |  | GI STUDIES |  |  | 0 | 5900000 |  | In Service | 640503 | Holt County 345 kV |  |  | Holt County 345 kV Substation – 345 kV substation bus work; add one (1) 345 kV line terminal, four (4) 345 kV circuit breakers, control panel, disconnect switches, and all associated and miscellaneous equipment. | 345
200477 | 51254 | 71963 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 345 kV Substation | Regional Reliability | 2025-12-23 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 20279796 | 2022 | 21839122.0879 | 24319368 |  | Delay - Mitigation Window |  |  |  |  | Tap the existing 345 kV line from Moore to Cooper to construct the new Monolith substation approximately 1 mile from Moore. Install any necessary 345 kV terminal equipment. | 345 | 0.2
200477 | 51254 | 71964 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #1 | Regional Reliability | 2025-12-23 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5468352 | 2022 | 5888816.9757 | 5468352 |  | Delay - Mitigation |  |  |  |  | Add a new 345/115 kV ckt 1 transformer at Monolith substation. | 345/115
200477 | 51254 | 71965 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 345/115 kV Transformer #2 | Regional Reliability | 2025-12-23 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5179657 | 2018 | 6156984.4658 | 5468352 |  | Delay - Mitigation Window |  |  |  |  | Add a new 345/115 kV ckt 2 transformer at Monolith substation. | 345/115
210682 | 51254 | 71966 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Monolith 115 kV Substation Upgrades | Regional Reliability | 2025-12-23 | 2020-12-01 | 2022-08-12 | DPA-2016-December-703 | 13329402 | 2022 | 14354307.984 | 18617823 |  | Delay - Mitigation Window |  |  |  |  | Re-terminate Firth - Sheldon 115 kV line at Monolith 115 kV sub rather than Sheldon 115 kV sub. Install any necessary 115 kV terminal equipment. | 115 | 2.6
210682 | 51254 | 71967 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Sheldon - Monolith 115 kV Ckt 1 New Line | Regional Reliability | 2026-06-01 | 2020-12-01 | 2022-08-12 | DPA-2016-December-703 | 1605462 | 2022 | 1772129.65 | 1173160 |  | Delay - Mitigation Window |  |  |  |  | Re-terminate LES SW 7th & Bennet - Sheldon 115 kV line at Monolith 115 kV sub rather than Sheldon 115 kV sub. Construct new 115 kV line interconnections into Monolith substation. | 115 | 1
200477 | 51254 | 71968 | NPPD | NE | Multi - Sheldon - Monolith 115 kV | Sheldon 115 kV Terminal Upgrades | Regional Reliability | 2025-12-23 | 2020-12-01 | 2018-02-21 | DPA-2016-December-703 | 5656017 | 2022 | 6090911.6539 | 5928037 |  | Delay - Mitigation Window |  |  |  |  | Upgrade all terminal equipment in northern half of Sheldon 115 kV substation to achieve Sheldon - Monolith 115 kV line rating of no less than 400/400 MVA | 115
| 51255 | 71970 | WFEC | OK | Sub - Snyder 138kV (WFEC) - GEN-2015-013 Addition | Snyder 138kV (WFEC) - GEN-2015-013 Addition (NU) | Generation Interconnection | 2024-03-26 |  |  | GI STUDIES |  |  | 0 | 1700000 |  | In Service | 521052 | SNYDER |  |  | Snyder 138kV Substation: Install one (1) new line terminal, one (1) 2000A circuit breaker, line relaying, disconnect switches, additional 4” IPS aluminum buss, and associated equipment.
210486 | 51278 | 72006 | WAPA | ND | Sub - Bismarck 115 kV and North Bismarck 115 kV Terminal Upgrades | Bismarck 115 kV Terminal Upgrades | Sponsored Upgrade | 2025-04-17 | 2024-06-01 | 2018-08-17 | SUS-002 | 90000 | 2018 | 106981.7175 | 148047 |  | Complete | 652427 | BISMARK | 655652 |  | Replace CTs at Bismarck 115 kV substation to increase rating of Bismarck - East Bismarck 115 kV line to at least 85 MVA. This is a mitigation upgrade resulting from the Sponsored Upgrade Study #SUS-002 CPEC North Bismarck Breaker. Costs will be Directly Assigned to CPEC. | 115
210483 | 51282 | 72018 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet - Watonga SW 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2025-09-20 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 8400000 | 2018 | 9984960.3 | 8400000 |  | Complete | 520839 | CALUMET | 521090 | WATONGA SW | Convert 16.8 mile 69 kV line from Calumet - Watonga SW to 138 kV. | 138 |  | 16.8 | 16.8
210483 | 51282 | 72019 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet - Concho 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2025-12-30 | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 1250000 | 2018 | 1485857.1875 | 2150000 |  | Delay - Mitigation | 520839 | CALUMET | 520865 | CONCHO | Convert 9.0 mile 69 kV line from Calumet - Concho to 138 kV. Complete necessary terminal upgrades at Concho. | 138 |  |  | 9
210483 | 51282 | 72020 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet - Cana 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2026-06-01 | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4550000 | 2018 | 5543733.195 | 6741332 |  | Delay - Mitigation | 520839 | CALUMET | 520502 |  | Convert 9.1 mile 69 kV line from Calumet - Cana to 138 kV. Complete necessary terminal upgrades at Cana. | 138 |  | 9.1 | 9.1
210483 | 51282 | 72021 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Calumet 138 kV Substation | Regional Reliability | 2025-10-30 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4754743 | 6580002 |  | Complete | 520839 | CALUMET |  |  | New Calumet 138 kV substation with 4-terminal ring bus. | 138
210483 | 51282 | 72022 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Cana - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2026-06-30 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 5650000 | 2018 | 6883976.385 | 2195001 |  | Delay - Mitigation | 520502 |  | 520899 | EL RENO | Convert 3.3 mile 69 kV line from Cana - El Reno Jct to 138 kV. Complete necessary terminal upgrades at El Reno Jct. | 138 |  | 3.3 | 3.3
210483 | 51282 | 72023 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | El Reno - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2026-07-31 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4873611.6 | 3500000 |  | Delay - Mitigation | 520892 | EL RENO SW | 520899 | EL RENO | Convert 6.5 mile 69 kV line from El Reno - El Reno Jct to 138 kV. Complete necessary terminal upgrades at El Reno. | 138
210483 | 51282 | 72024 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | El Reno - Mustang 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-05-30 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4000000 | 2018 | 4638773.68 | 12155000 |  | Complete | 520892 | EL RENO SW | 520412 |  | Convert 21.3 mile 69 kV line from El Reno - Mustang to 138 kV. Complete necessary terminal upgrades at Mustang. | 138 |  | 21.3 | 21.3
210483 | 51282 | 72027 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Cogar - El Reno Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2026-09-30 | 2020-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 5000000 | 2018 | 6092014.5 | 5300000 |  | Delay - Mitigation | 520859 | COGAR | 520899 | EL RENO | Convert 10.6 mile 69 kV line from Cogar - El Reno Jct to 138 kV. | 138 |  | 10.6 | 10.6
210483 | 51282 | 72031 | WFEC | OK | Multi - Park Community - Sunshine 138 kV | Concho - Kingfisher SW 138 kV Ckt 1 New Line | Regional Reliability | 2024-12-30 | 2019-06-01 | 2018-04-26 | DPA-2017-August-767-774-776 | 4250000 | 2018 | 4928697.035 | 6450000 |  | Complete | 520865 | CONCHO |  |  | Construct new 8.5 mile 138 kV line from Concho - Kingfisher SW. | 138 | 8.5
| 51283 | 72032 | EKC | KS/ | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (TOIF) | Generation Interconnection | 2025-02-28 |  |  | GI STUDIES |  |  | 0 | 1977982 |  | Complete |  |  |  |  | Transmission Owner’s GEN-2015-052 Tap Interconnection Substation: Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 51283 | 72034 | OGE | OK | Sub - Wild Plains 345kV Switching Station GEN-2015-052 Interconnection | Wild Plains 345kV Switching Station GEN-2015-052 Interconnection (NU - OGE) | Generation Interconnection | 2025-03-03 |  |  | GI STUDIES |  |  | 0 | 20000 |  | In Service |  |  |  |  | Oklahoma Gas and Electric Company – Checking and Verifying Relay Settings
210489 | 51327 | 82111 | WFEC | OK | Line - Cogar - OU SW 138 kV | Cogar - Cleveland Jct 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2027-02-28 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 15333000 | 2024 | 16109233.125 | 15333000 |  | Delay - Mitigation | 520859 | COGAR | 520509 |  | Convert 12.0 mile 69 kV line from Cogar - Cleveland Junction to 138 kV. | 138
210489 | 51327 | 82112 | WFEC | OK | Line - Cogar - OU SW 138 kV | Cleveland Jct - Amber Tap 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2026-04-28 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 12224000 | 2024 | 12842840 | 12224000 |  | Delay - Mitigation | 520509 |  |  |  | Convert 13.8 mile 69 kV line from Cleveland Jct - Amber Tap to 138 kV. | 138
210489 | 51327 | 82115 | WFEC | OK | Line - Cogar - OU SW 138 kV | Cleveland Jct - Anadarko 138 kV Ckt 1 Voltage Conversion | Regional Reliability | 2027-02-28 | 2018-12-31 | 2018-07-09 | DPA-2017-December-815 | 9932652 | 2024 | 10435492.5075 | 9932652 |  | Delay - Mitigation | 520509 |  | 520814 | ANADARKO | Convert 11.1 miles of double circuit 69 kV line from Cleveland Junction - Anadarko to single circuit 138 kV. | 138
| 51333 | 82128 | OGE | OK/ | Sub - Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection | Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection (TOIF) | Generation Interconnection | 2025-09-23 |  |  | GI STUDIES |  |  | 0 | 18000000 |  | Complete |  |  |  |  | Transmission Owner GEN-2015-066 Tap Interconnection Substation: Transmission Owner Interconnection Facilities Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 51333 | 82129 | OGE | OK | Sub - Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection | Tap Cleveland - Sooner 345 kV Substation GEN-2015-066 Interconnection (NU) | Generation Interconnection | 2025-09-23 |  |  | GI STUDIES |  |  | 0 | 18000000 |  | Complete |  |  |  |  | Transmission Owner GEN-2015-066 Tap Interconnection Substation - Non-Shared Network Upgrades* Install three (3) 3000 continuous ampacity breakers, cut in transmission line and re-terminate, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
210548 | 71348 | 102163 | OPPD | NE | Multi - S1361 | S1209 - S1231 Ckt 2 161 kV Reconductor | Regional Reliability | 2024-06-24 | 2021-06-01 | 2019-12-13 | DPA-2018-February-841 | 7345498 | 2024 | 7345498 | 7345497 |  | Closed Out | 646209 | Sub 1209 | 646231 | Sub 1231 | Reconductor 3.3 miles of S1209 - S1231 161 kV Ckt 2 | 161 |  | 3.3
| 81358 | 112179 | WFEC | OK | GEN-2016-118 Interconnection Costs | GEN-2016-118 Interconnection Costs (TOIF) (WFEC) | Generation Interconnection | 2021-06-29 |  |  | GI STUDIES |  |  | 0 | 400000 |  | In Service |  |  |  |  | Construct a new breaker and half configuration, eleven (11) 138kV 2000 continuous ampacity breakers, control panels, line relaying, re-terminate, transferring 138/69 kV autotransformer to the new station, acquire land, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 81358 | 112186 | OGE | OK | GEN-2016-118 Interconnection Costs | GEN-2016-118 Interconnection Costs (NU) (OKGE) | Generation Interconnection | 2021-06-29 |  |  | GI STUDIES |  |  | 0 | 142965 |  | In Service | 520882 | DOVER SW |  |  | Dover - Henessey 138kV CKT 1 Upgrade terminal equipment from 800A CT to 1200A CT.
| 81454 | 112284 | OGE | OK | GEN-2016-071 Interconnection Costs | GEN-2016-071 Interconnection Costs | Generation Interconnection | 2026-09-30 |  |  | GI STUDIES |  |  | 0 |  |  | On Schedule < 4 |  |  |  |  | (OKGE) Construct a new 4 breaker 138 kV ring bus substation and terminate WFEC 138 kV transmission line (WFEC) Construct a 138 kV transmission line with length TBD (WFEC) Add a 138 kV in-line transmission tap near Chilocco and terminate GEN-2016-071. (Customer) Construct 138 kV transmission and 138/34.5 kV collection system and add one 138 kV breaker controllable by WFEC.
210611 | 81474 | 112307 | AEP | OK/ | Sub - Oklaunion 345 kV Capacitive Reactive Power Support | Oklaunion 345 kV Capacitive Reactive Power Support | Generation Interconnection | 2026-05-15 | 2023-05-15 | 2021-05-17 | DISIS-2016-002 | 9453182 | 2021 | 10695407.7254 | 36148953 |  | Delay - Mitigation |  |  |  |  | Install +200Mvar Capacitor Bank(s) at the Oklaunion 345kV substation.
| 81483 | 112331 | AEP | LA | Sub - Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection | Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection (TOIF) (AEPW) | Generation Interconnection | 2026-03-01 |  |  | GI STUDIES |  |  | 0 | 1175646 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 138 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating |  | 0.04
| 81483 | 112332 | AEP | LA | Sub - Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection | Lieberman - North Benton 138 kV Substation GEN-2016-167 Interconnection (Non-Shared NU) (AEPW) | Generation Interconnection | 2026-03-01 |  |  | GI STUDIES |  |  | 0 | 9959548.73 |  | On Schedule < 4 |  |  |  |  | Build a 3-breaker ring bus station on the Lieberman-North Benton 138 kV section of the Lieberman-Red Point 138 kV line to facilitate the new generation interconnection. |  | 1.32
| 81490 | 112335 | AEP | OK | Multi - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-095 (TOIF) (AEPW) | Generation Interconnection | 2023-11-17 |  |  | GI STUDIES |  |  | 0 | 1388819 |  | In Service |  |  |  |  | Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. |  | 0.18
| 81490 | 112336 | AEP | OK | Multi - Gracemont - Lawton East Side 345 kV | Gracemont - Lawton East Side 345 kV Substation GEN-2016-095 (NU) (AEPW) | Generation Interconnection | 2023-11-17 |  |  | GI STUDIES |  |  | 0 | 17798882 |  | In Service |  |  |  |  | Construct new 345 kV four (4) breaker ring bus, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials. |  | 0.32
| 81491 | 112337 | AEP | OK | GEN-2016-097 Interconnection Costs | Tap Southwestern - Fletcher Tap 138 kV Substation GEN-2016-097 (TOIF) (AEPW) | Generation Interconnection | 2023-05-09 |  |  | GI STUDIES |  |  | 0 | 918474 |  | In Service |  |  |  |  | Construct one (1) 138 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. |  | 0.04
| 81491 | 112338 | AEP | OK | GEN-2016-097 Interconnection Costs | Tap Southwestern - Fletcher Tap 138 kV Substation GEN-2016-097 (Non-Shared NU) (AEPW) | Generation Interconnection | 2023-05-09 |  |  | GI STUDIES |  |  | 0 | 7400346 |  | In Service |  |  |  |  | Construct new 138 kV three (3) breaker ring bus, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 81486 | 112341 | OGE | OK | Blue River 138 kV Substation GEN-2016-102 Interconnection | Blue River 138 kV Substation GEN-2016-102 Interconnection (TOIF) (OKGE) | Generation Interconnection | 2025-03-31 |  |  | GI STUDIES |  |  | 0 | 410000 |  | Complete |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-102 (150.9 MW/Wind) into the POI at Blue River 138 kV.
| 81486 | 112342 | OGE | NA | Blue River 138 kV Substation GEN-2016-102 Interconnection | Blue River 138 kV Substation GEN-2016-102 Interconnection (Non-Shared NU) (OKGE) | Generation Interconnection | 2025-03-31 |  |  | GI STUDIES |  |  | 0 | 2995000 |  | Complete |  |  |  |  | Non-Shared Network Upgrade Interconnection cost estimates needed to interconnect GEN-2016-102 (150.9 MW/Wind) into the POI at Blue River 138 kV.
| 81485 | 112343 | OGE | OK | Sub - Arbuckle 138 kV Substation GEN-2016-126 Interconnection | Arbuckle 138 kV Substation GEN-2016-126 Interconnection (TOIF) (OKGE) | Generation Interconnection | 2025-07-29 |  |  | GI STUDIES |  |  | 0 | 410000 |  | Complete |  |  |  |  | TOIF Interconnection upgrade and cost estimates needed to interconnect GEN-2016-126 (172.5 MW/Wind) into the POI Arbuckle 138 kV.
| 81485 | 112344 | OGE | OK | Sub - Arbuckle 138 kV Substation GEN-2016-126 Interconnection | Arbuckle 138 kV Substation GEN-2016-126 Interconnection (Non-Shared NU) (OKGE) | Generation Interconnection | 2025-07-29 |  |  | GI STUDIES |  |  | 0 | 3590000 |  | Complete |  |  |  |  | Non-Shared Network Upgrade Interconnection cost estimates needed to interconnect GEN-2016-126 (172.5 MW/Wind) into the POI at Arbuckle 138 kV.
| 81495 | 112354 | SPS | TX | XTO to Cornell GEN-2016-177 Interconnection Costs | GEN-2016-177 Interconnection Costs (NU) (SPS) | Generation Interconnection | 2020-10-07 |  |  | GI STUDIES |  |  | 0 |  |  | In Service |  |  |  |  | Network Upgrade Interconnection cost estimates needed to interconnect GEN-2016-177 (17.0 MW/Gas Turbine) into the POI at XTO_Cornell 115kV
210623 | 81500 | 112360 | AEP | OK | Sub - Riverside Station 138 kV | Riverside Station 138 kV Breakers | Regional Reliability | 2026-05-01 | 2021-06-01 | 2021-11-05 | 2019 ITP | 41100000 | 2020 | 47663399.562 | 49939073 |  | Delay - Mitigation | 509783 | RIVERSIDE STATION 138KV |  |  | Replace 27 breakers at Riverside Station 138 kV with 90 kA breakers and expand substation as necessary to accommodate physically larger breakers | 138 | 1.56
210545 | 81513 | 112377 | WFEC | OK | Sub - Anadarko 138 kV | Anadarko 138 kV Breakers | Regional Reliability | 2025-11-21 | 2021-06-01 | 2019-11-18 | 2019 ITP | 828359 | 2020 | 937212.1734 | 1190980 |  | Complete | 520814 | ANADARKO |  |  | Replace 3 breakers at Anadarko 138 kV with 63 kA breakers | 138
220908 | 81515 | 112380 | WFEC | OK | Sub - Mooreland 138/69 kV Breakers | Mooreland 69 kV Breakers #2 | Regional Reliability | 2026-06-30 | 2021-06-01 | 2025-05-12 | 2019 ITP | 685000 | 2025 | 702125 | 685000 |  | NTC - Commitment Window | 520995 | MOORELAND |  |  | Remove retired breakers 142 and 442. Install 4 PTs, 2 three-phase switches, 3 lightning arresters, 3 runs of 336-string bus and move transmission lines to 542 breaker.
210545 | 81525 | 112395 | WFEC | OK | Device - Gypsum 69 kV Capacitor Bank | Gypsum 69 kV Capacitor Bank | Regional Reliability | 2026-03-31 | 2021-06-01 | 2019-11-18 | 2019 ITP | 400000 | 2020 | 463877.368 | 400000 |  | Delay - Mitigation | 520929 | GYPSUM |  |  | Install a new 12 MVAR capacitor bank at Gypsum 69 kV substation. | 69/69
210538 | 81533 | 112403 | NPPD | NE | Sub - Firth 115kV | Firth Cap Bank 115kV Ckt 1 | Regional Reliability | 2024-07-02 | 2021-04-01 | 2019-11-18 | 2019 ITP | 608900 | 2020 | 672111.6687 | 570000 | 570000 | Complete | 640171 | Firth |  |  | Install new 15 MVAR capacitor bank at Firth 115 kV substation. | 115
210538 | 81533 | 112404 | NPPD | NE | Sub - Firth 115kV | Firth 115 kV Substation Expansion | Regional Reliability | 2024-07-02 | 2021-04-01 | 2019-11-18 | 2019 ITP | 3600000 | 2020 | 3973726.404 | 3036560 | 3036560 | Complete | 640171 | Firth |  |  | Expand the existing Firth 115 kV substation to accommodate a new 15 MVAR capacitor bank. | 115
210545 | 81550 | 112435 | WFEC | OK | Line - East Kingfisher - Kingfisher 138kV | East Kingfisher - Kingfisher 138 kV Rebuild | Economic | 2026-05-31 | 2021-01-01 | 2019-11-18 | 2019 ITP | 1000000 | 2020 | 1159693.42 | 1000000 |  | Delay - Mitigation |  |  |  |  | Rebuild 2.03 miles of 138 kV line from Kingfisher to East Kingfisher and upgrade any necessary terminal equipment at East Kingfisher and/or Kingfisher to increase the summer emergency rating to 187 MVA | 138
210586 | 81553 | 112443 | WFEC | OK | Line - Russett - South Brown 138 kV | Russett - South Brown 138 kV Ckt 1 Rebuild | Economic | 2027-10-31 | 2022-01-01 | 2020-11-17 | 2020 ITP | 10267390.81 | 2021 | 11616610.2577 | 10267390 |  | Delay - Mitigation | 505602 | Brown | 521044 | RUSSETT | Rebuild 18.62 miles of 138 kV line from Russett to South Brown and upgrade terminal equipment at South Brown as needed to achieve a summer emergency rating of 234 MVA | 138
210593 | 81561 | 112458 | TSOK | OK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV New Line | Economic | 2025-11-20 | 2026-01-01 | 2021-02-10 | 2019 ITP | 144559958 | 2025 | 144559958 | 144559958 |  | On Schedule < 4 | 509755 | WEKIWA 345KV | 514803 | SOONER 345 | Build a new 345kV line from Sooner to Wekiwa with a summer emergency rating of 1792 MVA | 345
210544 | 81561 | 112460 | AEP | OK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sand Springs - Sheffield Steel 138 kV Terminal Upgrades | Economic | 2026-02-26 | 2026-01-01 | 2019-11-18 | 2019 ITP |  |  | 0 | 0 |  | Delay - Mitigation Window | 509812 | SHEFFIELD | 509815 | Sand Springs 138 kV | Upgrade any necessary terminal equipment at Sand Springs and/or Sheffield Steel to increase the summer rating to 278 MVA | 138
210544 | 81561 | 112502 | AEP | OK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV Terminal Upgrades (AEP) | Economic | 2025-11-20 | 2026-01-01 | 2019-11-18 | 2019 ITP | 7651684 | 2025 | 7651684 | 7651684 |  | On Schedule < 4 |  |  |  |  | Install terminal equipment at Wekiwa to support a 345 kV line from Sooner to Wekiwa rated at summer emergency of 1792 MVA | 345 | 0.06
210540 | 81561 | 112504 | OGE | OK | Multi - Sooner - Wekiwa 345 kV and Sand Springs - Sheffield 138 kV | Sooner - Wekiwa 345 kV Terminal Upgrades (OGE) | Economic | 2025-11-20 | 2026-01-01 | 2019-11-18 | 2019 ITP | 5642819 | 2025 | 5642819 | 5642819 |  | Complete |  |  |  |  | Install terminal equipment to support a 345kV line from Wekiwa to Sooner rated at summer emergency of 1792 MVA | 345
220789 | 81547 | 112509 | EKC | KS | Line - Wolf Creek - Blackberry 345 kV | Wolf Creek 345kV Terminal Equipment | Economic | 2025-07-15 | 2026-01-01 | 2024-08-16 | 2019 ITP | 11618029 | 2021 | 12824130.1666 | 28263970 |  | Complete |  |  |  |  | Install terminal equipment at Wolf Creek and re-terminate Wolf Creek - Waverly 345 kV line to support 345kV line from Wolf Creek to Blackberry rated at 1792 MVA | 345
220790 | 81591 | 122537 | OGE | OK | Device - Border 345kV Capacitive Reactive Support | Border 345kV Capacitive Reactive Support | Generation Interconnection | 2026-12-31 | 2023-04-20 | 2024-08-28 | DISIS-2016-002 | 3996000 | 2021 | 4521107.2072 | 4751519 |  | NTC - Commitment Window |  |  |  |  | Install 1-345 kV 39 Mvar Capacitor Bank, 1-345 kV Capacitor Breaker, and associated switches, relaying, and control equipment at Border substation.
| 81606 | 122555 | SPS | TX | Roadrunner 115kV GEN-2016-121 Interconnection Costs | GEN-2016-121 Interconnection Costs (NU) (SPS) | Generation Interconnection | 2026-07-01 |  |  | GI STUDIES |  |  | 0 |  |  | On Schedule < 4 |  |  |  |  | Network Upgrade Interconnection cost estimates needed to interconnect GEN-2016-121 (110.0 MW/Solar) into the POI at Roadrunner 115kV.
| 81607 | 122557 | SPS | NM | Eddy County to Tolk GEN-2016-123 Interconnection Costs | GEN-2016-123 Interconnection Costs (NU) (SPS) | Generation Interconnection | 2020-12-31 |  |  | GI STUDIES |  |  | 0 | 0 |  | In Service |  |  |  |  | Network Upgrade Interconnection cost estimates needed to interconnect GEN-2016-123 (298.0 MW/Wind) into the POI at Eddy County - Tolk (Crossroads) 345kV.
| 81608 | 122559 | SPS | NM | Eddy County to Tolk GEN-2016-124 Interconnection Costs | GEN-2016-124 Interconnection Costs (NU) (SPS) | Generation Interconnection | 2020-12-31 |  |  | GI STUDIES |  |  | 0 | 0 |  | In Service |  |  |  |  | Network Upgrade Interconnection cost estimates needed to interconnect GEN-2016-124 (150.0 MW/Wind) into the POI at Eddy County - Tolk (Crossroads) 345kV.
| 81609 | 122561 | SPS | NM | Eddy County to Tolk GEN-2016-125 Interconnection Costs | GEN-2016-125 Interconnection Costs (NU) (SPS) | Generation Interconnection | 2020-12-31 |  |  | GI STUDIES |  |  | 0 | 0 |  | In Service |  |  |  |  | Network Upgrade Interconnection cost estimates needed to interconnect GEN-2016-125 (74.0 MW/Wind) into the POI at Eddy County - Tolk (Crossroads) 345kV.
| 93121 | 122591 | OGE | OK | Multi - Anadarko - Gracemont 345 kV/138 kV | Gracemont 345 kV Terminal Equipment | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 0 |  | Identified | 515802 | Gracemont 138 kV |  |  | Upgrade any necessary equipment to support new 345 kV line from Anadarko | 138/138
210626 | 81547 | 122598 | NEET | KS/MO | Line - Wolf Creek - Blackberry 345 kV | Blackberry - Wolf Creek 345 kV | Economic | 2025-07-15 | 2026-01-01 | 2021-12-03 | 2019 ITP | 85168938 | 2021 | 94010571.592 | 87298154 | 87298154 | Complete |  |  |  |  | Build a new 345kV line from Wolf Creek to Blackberry with a summer emergency rating of 1792 MVA | 345
210562 | 81628 | 122602 | WAPA | ND// | Sub - Jamestown 230 kV Redundant Bus Tie | Jamestown 230 kV Redundant Bus Tie | Generation Interconnection | 2025-10-30 |  | 2020-06-10 | DISIS-2016-002 | 1510000 | 2020 | 1708426.3971 | 1741183 |  | Complete |  |  |  |  | Add a redundant bus to Jamestown 230 kV substation to mitigate for a fault and breaker fail of CB 9182.
| 81632 | 122614 | EKC | KS | GEN-2016-111 and GEN-2016-114 Interconnection Costs | Reno - Summit 345kV GEN-2016-111 Interconnection (TOIF) (WERE) | Generation Interconnection | 2028-12-31 |  |  | GI STUDIES |  |  | 0 | 1593920.46 |  | On Schedule < 4 |  |  |  |  | Construct one (1) breaker, four (4) switches, three (3) CTs, and three (3) PTs to accept a transmission line from the Interconnection Customer's Generating Facility.
| 81632 | 122615 | EKC | KS | GEN-2016-111 and GEN-2016-114 Interconnection Costs | Reno - Summit 345kV GEN-2016-111 Interconnection (Non-Shared NU) (WERE) | Generation Interconnection | 2028-12-31 |  |  | GI STUDIES |  |  | 0 | 21351346 |  | On Schedule < 4 |  |  |  |  | Construct two (2) breakers, eight (8) switches, two (2) wavetraps, three (3) CCVts, six (6) PTs, and one (1) control panel. Additional line work to include .15 miles of two (2) new bundles 1590 Lapwing ASCR lines with two (2) 64mm OPGW static wires, two (2) three pole steel dead-end structures, and no distribution overbuild. |  | 0.3
| 81636 | 122627 | OGE | OK | Spring Creek to Sooner 345kV GEN-2016-119 Interconnection Costs | Sooner - Spring Creek GEN-2016-119 Tap 345kV Interconnection Substation (DISIS-2016-002-3) | Generation Interconnection | 2026-02-27 |  |  | GI STUDIES |  |  | 0 | 12930000 |  | In Service |  |  |  |  | Construct a new EHV substation. Install 4-345 kV 3000A breakers, line relaying, disconnect switches, and associated equipment. Costs of this new substation are split by GEN-2016-100, GEN-2016-101, and GEN-2016-119
| 81636 | 122635 | OGE | OK | Spring Creek to Sooner 345kV GEN-2016-119 Interconnection Costs | GEN-2016-119 Interconnection (TOIF) (OKGE) | Generation Interconnection | 2025-03-15 |  |  | GI STUDIES |  |  | 0 | 1099871 |  | Complete |  |  |  |  | Add a single 345kV line terminal to a new EHV Substation. Dead end structure, line switch, line relaying, revenue metering including CTs and PTs.
210606 | 81636 | 122637 | EKC | KS | Spring Creek to Sooner 345kV GEN-2016-119 Interconnection Costs | Spring Creek345 kV (GEN-2016-119) | Generation Interconnection | 2026-03-31 | 2025-03-15 | 2021-03-04 | DISIS-2016-002 | 16624 | 2021 | 18808.5301 | 0 |  | Delay - Mitigation |  |  |  |  | Review and/or apply relay protection settings at the Spring Creek substation.
| 81641 | 122642 | SPS | NM | Tolk West - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Tolk West - Plant X 230 kV Ckt 1 Rebuild (DISIS-2016-002) | Generation Interconnection | 2020-08-05 |  |  | GI STUDIES |  |  | 0 |  |  | In Service |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 796 MVA. Network Upgrade shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81642 | 122643 | SPS | NM | Tolk East - Plant X 230 kV Ckt 2 Rebuild (DISIS-2016-002) | Tolk East - Plant X 230 kV Ckt 2 Rebuild (DISIS-2016-002) | Generation Interconnection | 2020-08-05 |  |  | GI STUDIES |  |  | 0 |  |  | In Service |  |  |  |  | Rebuild line to achieve minimum normal/emergency rating of 796 MVA. Network Upgrade shared among three requests: GEN-2016-123, GEN-2016-124, and GEN-2016-125
| 81655 | 122662 | OGE | OK | Woodring 345kV GEN-2016-128 Interconnection Costs | Woodring 345kV GEN-2016-128 Interconnection (TOIF) (OKGE) | Generation Interconnection | 2025-08-18 |  |  | GI STUDIES |  |  | 0 | 15000 |  | Complete |  |  |  |  | At an existing EHV substation, update relay settings on an existing Gen-Tie line to accommodate new protection settings.
| 81657 | 122665 | AEP | OK | Multi - Riverside 345 kV Substation | Riverside 345kV GEN-2016-133 thru 146 Interconnection (TOIF) (AEP) | Generation Interconnection | 2025-06-08 |  |  | GI STUDIES |  |  | 0 | 1388819 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility. |  | 0.18
| 81657 | 122666 | AEP | OK | Multi - Riverside 345 kV Substation | Riverside 345kV GEN-2016-133 thru 146 Interconnection (Non-Shared NU) (AEP) | Generation Interconnection | 2025-06-08 |  |  | GI STUDIES |  |  | 0 | 10361130 |  | On Schedule < 4 |  |  |  |  | Expand the 345 kV breaker and a half scheme, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
210631 | 81657 | 122667 | OGE | OK | Multi - Riverside 345 kV Substation | Redbud 345kV | Generation Interconnection | 2023-12-31 | 2025-12-31 | 2022-01-31 | DISIS-2016-002 | 15000 | 2022 | 15375 | 15000 |  | On Schedule < 4 |  |  |  |  | Change relay settings to accommodate the Interconnection of the States Edge 1 Wind Farm.
| 81658 | 122668 | BEPC | SD | GEN-2016-130 Interconnection Costs | GEN-2016-130 Interconnection (TOIF) (BEPC) | Generation Interconnection | 2024-12-18 |  |  | GI STUDIES |  |  | 0 | 1415480 |  | Complete |  |  |  |  | Modify existing line terminal for the new interconnections inlcuding three (3) 345 kV PTs, three (3) 345 kV CTs, one (1) line disconnect switch, three (3) 345 kV surge arrestors, protection and control package, revenue metering, and all communication upgrades required.
| 81658 | 122669 | BEPC | ND | GEN-2016-130 Interconnection Costs | Leland Olds 345 kV Substation Reconfiguration (DISIS-2016-002-2) | Generation Interconnection | 2024-12-18 |  |  | GI STUDIES |  |  | 0 | 2776827 |  | Complete |  |  |  |  | Build out of a new line terminal for relocation of LOS Unit 2 main transformer. This includes one (1) 345 kV power circuit breaker, two (2) 345 kV breaker disconnect switches, three (3) 345 kV PTs, three (3) 345 kV surge arrestors, and protection and control package.
| 81660 | 122673 | EKC | KS | Viola 345kV GEN-2016-153 Interconnection Costs | Viola 345kV GEN-2016-153 Interconnection (Non-Shared NU) (WERE) | Generation Interconnection | 2024-12-18 |  |  | GI STUDIES |  |  | 0 | 3022 |  | Complete |  |  |  |  | Review relay settings and apply adjusted settings at Flat Ridge 2 East and Viola 345 kV substations. Install PMU at Viola Substation
210612 | 81660 | 122674 | OGE | OK | Viola 345kV GEN-2016-153 Interconnection Costs | Renfrow 345 kV Relay Setting Adjustment | Generation Interconnection | 2023-10-01 | 2023-10-01 | 2021-06-08 | DISIS-2016-002 | 15000 | 2021 | 15759.375 | 15000 |  | In Service |  |  |  |  | At the existing Renfrow 345 kV substation, update relay settings to accommodate new protection settings.
| 81662 | 122677 | NPPD | NE | Sweetwater 345kV GEN-2016-074 Interconnection Costs | GEN-2016-074 Interconnection (TOIF) (NPPD) | Generation Interconnection | 2027-06-01 |  |  | GI STUDIES |  |  | 0 |  |  | On Schedule < 4 |  |  |  |  | Expanding the existing Sweetwater 345kV Substation to accommodate the GEN-2016-074 interconnection request
| 81662 | 122678 | NPPD | NE | Sweetwater 345kV GEN-2016-074 Interconnection Costs | Sweetwater 345kV GEN-2016-074 Interconnection (TOIF) (NPPD) | Generation Interconnection | 2027-06-01 |  |  | GI STUDIES |  |  | 0 |  |  | On Schedule < 4 |  |  |  |  | Expand the existing Sweetwater 345kV Substation to accommodate GEN-2016-074 interconnection request
| 81665 | 122684 | TSGT | NE | Sidney 115kV GEN-2016-147 Interconnection Costs | Sidney 115kV GEN-2016-147 Interconnection Costs (TOIF) (TSGT) | Generation Interconnection | 2024-04-04 |  |  | GI STUDIES |  |  | 0 | 1636796 |  | In Service |  |  |  |  | Construct one (1) 115 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 81665 | 122687 | TSGT | NE | Sidney 115kV GEN-2016-147 Interconnection Costs | Sidney 115kV GEN-2016-147 Interconnection Costs (Non-Shared NU) (TSGT) | Generation Interconnection | 2024-04-04 |  |  | GI STUDIES |  |  | 0 | 2155837 |  | In Service |  |  |  |  | Construct one (1) 230 kV power circuit breaker, two (2) 115 kV power circuit breakers, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 81666 | 122688 | WAPA | SD | Bismark to Glenham GEN-2016-087 Interconnection Costs | Bismark to Glenham 230kV GEN-2016-087 Interconnection (TOIF) (WAPA) | Generation Interconnection | 2026-08-01 |  |  | GI STUDIES |  |  | 0 | 226495 |  | In Service |  |  |  |  | Construct one (1) 230 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and the re-route of the Glenham line to the new 230 kV line bay.
| 81666 | 122689 | WAPA | NA | Bismark to Glenham GEN-2016-087 Interconnection Costs | GEN-2016-087 Interconnection (Non-Shared NU) (WAPA) | Generation Interconnection | 2026-08-01 |  |  | GI STUDIES |  |  | 0 | 0 |  | In Service |  |  |  |  | Construct one (1) new 230 kV line bay at the Campbell County Switching Station.
210574 | 81682 | 122725 | SPS | TX | Line - Allen - Quaker 115kV | Allen - Quaker 115 kV Ckt 1 Rebuild | Regional Reliability | 2025-03-03 | 2022-06-01 | 2020-11-17 | 2020 ITP | 2961075 | 2021 | 3268472.7533 | 3533803 |  | Complete | 526213 | Allen Sub 115 kV | 526243 | South Plains REC-Quaker 115 kV | Rebuild 3.6 miles 115 kV line from Allen to Quaker and upgrade any necessary terminal equipment to achieve a summer emergency rating of 300 MVA |  |  | 3.5
210574 | 81684 | 122727 | SPS | TX | Line - Allen - Lubbock South 115kV | Allen - Lubbock South 115 kV Ckt 1 Rebuild | Regional Reliability | 2025-03-03 | 2022-06-01 | 2020-11-17 | 2020 ITP | 7350796 | 2021 | 8113903.3766 | 6232467 |  | Complete | 526213 | Allen Sub 115 kV | 526268 | Lubbock South Interchange 115 kV | Rebuild 5.98 miles of 115 kV line from Allen to Lubbock and upgrade any necessary terminal equipment to achieve a summer emergency rating of 300 MVA. |  |  | 6
210575 | 81687 | 122730 | AEP | LA | Line - South Shreveport - Wallace Lake 138 kV #2 | South Shreveport - Wallace Lake 138 kV Ckt 1 Rebuild #2 | Regional Reliability | 2025-12-29 | 2024-06-01 | 2020-11-17 | 2020 ITP | 20575323 | 2025 | 20575323 | 20575323 |  | Delay - Mitigation Window | 507755 | SOUTH SHREVEPORT 138KV | 507765 | WALLACE LAKE 138KV | Rebuild 11.18 miles of 138 kV line from South Shreveport to Wallace Lake and upgrade any necessary terminal equipment to achieve a summer emergency to 347 MVA |  | 11.2
210648 | 81691 | 122734 | WAPA | SD | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Oahe 230 kV Terminal Upgrades (WAPA) | Economic | 2025-04-17 | 2025-01-01 | 2022-03-11 | 2021 ITP | 561800 | 2022 | 604997.1503 | 770086 |  | Complete |  |  |  |  | Upgrade terminal equipment at Oahe 230 kV for the Oahe to Sully Buttes 230 kV line. Re-conductor three spans of line between Oahe 230 kV substation and Sully Buttes 230 kV substation..
210645 | 81694 | 122739 | NPPD | NE | XFR - Columbus 230/115 kV | Columbus East 230/115 kV Transformer | Economic | 2026-01-15 | 2023-01-01 | 2022-03-09 | 2021 ITP | 5080000 | 2022 | 5607369.4812 | 9278651 |  | Complete | 640127 | Columbus East | 640126 | Columbus East | Replace the 230/115 kV transformer and any necessary terminal equipment at Columbus East. | 230/115
210645 | 81769 | 122741 | NPPD | NE | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Scottsbluff - Victory Hill 115kV Ckt 2 | Economic | 2025-06-25 | 2023-01-01 | 2022-03-09 | 2021 ITP | 7760000 | 2022 | 8356671.2112 | 17809299 | 17809299 | Complete | 640338 | Scottsbluff | 640397 | Victory Hill | Build second 9 mile 115 kV line from Scottsbluff to Victory Hill.
210581 | 81768 | 122745 | BEPC | ND | Multi - Watford City 230/115 kV | Watford City 230/115 kV Transformer Ckt 1 (KV1A) | Regional Reliability | 2024-10-29 | 2022-06-01 | 2020-11-17 | 2020 ITP | 3389739 | 2021 | 3650378.1333 | 3766576 |  | Complete |  |  |  |  | Replace the 230/115 kV transformer Ckt 1 at Watford City to achieve a summer emergency rating of 208 MVA | 230/115
210581 | 81768 | 122746 | BEPC | ND | Multi - Watford City 230/115 kV | Watford City 230/115 kV Transformer Ckt 2 (KV2A | Regional Reliability | 2025-07-11 | 2022-06-01 | 2020-11-17 | 2020 ITP | 173041 | 2021 | 191004.8863 | 173041 |  | Complete |  |  |  |  | Upgrade any necessary terminal equipment at Watford City for the 230/115 kV transformer Ckt 2 to achieve a summer emergency rating of 208 MVA | 230/115
220773 | 81701 | 122756 | WFEC | OK/ | Line - Anadarko - Gracemont 138 kV double Ckt 2 & 3 | Anadarko SPA 138 kV Substation Rebuild and Line Re-termination | Economic | 2028-05-31 | 2023-11-14 | 2024-04-11 | 2023 ITP | 22000000 | 2024 | 23113750 | 405535 |  | Delay - Mitigation | 520814 | ANADARKO |  |  | Rebuild Anadarko SPA 138 kV substation to support a new second and third 138 kV line from Anadarko to Gracemont to achieve a summer emergency rating of 478 MVA. Re-terminate all existing lines into the new station.
220739 | 81700 | 122761 | OGE | OK | Line - Cimarron - Czech Hall 138 kV Ckt 1 | Czech Hall 138 kV Terminal Upgrade | Economic | 2024-12-06 | 2025-01-01 | 2023-12-15 | 2023 ITP | 154916 | 2024 | 154916 | 223776.17 | 223776.17 | Closed Out | 514898 | CIMARRON 138 | 514894 | CZECH HALL 138 | Upgrade the switch at Czech Hall 138 kV on the Cimarron to Czech Hall line to achieve a 388/444/478/478 (SN/SE/WN/WE) MVA rating.
| 81670 | 122792 | EKC | KS | Viola 345/138 kV Transformer CKT 2 | Viola 345/138 kV Transformer CKT 2 (DISIS-2016-002-2) | Generation Interconnection | 2024-11-21 |  |  | GI STUDIES |  |  | 0 | 12195318 |  | Complete |  |  |  |  | Install a new 345 kV terminal on a new rung consisting of two (2) breakers, four (4) switches, and two (2) control panels. Install a new 138 kV terminal on an existing rung consisting of one (1) breaker, three (3) switches, three (3) PTs, and one (1) 400/440 MVA 345-138 kV transformer with LTCs. Network Upgrade shared among fourteen requests: GEN-2016-100, GEN-2016-101, GEN-2016-119, GEN-2016-128, GEN-2016-133, GEN-2016-134, GEN-2016-137, GEN-2016-138, GEN-2016-139, GEN-2016-141, GEN-2016-142, GEN-2016-145, GEN-2016-146, GEN-2016-153
210627 | 81717 | 122796 | AEP | OK | Multi - Border - Woodward 345 kV Tap | Chisholm Substation 345 kV Terminal Upgrades | Economic | 2025-12-11 | 2022-01-01 | 2021-11-05 | 2020 ITP | 6275764 | 2023 | 6593474.5525 | 8289302 |  | Delay - Mitigation | 511553 | Elk City 345 kV |  |  | Install any necessary terminal equipment to support a new line 345 kV line from Border - Woodward 345 kV substation with a summer emergency rating of 1792 MVA |  | 0.2
210583 | 81720 | 122804 | EM | KS | Sub - Northeast 161 kV | Northeast 161 kV Breakers | Regional Reliability | 2025-11-21 | 2022-06-01 | 2020-11-17 | 2020 ITP | 887479 | 2021 | 979610.7598 | 1827550 |  | Complete |  |  |  |  | Replace three breakers at the Northeast 161 kV station with 63 kA breakers
210589 | 81733 | 122818 | OGE | OK// | Line - Cushing Tap - Shell Cushing Tap - Pipeline | Cushing - Shell Pipeline Cushing Tap 69 kV Ckt 1 Rebuild | Regional Reliability | 2025-11-28 | 2023-06-01 | 2020-11-17 | 2020 ITP | 4281150 | 2021 | 4725588.554 | 7271212 |  | NTC - Commitment Window | 515032 | CUSHING 69 | 515022 | PIPELINE 69 | Rebuild 4.71 miles of 69 kV line from Cushing to Shell Pipeline Cushing Tap and upgrade any necessary terminal equipment to achieve a summer emergency rating of 72 MVA
210589 | 81733 | 122819 | OGE | OK/ | Line - Cushing Tap - Shell Cushing Tap - Pipeline | Pipeline - Shell Pipeline Cushing Tap 69 kV Ckt 1 Rebuild | Regional Reliability | 2025-11-28 | 2023-06-01 | 2020-11-17 | 2020 ITP | 1081649 | 2021 | 1193938.1087 | 1235418 |  | NTC - Commitment Window | 515022 | PIPELINE 69 |  |  | Rebuild 1.19 miles of 69 kV line from Pipeline to Shell Pipeline Cushing Tap and upgrade any necessary terminal equipment to achieve a summer emergency rating of 72 MVA
210628 | 81717 | 122823 | OGE | OK | Multi - Border - Woodward 345 kV Tap | Border - Woodward Tap 345 kV Substation | Economic | 2025-07-31 | 2022-01-01 | 2021-11-05 | 2020 ITP | 23239179 | 2023 | 24415662.4369 | 23239179 |  | Complete |  |  |  |  | Tap the existing Border to Woodward 345 kV line 19 miles from the Border station and build a new 345 kV substation or switching station
210616 | 81741 | 122848 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Minco 345 kV Terminal Equipment | Economic | 2025-01-29 | 2025-01-01 | 2021-06-04 | 2020 ITP | 1843729 | 2021 | 2035131.8359 | 5170350 |  | Complete | 514801 | Minco 345 kv |  |  | Install terminal equipment at Minco substation 345 kV to support a new 345 kV line from Minco with a summer emergency rating of 1792 MVA | 345
210616 | 81741 | 122849 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Substation (345 kV) | Economic | 2024-11-18 | 2025-01-01 | 2021-06-04 | 2020 ITP | 30707951 | 2021 | 33069104.3913 | 32542389 |  | Complete |  |  |  |  | Expand the existing Pleasant Valley 138 kV substation to 345 kV with new terminals to accommodate new line from Minco to Pleasant Valley to Draper and terminals to accommodate cut in of existing Cimarron to Draper 345 kV line. Tie into existing Cimarron to Draper 345 kV line. This description is specific to the 345 kV components. | 345
210616 | 81741 | 122850 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Transformer Ckt 1 | Economic | 2024-11-18 | 2025-01-01 | 2021-06-04 | 2020 ITP | 5003830 | 2021 | 5388577.5911 | 4836741 |  | Complete |  |  | 514929 | PLEASANT VALLEY 138 | Install a new 345/138 kV transformer to achieve a summer emergency rating of 478 MVA | 345/138
210616 | 81741 | 122851 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Transformer Ckt 2 | Economic | 2024-12-18 | 2025-01-01 | 2021-06-04 | 2020 ITP | 4885649 | 2021 | 5261309.5807 | 4536741 |  | Complete |  |  | 514929 | PLEASANT VALLEY 138 | Install a new 345/138 kV transformer to achieve a summer emergency rating of 478 MVA | 345/138
210616 | 81741 | 122858 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Cimarron - Draper 345 kV Terminal Upgrades #2 | Economic | 2025-01-01 | 2025-01-01 | 2021-06-04 | 2020 ITP | 2541200 | 2021 | 2805009.3161 | 647852 |  | Complete | 514901 | CIMARRON 345 | 514934 | DRAPER LAKE 345 | Upgrade any necessary terminal equipment on the Cimarron to Draper 345 kV line to achieve a summer emergency rating of 1540 MVA
210586 | 81751 | 122864 | WFEC | OK | Sub - Anadarko 138 kV #2 | Anadarko 138 kV Breakers #2 | Regional Reliability | 2025-11-21 | 2022-06-01 | 2020-11-17 | 2020 ITP | 850000 | 2021 | 938240.9565 | 405000 |  | Complete | 520814 | ANADARKO |  |  | Replace 4 breakers at the Anadarko 138 kV station with a 63 kA breakers
210574 | 81758 | 122872 | SPS | TX | Line - Carlisle - Murphy 115 kV #2 | Carlisle - Murphy 115 kV Ckt 1 Rebuild | Regional Reliability | 2026-04-15 | 2022-06-01 | 2020-11-17 | 2020 ITP | 4160581 | 2021 | 4707315.5018 | 5149559 |  | Delay - Mitigation | 526160 | Carlisle Interchange 115 kV | 526192 | Murphy Sub 115 kV | Rebuild 4.0 miles of 115 kV line from Carlisle to Murphy and upgrade any necessary terminal equipment to achieve a summer emergency rating of 240 MVA |  |  | 4
210574 | 81760 | 122876 | SPS | TX | Line - Deaf Smith #6 - Hereford 115 kV | Deaf Smith #6 - Hereford 115 kV Ckt 1 Rebuild | Regional Reliability | 2025-05-08 | 2022-04-01 | 2020-11-17 | 2020 ITP | 6956586 | 2021 | 7678769.2972 | 7325142 |  | Closed Out | 524629 | Deaf Smith REC-#6 115 kV | 524606 | Hereford Interchange 115 kV | Rebuild 2.33 miles of 115 kV line from Deaf Smith #6 to Hereford and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA |  | 7.3
| 81790 | 132936 | ITCGP | KS | Elm Creek-Summit 345 kV | Elm Creek - Summit 345 kV GEN-2017-004 Interconnection (TOIF) (ITCGP) | Generation Interconnection | 2027-07-15 |  |  | GI STUDIES |  |  | 0 | 880335 |  | On Schedule < 4 |  |  |  |  | Construct one (1) set of 345kV CCVTs, two (2) paths of OPGW fiber optic cable, one (1) 345kV line relaying panel, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility
| 81790 | 132937 | ITCGP | KS | Elm Creek-Summit 345 kV | Elm Creek - Summit 345 kV GEN-2017-004 Interconnection (Non-Shared NU) (ITCGP) | Generation Interconnection | 2027-07-15 |  |  | GI STUDIES |  |  | 0 | 13943022 |  | On Schedule < 4 |  |  |  |  | Construct new 345kV 3-breaker ring bus, eight (8) 345kV disconnect switch stands, nineteen (19) 345kV bus supports, four (4) 345kV wave trap stands, three (3) H-frame line entrance structures, six (6) 345kV CCVT stands, six (6) 345kV surge arrester stands, and all other associated work and materials.
| 81796 | 132948 | BEPC | ND | Rhame 230 kV Substation GEN-2017-010 Interconnection Costs | Rhame 230 kV Substation GEN-2017-010 Interconnection (TOIF) (BEPC) | Generation Interconnection | 2025-06-30 |  |  | GI STUDIES |  |  | 0 | 1674744 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 230 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 81796 | 132949 | BEPC | ND | Rhame 230 kV Substation GEN-2017-010 Interconnection Costs | Rhame 230 kV Substation GEN-2017-010 Interconnection (Non-Shared NU) (BEPC) | Generation Interconnection | 2025-06-30 |  |  | GI STUDIES |  |  | 0 | 1122552 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 230kV breaker, one (1) 230kV breaker disconnect switch, one (1) set of line PT, one (1) set of CTs, one (1) set of line surge arrestors and all other associated work and materials.
| 81797 | 132950 | OGE | OK | Badger - Woodward 345 kV GEN-2017-011 Interconnection Costs | Badger - Woodward 345 kV GEN-2017-011 Interconnection (TOIF) (OKGE) | Generation Interconnection | 2026-09-01 |  |  | GI STUDIES |  |  | 0 |  |  | On Schedule < 4 |  |  |  |  | Add one 345kV line terminal to Bobcat Substation. one dead end structure, line switch, line relaying, revenue metering including CTs and PTs
| 81797 | 132951 | OGE | OK | Badger - Woodward 345 kV GEN-2017-011 Interconnection Costs | Badger - Woodward 345 kV GEN-2017-011 Interconnection (Non-Shared NU) (OKGE) | Generation Interconnection | 2026-09-01 |  |  | GI STUDIES |  |  | 0 | 15000 |  | In Service |  |  |  |  | At Bobcat sub, install one-345kV 5000A breaker, line relaying, disconnect switches, and associated equipment
| 81800 | 132956 | WAPA | Sd | Underwood - Philip 230 kV GEN-2017-014 Interconnection Costs | Philip Tap 230 kV GEN-2017-014 Interconnection (TOIF) (WAPA) | Generation Interconnection | 2027-12-31 |  |  | GI STUDIES |  |  | 0 | 400000 |  | In Service |  |  |  |  | Construct one (1) 230kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility
| 81800 | 132957 | WAPA | SD | Underwood - Philip 230 kV GEN-2017-014 Interconnection Costs | Philip Tap 230 kV GEN-2017-014 Interconnection (Non-Shared NU) (WAPA) | Generation Interconnection | 2027-12-31 |  |  | GI STUDIES |  |  | 0 | 12195000 |  | In Service |  |  |  |  | Construct one (1) new WAPA-UGP-owned 230kV switchyard consisting of a four (4) breaker ring bus that includes four (4) 230kV circuit breakers, twelve (12) 230kV disconnect switches, instrument transformers, associated control and protection equipment, high voltage bus, four (4) transmission line take-offstructures, conductor, overhead optical ground wire, communication equipment, and new transmission line structures to re-terminate the four (4) lines into the 230kV switchyard.
| 81802 | 132960 | ITCGP | KS | Multi - Buffalo Flats - Degrasse - Thistle 345 kV Sub | Thistle 345 kV Substation GEN-2017-018 Interconnection (TOIF) (ITCGP) | Generation Interconnection | 2024-12-01 |  |  | GI STUDIES |  |  | 0 | 918132 |  | In Service |  |  |  |  | Construct one (1) set of 345kV CCVTs, two (2) paths of OPGW fiber optic cable, one (1) 345kV line relaying panel, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility
| 81802 | 132961 | ITCGP | KS | Multi - Buffalo Flats - Degrasse - Thistle 345 kV Sub | Thistle 345 kV Substation GEN-2017-018 Interconnection (Non-Shared NU) (ITCGP) | Generation Interconnection | 2024-12-01 |  |  | GI STUDIES |  |  | 0 | 1412092 |  | In Service |  |  |  |  | Construct one (1) 345kV disconnect switch stands, one (1) H-frame line entrance structures, two (2) 345kV CCVT stands, three (3) 345kV surge arrester stands, and all other associated work and materials.
| 81804 | 132964 | EKC | KS | Altoona - Parson 138 kV GEN-2017-022 Interconnection Costs | Altoona - Parson 138 kV GEN-2017-022 Interconnection (TOIF) (EKC) | Generation Interconnection | 2026-07-17 |  |  | GI STUDIES |  |  | 0 | 907068 |  | In Service |  |  |  |  | Construct approximately 0.1 miles of two (2) new single 1192.5 Bunting ACSR lines with two (2) 64mm OPGW static wire, one (1) vertical single pole steel dead-end structure, and no distribution underbuild.
| 81804 | 132965 | EKC | KS | Altoona - Parson 138 kV GEN-2017-022 Interconnection Costs | Altoona - Parson 138 kV GEN-2017-022 Interconnection (Non-Shared NU) (EKC) | Generation Interconnection | 2026-07-17 |  |  | GI STUDIES |  |  | 0 | 5453506 |  | In Service |  |  |  |  | Construct two (2) breakers, two (2) wavetraps, seven (7) switches, six (6) CCVTs, two (2) control panels, and all other associated work and materials. |  | 0.1
| 81805 | 132966 | WFEC | OK | Hugo 138 kV Substation GEN-2017-023 Interconnection Costs | Hugo 138 kV Substation GEN-2017-023 Interconnection (TOIF) (WFEC) | Generation Interconnection | 2026-02-02 |  |  | GI STUDIES |  |  | 0 | 750000 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 138kV terminal connection with breaker, line switches, dead-end structure, line relaying, communications, revenue metering, line arrestor, transmission line to edge of property and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer's Generating Facility
| 81813 | 132982 | AEP | TX | Oklaunion 345 kV Substation GEN-2017-033 Interconnection Costs | Oklaunion 345 kV Substation GEN-2017-033 Interconnection (TOIF) (AEPW) | Generation Interconnection | 2024-04-15 |  |  | GI STUDIES |  |  | 0 | 1436587 |  | In Service |  |  |  |  | Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 81813 | 132983 | AEP | TX | Oklaunion 345 kV Substation GEN-2017-033 Interconnection Costs | Oklaunion 345 kV Substation GEN-2017-033 Interconnection (Non-Shared NU) (AEPW) | Generation Interconnection | 2024-04-15 |  |  | GI STUDIES |  |  | 0 | 4000000 |  | In Service |  |  |  |  | Construct two (2) new 345kV breakers, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 81814 | 132984 | AEP | OK | Snyder 138 kV Substation GEN-2017-036 Interconnection Costs | Snyder - Cache 138 kV GEN-2017-036 Interconnection (TOIF) (AEPW) | Generation Interconnection | 2024-09-15 |  |  | GI STUDIES |  |  | 0 | 1114451 |  | In Service |  |  |  |  | Construct one (1) 138 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 81814 | 132985 | AEP | OK | Snyder 138 kV Substation GEN-2017-036 Interconnection Costs | Snyder - Cache 138 kV GEN-2017-036 Interconnection (Non-Shared NU) (AEPW) | Generation Interconnection | 2024-09-15 |  |  | GI STUDIES |  |  | 0 | 8923402 |  | In Service |  |  |  |  | Construct new 138 kV three (3) breaker ring bus, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators ,and all other associated work and materials.
| 81818 | 132992 | OGE | OK | Canadian River - Muskogee - Seminole 345 kV GEN-2017-040 Interconnection Costs | Canadian River - Muskogee - Seminole 345 kV GEN-2017-040 Interconnection (TOIF) (OKGE) | Generation Interconnection | 2025-12-31 |  |  | GI STUDIES |  |  | 0 | 599979 |  | In Service |  |  |  |  | Add a single 345kV line terminal to a new Substation. Dead end structure, line switch, line relaying, revenue metering including CTs and PTs
| 81818 | 132993 | OGE | OK | Canadian River - Muskogee - Seminole 345 kV GEN-2017-040 Interconnection Costs | Canadian River - Muskogee - Seminole 345 kV GEN-2017-040 Interconnection (Shared NU) (OKGE) | Generation Interconnection | 2025-12-01 |  |  | GI STUDIES |  |  | 0 | 5741321 |  | In Service |  |  |  |  | At a new sub, Install 5-345kV 3000A breakers, line relaying, bus work, disconnect switches, and associated equipment.
| 81820 | 132996 | SPS | OK | Cole 115 kV Substation GEN-2017-047 Interconnection Costs | Cole 115 kV Substation GEN-2017-047 Interconnection (TOIF) (SWPS) | Generation Interconnection | 2024-11-01 |  |  | GI STUDIES |  |  | 0 | 0 |  | In Service |  |  |  |  | Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility
| 81820 | 132997 | SPS | OK | Cole 115 kV Substation GEN-2017-047 Interconnection Costs | Cole 115 kV Substation GEN-2017-047 Interconnection (Non-Shared NU) (SWPS) | Generation Interconnection | 2024-11-01 |  |  | GI STUDIES |  |  | 0 | 0 |  | In Service |  |  |  |  | Construct one (1) greenfield 115kV Bull Creek substation to include rerouting 115kV lines into substation, remote end upgrades and removals, communications equipment, and all other associated work and materials. |  | 2
| 81821 | 132998 | BEPC | ND | Neset 230 kV Substation GEN-2017-048 Interconnection Costs | Neset 230 kV Substation GEN-2017-048 Interconnection (TOIF) (BEPC) | Generation Interconnection | 2026-10-01 |  |  | GI STUDIES |  |  | 0 | 1683828 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 230 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility.
| 81821 | 132999 | BEPC | ND | Neset 230 kV Substation GEN-2017-048 Interconnection Costs | Neset 230 kV Substation GEN-2017-048 Interconnection (Non-Shared NU) (BEPC) | Generation Interconnection | 2026-10-01 |  |  | GI STUDIES |  |  | 0 | 1296018 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 230kV breaker, one (1) 230kV breaker disconnect switch, one (1) set of line PT, one (1) set of CTs, one (1) set of line surge arrestors and all other associated work and materials.
| 81828 | 133012 | AEP | LA | Houston 69 kV Substation GEN-2017-057 Interconnection Costs | Hosston 69 kV Substation GEN-2017-057 Interconnection (TOIF) (AEPW) | Generation Interconnection | 2024-09-15 |  |  | GI STUDIES |  |  | 0 | 1086124 |  | In Service |  |  |  |  | Construct one (1) 69 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility
| 81828 | 133013 | AEP | LA | Houston 69 kV Substation GEN-2017-057 Interconnection Costs | Hosston 69 kV Substation GEN-2017-057 Interconnection (Non-Shared NU) (AEPW) | Generation Interconnection | 2024-09-15 |  |  | GI STUDIES |  |  | 0 | 17635037 |  | In Service |  |  |  |  | Rebuild Hosston 69kV as a five (5) breaker ring bus to include control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 81832 | 133020 | GRDA | OK | GRDA1 - CLARMR5 161 kV GEN-2017-061 Interconnection Costs | GRDA1 - CLARMR5 161 kV GEN-2017-061 Interconnection (TOIF) (GRDA) | Generation Interconnection | 2025-06-01 |  |  | GI STUDIES |  |  | 0 | 715000 |  | On Schedule < 4 |  |  |  |  | Add a single 161kV line terminal to the new 161kV interconnect substation. Dead end structure, line switch, line relaying, CCVTs, arrestors, bus support, (interconnect customer to install/own their interconnect metering including CTs and PTs - at their low voltage facility, GRDA may request to install parallel meter with biasing), communications, and all other associated equipment to terminate the line.
| 81832 | 133021 | GRDA | OK | GRDA1 - CLARMR5 161 kV GEN-2017-061 Interconnection Costs | GRDA1 - CLARMR5 161 kV GEN-2017-061 Interconnection (Non-Shared NU) (GRDA) | Generation Interconnection | 2025-06-01 |  |  | GI STUDIES |  |  | 0 | 3728000 |  | On Schedule < 4 |  |  |  |  | Construct one (1) greenfield 161kV substation; 161kV breakers, disconnect switches, control panels, conductor, foundations, insulators and all other associated work and materials.
| 81837 | 133030 | EKC | KS | Wichita 345 kV Substation GEN-2017-068 Interconnection Costs | Gordon Evans 138 kV Substation GEN-2017-068 Interconnection (TOIF) (EKC) | Generation Interconnection | 2028-03-15 |  |  | GI STUDIES |  |  | 0 | 687462 |  | In Service |  |  |  |  | Construct one (1) new 138kV dead-end, three (3) new voltage transformers, three (3) new current transformers, and one (1) new line panel, , and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility
| 81837 | 133031 | EKC | KS | Wichita 345 kV Substation GEN-2017-068 Interconnection Costs | Gordon Evans 138 kV Substation GEN-2017-068 Interconnection (Non-Shared NU) (EKC) | Generation Interconnection | 2028-03-15 |  |  | GI STUDIES |  |  | 0 | 1485126 |  | In Service |  |  |  |  | Construct two (2) new 138kV circuit breakers, four (4) new 138kV disconnect switches, one (1) new breaker panel, and all other associated work and materials.
| 81839 | 133034 | OGE | OK | Greenwood 138 kV Substation GEN-2017-071 Interconnection Costs | Greenwood 138 kV Substation GEN-2017-071 Interconnection (TOIF) (OKGE) | Generation Interconnection | 2025-05-30 |  |  | GI STUDIES |  |  | 0 | 515000 |  | Complete |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-071 (124.7 MW/Solar), into the Point of Interconnection (POI) at Greenwood 138 kV Substation.
| 81840 | 133036 | OGE | OK | Greenwood 138 kV Substation GEN-2017-072 Interconnection Costs | Greenwood 138 kV Substation GEN-2017-072 Interconnection (TOIF) (OKGE) | Generation Interconnection | 2025-05-30 |  |  | GI STUDIES |  |  | 0 | 515000 |  | Complete |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-072 (52.2 MW/Solar), into the Point of Interconnection (POI) at Greenwood 138 kV Substation.
| 81840 | 133037 | OGE | OK | Greenwood 138 kV Substation GEN-2017-072 Interconnection Costs | Greenwood 138 kV Interconnection Expansion (DISIS-2017-001) | Generation Interconnection | 2025-04-30 |  |  | GI STUDIES |  |  | 0 | 1721000 |  | Complete |  |  |  |  | At Greenwood Sub, expand sub and ground grid, expand ring bus to East, Install 1- 138kV 2000A breaker, line relaying, disconnect switches, and associated equipment, Re-route Greenwood – Cushing Tap line into Greenwood Substation
| 81841 | 133038 | GRDA | OK | Dry Gulch 161 kV Substation GEN-2017-073 Interconnection Costs | Dry Gulch 161 kV Substation GEN-2017-073 Interconnection (TOIF) (GRDA) | Generation Interconnection | 2025-06-01 |  |  | GI STUDIES |  |  | 0 | 1100000 |  | On Schedule < 4 |  |  |  |  | Add a single 161kV line terminal to an existing 161kV Substation. Dead end structure, line switch, line relaying, CCVTs, arrestors, bus support, interconnect metering including CTs and PTs, communications, and all other associated equipment to terminate the line from interconnect customer’s generator facility.
| 81841 | 133039 | GRDA | OK | Dry Gulch 161 kV Substation GEN-2017-073 Interconnection Costs | Dry Gulch 161 kV Substation GEN-2017-073 Interconnection (Non-Shared NU) (GRDA) | Generation Interconnection | 2025-06-01 |  |  | GI STUDIES |  |  | 0 | 810900 |  | On Schedule < 4 |  |  |  |  | At an existing substation; 161kV breaker, disconnect switches, control panel, conductor, foundations, insulators and all other associated work and materials.
| 81842 | 133040 | AEP | OK | Pryor Junction 138 kV Substation GEN-2017-074 Interconnection Costs | Pryor Junction 138 kV Substation GEN-2017-074 Interconnection (TOIF) (AEPW) | Generation Interconnection | 2025-05-01 |  |  | GI STUDIES |  |  | 0 | 1114451 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 138 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility
| 81842 | 133041 | AEP | OK | Pryor Junction 138 kV Substation GEN-2017-074 Interconnection Costs | Pryor Junction 138 kV Substation GEN-2017-074 Interconnection (Non-Shared NU) (AEPW) | Generation Interconnection | 2025-05-01 |  |  | GI STUDIES |  |  | 0 | 1451533 |  | On Schedule < 4 |  |  |  |  | Expand Pryor Junction 138kV to a six (6) breaker ring bus to include control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 81843 | 133042 | OGE | OK | Hugo - Sunnyside 345 kV GEN-2017-075 Interconnection Costs | Hugo - Sunnyside 345 kV GEN-2017-075 Interconnection (TOIF) (OKGE) | Generation Interconnection | 2026-05-01 |  |  | GI STUDIES |  |  | 0 | 915000 |  | On Schedule < 4 |  |  |  |  | Add a single 345kV line terminal a new EHV substation. Dead end structure, line relaying, revenue metering including CTs and PTs
| 81843 | 133043 | OGE | OK | Hugo - Sunnyside 345 kV GEN-2017-075 Interconnection Costs | Hugo - Sunnyside 345 kV GEN-2017-075 Interconnection (Non-Shared NU) (OKGE) | Generation Interconnection | 2026-05-01 |  |  | GI STUDIES |  |  | 0 | 1430000 |  | On Schedule < 4 |  |  |  |  | At a new EHV sub, Install 1-345kV 3000A breakers, line relaying, disconnect switches, and associated equipment.
| 81844 | 133044 | AEP | AR | Chamber Springs 161 kV Substation GEN-2017-076 Interconnection Costs | Chamber Springs 161 kV Substation GEN-2017-076 Interconnection (TOIF) (AEPW) | Generation Interconnection | 2024-09-01 |  |  | GI STUDIES |  |  | 0 | 1125771 |  | In Service |  |  |  |  | Construct one (1) 161 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility
| 81844 | 133045 | AEP | AR | Chamber Springs 161 kV Substation GEN-2017-076 Interconnection Costs | Chamber Springs 161 kV Substation GEN-2017-076 Interconnection (Non-Shared NU) (AEPW) | Generation Interconnection | 2024-09-01 |  |  | GI STUDIES |  |  | 0 | 1419431 |  | In Service |  |  |  |  | Construct one (1) new 345kV breaker, control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 81845 | 133046 | AEP | OK | Explorer - Claremore 69 kV GEN-2017-077 Interconnection Costs | Explorer - Claremore 69 kV GEN-2017-077 Interconnection (TOIF) (AEPW) | Generation Interconnection | 2025-05-01 |  |  | GI STUDIES |  |  | 0 | 1114451 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 69 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility
| 81845 | 133047 | AEP | OK | Explorer - Claremore 69 kV GEN-2017-077 Interconnection Costs | Explorer - Claremore 69 kV GEN-2017-077 Interconnection (Non-Shared NU) (AEPW) | Generation Interconnection | 2025-05-01 |  |  | GI STUDIES |  |  | 0 | 11733632 |  | On Schedule < 4 |  |  |  |  | Rebuild Explorer - Claremore Tap 138 kV as a four (4) breaker ring bus to include control panels, line relaying, disconnect switches, structures, foundations, conductors, insulators, and all other associated work and materials.
| 81854 | 133064 | EKC | KS | Sub - Renfrow 345 kV | Viola 345 kV Substation GEN-2017-086 Interconnection (TOIF) (EKC) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 0 |  | In Service |  |  |  |  | No upgrade needed
| 81858 | 133072 | OGE | OK | Canadian River - Muskogee - Seminole GEN-2017-092 345 kV Interconnection Costs | Canadian River - Muskogee - Seminole 345 kV GEN-2017-092 Interconnection (TOIF) (OKGE) | Generation Interconnection | 2025-12-01 |  |  | GI STUDIES |  |  | 0 | 599979 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-092 (200 MW/Solar), into the Point of Interconnection (POI) at Canadian River - Muskogee - Seminole
| 81858 | 133073 | OGE | OK | Canadian River - Muskogee - Seminole GEN-2017-092 345 kV Interconnection Costs | Canadian River - Muskogee - Seminole 345 kV GEN-2017-092 Interconnection (Non-Shared NU) (OKGE) | Generation Interconnection | 2025-12-30 |  |  | GI STUDIES |  |  | 0 | 5741321 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-092 (200 MW/Solar), into the Point of Interconnection (POI) at Canadian River - Muskogee - Seminole
| 81862 | 133080 | SPS | OK | Texas County 115 kV Substation GEN-2017-100 Inteconnection Costs | Texas County 115 kV Substation GEN-2017-100 Inteconnection (TOIF) (SWPS) | Generation Interconnection | 2025-10-14 |  |  | GI STUDIES |  |  | 0 | 0 |  | On Schedule < 4 |  |  |  |  | Construct one (1) 345 kV line terminal, line switches, dead end structure, line relaying, communications, revenue metering, line arrestor, and all associated equipment and facilities necessary to accept transmission line from Interconnection Customer’s Generating Facility
| 81862 | 133081 | SPS | OK | Texas County 115 kV Substation GEN-2017-100 Inteconnection Costs | Texas County 115 kV Substation GEN-2017-100 Inteconnection (Non-Shared NU) (SWPS) | Generation Interconnection | 2025-10-14 |  |  | GI STUDIES |  |  | 0 | 0 |  | On Schedule < 4 |  |  |  |  | Construct one (1) greenfield 115kV Guymon South substation to include rerouting 115kV lines into substation, remote end upgrades, communications equipment, and all other associated work and materials.
210670 | 81741 | 133085 | NEET | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Minco - Pleasant Valley 345 kV Ckt 1 | Economic | 2025-01-29 | 2025-01-01 | 2022-04-28 | 2020 ITP | 38537430 | 2022 | 41500596.8859 | 38537430 |  | Complete |  |  |  |  | Build 34.8 miles of 345 kV line from Minco to Pleasant Valley 345 kV to achieve a 1792 MVA summer emergency rating. | 345
210670 | 81741 | 133106 | NEET | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Draper - Pleasant Valley 345 kV Ckt 2 | Economic | 2025-01-23 | 2025-01-01 | 2022-04-28 | 2020 ITP | 16516041 | 2022 | 17785969.6324 | 16516041 |  | Complete |  |  |  |  | Build a second 13.2-mile 345 kV line from Draper 345 kV substation to Pleasant Valley 345 kV substation with a summer emergency rating of 1792 MVA | 345
210677 | 81802 | 143117 | OGE | KS | Multi - Buffalo Flats - Degrasse - Thistle 345 kV Sub | Degrasse345 kV Substation | Generation Interconnection | 2024-06-01 | 2024-07-12 | 2022-06-22 | DISIS-2017-001 | 30000 | 2022 | 31518.75 | 30000 |  | In Service |  |  |  |  | Update relay settings at Degrasse 345 kV Substation.
210676 | 81802 | 143118 | EKC | KS | Multi - Buffalo Flats - Degrasse - Thistle 345 kV Sub | Buffalo Flats 345 kV | Generation Interconnection | 2024-05-29 | 2024-07-12 | 2022-06-22 | DISIS-2017-001 | 13299 | 2022 | 13972.2619 | 0 |  | In Service |  |  |  |  | Review relay settings and apply adjusted settings at Buffalo Flats 345 kV substation.
210704 | 81854 | 143125 | OGE | KS/ | Sub - Renfrow 345 kV | Renfrow 345 kV Substation | Generation Interconnection | 2024-05-08 | 2024-10-31 | 2022-10-16 | DISIS-2017-001 | 20000 | 2023 | 20500 | 20000 |  | In Service |  |  |  |  | Update relay settings and records at Renfrow 345 kV Substation for the Renfrow to Viola 345 kV line for interconnection of GEN-2017-086 at Viola 345 kV.
210643 | 81773 | 143127 | OGE | OK | Sub - Chisholm - Gracemont 345 kV | Gracemont 345 kV | Generation Interconnection | 2022-08-31 | 2022-09-01 | 2022-02-25 | DISIS-2017-001 | 15000 | 2022 | 15000 | 15000 |  | On Schedule < 4 |  |  |  |  | At the existing Gracmont 345 kV substation, update relay settings to accommodate new protection settings.
210717 | 81790 | 143151 | EKC | OK | Elm Creek-Summit 345 kV | Summit 345 kV GEN-2017-004 Interconnection (Non-Shared Network Upgrade (NU)) (EKC) | Generation Interconnection | 2025-07-18 | 2025-07-18 | 2022-12-13 | DISIS-2017-001 | 24937 | 2023 | 26199.4356 | 24936 |  | On Schedule < 4 |  |  |  |  | Review relay settings and apply adjusted settings at Summit 345kV substation.
210579 | 91876 | 143157 | WAPA | ND/ | Device - Bismarck 12.47 kV | Bismarck 12.47 kV Reactors | Regional Reliability | 2023-11-30 | 2022-04-01 | 2020-11-23 | 2020 ITP | 2143217 | 2021 | 2251717.3606 | 2906871.77 | 2906871.77 | Complete |  |  |  |  | Install 2x35 MVAR reactors at Bismarck to control voltage on the 230 kV transmission system
210616 | 81741 | 143176 | OGE | OK | Multi - Minco - Pleasant Valley - Draper 345 kV | Draper 345 kV Terminal Equipment | Economic | 2025-01-23 | 2025-01-01 | 2021-06-04 | 2020 ITP | 6484533 | 2021 | 7157711.111 | 7099323 | 6264467.52 | Complete |  |  |  |  | Install a new line terminal at Draper 345 kV to accommodate new 345 kV line from Pleasant Valley.
210584 | 81497 | 143181 | EREC | SD | Multi - Aberdeen Junction - Richmond 115 kV | Aberdeen Jct - Richmond 115 kV Ckt 1 (NWE) | Regional Reliability | 2021-11-30 | 2022-12-01 | 2020-11-17 | 2020 ITP | 3277500 | 2021 | 3277500 | 3277500 |  | Complete |  |  |  |  | Build a new 13.5 mile 115 kV line from Aberdeen Junction to Richmond to achieve a summer emergency rating of 139 MVA
210627 | 81717 | 143182 | AEP | OK// | Multi - Border - Woodward 345 kV Tap | Chisholm - Woodward - Border 345 kV Ckt 1 (AEP) | Economic | 2025-12-11 | 2022-01-01 | 2021-11-05 | 2020 ITP | 9059992 | 2023 | 9518654.095 | 12238460 |  | Delay - Mitigation |  |  |  |  | Build 0.84-miles of new 345 kV line from a new tap on the Woodward to Border 345 kV line to Chisholm with a summer emergency rating of 1792 MVA. Oklahoma Gas and Electric Co. and American Electric Power shall decide who shall build how much of these Network Upgrades and shall provide such information, along with specific cost estimates for each DTO's portion of the Network Upgrades, to SPP in its response to this NTC | 345 | 1
| 91918 | 143226 | BEPC | SD | Broadland 345/230kV Transformer Replacement | Broadland 345/230kV Transformer Replacement (DISIS-2017-001) | Generation Interconnection | 2025-05-14 |  |  | GI STUDIES |  |  | 0 | 10061320 |  | Closed Out | 659205 | BROADLAND |  |  | Replace the existing Broadland 345/230kV Transformer to achieve a minimum Summer/Normal rating of 471 MVA
| 91924 | 143236 | BEPC | ND | Neset to Tioga 230kV Rebuild | Neset to Tioga 230kV Rebuild (DISIS-2017-001) (BEPC) | Generation Interconnection | 2026-10-01 |  |  | GI STUDIES |  |  | 0 | 437516 |  | On Schedule < 4 |  |  |  |  | Rebuild the existing Neset to Tioga 230kV 1.0 mile line to achieve a minimum Summer/Emergency rating of 725 MVA | 230 |  | 1
| 91925 | 143237 | MDU | KS | Tioga 230kV Terminal Upgrades | Tioga 230kV Terminal Upgrades (DISIS-2017-001) (MDU) | Generation Interconnection | 2027-08-01 |  |  | GI STUDIES |  |  | 0 | 800000 |  | On Schedule < 4 |  |  |  |  | Upgrade terminal equipment at Tioga 230kV to achieve a minimum Summer/Emergency rating of 725 MVA
210617 | 91939 | 143253 | WFEC | OK | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Paoli - Lexington kV 138 kV | Regional Reliability | 2025-07-31 | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 7865000 | 2021 | 8681488.3799 | 10608616 |  | Complete | 521022 | PAOLI | 520973 | LEXINGTON | Rebuild 14.3 miles of 69 kV line from Paoli to Lexington to 138 kV | 69
210617 | 91939 | 143254 | WFEC | OK | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Lexington - Lil Axe 138 kV | Regional Reliability | 2025-12-31 | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 5340500 | 2021 | 5894912.739 | 7378510 |  | Delay - Mitigation | 520973 | LEXINGTON | 520976 | LITTLE AXE | Rebuild 9.7 miles of 69 kV line from Lexington to Lil Axe to 138 kV | 69
210617 | 91939 | 143255 | WFEC | OK | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Paoli 138 kV Terminal Upgrades | Regional Reliability | 2025-07-30 | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 450000 | 2021 | 496715.8005 | 2225000 |  | Complete |  |  |  |  | Convert 69 kV terminal equipment at Paoli Switch to 138 kV
210617 | 91939 | 143256 | WFEC | OK | Multi - Lil Axe - Lexington 138 kV Voltage Conversion | Canadian Switch138 kV Terminal Upgrades | Regional Reliability | 2026-09-30 | 2021-06-01 | 2021-10-11 | DPA-2020-May-1203 | 500000 | 2021 | 565704.105 | 1170000 |  | Delay - Mitigation |  |  |  |  | Convert 69 kV terminal equipment at Canadian Switch to 138 kV
210616 | 81741 | 143257 | OGE | OK/ | Multi - Minco - Pleasant Valley - Draper 345 kV | Pleasant Valley 345/138 kV Substation (138 kV) | Economic | 2024-12-18 | 2025-01-01 | 2021-06-04 | 2020 ITP | 10112621 | 2021 | 10890186.6985 | 28449977 |  | Complete |  |  |  |  | Expand the existing Pleasant Valley 138 kV substation to 345 kV with new terminals to accommodate new line from Minco to Pleasant Valley to Draper. This description is specific to the 138 kV components.
| 91996 | 143336 | OPPD | NE | Tekamah - Raun 161 kV Line GEN-2017-105 Interconnection Costs | Tekamah - Raun 161kV GEN-2017-105 Interconnection (Non-Shared NU) (OPPD) | Generation Interconnection | 2026-10-01 |  |  | GI STUDIES |  |  | 0 | 6684356 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-105 (75 MW/Wind), into the Point of Interconnection (POI) at Tekamah - Raun 161kV | 161
| 91996 | 143337 | OPPD | NE | Tekamah - Raun 161 kV Line GEN-2017-105 Interconnection Costs | Tekamah - Raun 161kV GEN-2017-105 Interconnection (TOIF) (OPPD) | Generation Interconnection | 2026-10-01 |  |  | GI STUDIES |  |  | 0 | 3142178 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-105 (75 MW/Wind), into the Point of Interconnection (POI) at Tekamah - Raun 161kV | 161
| 91999 | 143342 | EMW | TX | Stillwell - Clinton 161kV Line GEN-2017-108 Interconnection Costs | Stillwell - Clinton 161kV New Three (3) Breaker Ring Bus Interconnection Substation (DISIS-2017-002) | Generation Interconnection | 2027-03-01 |  |  | GI STUDIES |  |  | 0 | 24477708 |  | In Service |  |  |  |  | Construct a new three breaker ring bus Stillwell - Clinton 161kV substation to accommodate the interconnection of GEN-2017-108 | 161
| 91999 | 143343 | EMW | MO | Stillwell - Clinton 161kV Line GEN-2017-108 Interconnection Costs | Stillwell - Clinton 161kV GEN-2017-108 Interconnection (TOIF) (KCPL) | Generation Interconnection | 2027-03-01 |  |  | GI STUDIES |  |  | 0 | 1288300 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-108 (400 MW/Solar), into the Point of Interconnection (POI) at Stillwell - Clinton 161kV | 161
| 92005 | 143354 | KCPL | MO | Holt County 345 kV GEN-2017-115 Interconnection Costs | Holt County 345kV GEN-2017-115 Interconnection (Non-Shared NU) (KCPL) | Generation Interconnection | 2030-03-22 |  |  | GI STUDIES |  |  | 0 | 3237862 |  | On Schedule > 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-115 (244 MW/Wind), into the Point of Interconnection (POI) at Holt County 345kV | 345
| 92005 | 143355 | KCPL | MO | Holt County 345 kV GEN-2017-115 Interconnection Costs | Holt County 345kV GEN-2017-115 Interconnection (TOIF) (KCPL) | Generation Interconnection | 2030-03-22 |  |  | GI STUDIES |  |  | 0 | 2061421 |  | On Schedule > 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-115 (244 MW/Wind), into the Point of Interconnection (POI) at Holt County 345kV | 345
| 92007 | 143358 | WFEC | OK | El Reno SW 138kV GEN-2017-117 Interconnection Costs | El Reno SW 138kV GEN-2017-117 Interconnection (Non-Shared NU) (WFEC) | Generation Interconnection | 2026-09-15 |  |  | GI STUDIES |  |  | 0 | 550000 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-117 (19.8 MW/Battery), into the Point of Interconnection (POI) at El Reno SW 138kV | 138
| 92007 | 143359 | WFEC | OK | El Reno SW 138kV GEN-2017-117 Interconnection Costs | El Reno SW 138kV GEN-2017-117 Interconnection (TOIF) (WFEC) | Generation Interconnection | 2026-09-15 |  |  | GI STUDIES |  |  | 0 | 550000 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-117 (19.8 MW/Battery), into the Point of Interconnection (POI) at El Reno SW 138kV | 138
| 92008 | 143360 | ITCGP | KS | Elm Creek 345kV substation GEN-2017-118 Interconnection Costs | Elm Creek 345kV Interconnection Expansion (DISIS-2017-002) | Generation Interconnection | 2027-09-08 |  |  | GI STUDIES |  |  | 0 | 3404822 |  | On Schedule < 4 |  |  |  |  | Expand the Elm Creek 345kV substation to accommodate the interconnection of GEN-2017-119 | 345
| 92009 | 143363 | ITCGP | KS | Elm Creek 345kV substation GEN-2017-119 Interconnection Costs | Elm Creek 345kV GEN-2017-119 Interconnection (TOIF) (ITCGP) | Generation Interconnection | 2027-09-08 |  |  | GI STUDIES |  |  | 0 | 805608 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-119 (260 MW/Wind), into the Point of Interconnection (POI) at Elm Creek 345kV | 345
| 92010 | 143364 | WR | KS | Abilene Energy Center-Northview 115kV GEN-2017-120 Interconnection Costs | Abilene Energy Center - Northview 115kV GEN-2017-120 Interconnection (Non-Shared NU) (WERE) | Generation Interconnection | 2027-11-01 |  |  | GI STUDIES |  |  | 0 | 16044024 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-120 (260 MW/Wind), into the Point of Interconnection (POI) at Abilene Energy Center - Northview 115kV | 115
| 92010 | 143365 | WR | KS | Abilene Energy Center-Northview 115kV GEN-2017-120 Interconnection Costs | Abilene Energy Center - Northview 115kV GEN-2017-120 Interconnection (TOIF) (WERE) | Generation Interconnection | 2027-11-01 |  |  | GI STUDIES |  |  | 0 | 1280256 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-120 (260 MW/Wind), into the Point of Interconnection (POI) at Abilene Energy Center - Northview 115kV | 115
| 92011 | 143366 | WR | KS | Sumner 138kV GEN-2017-121 Interconnection Costs | Sumner 138kV GEN-2017-121 Interconnection (Non-Shared NU) (WERE) | Generation Interconnection | 2026-10-01 |  |  | GI STUDIES |  |  | 0 | 591564 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-121 (200 MW/Wind), into the Point of Interconnection (POI) at Sumner 138kV | 138
| 92011 | 143367 | WR | KS | Sumner 138kV GEN-2017-121 Interconnection Costs | Sumner 138kV GEN-2017-121 Interconnection (TOIF) (WERE) | Generation Interconnection | 2026-10-01 |  |  | GI STUDIES |  |  | 0 | 872040 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-121 (200 MW/Wind), into the Point of Interconnection (POI) at Sumner 138kV | 138
| 92015 | 143374 | WR | KS | Altoona- NE Parson 138kV GEN-2017-131 Interconnection Costs | Altoona - NE Parson 138kV GEN-2017-131 Interconnection (Non-Shared NU) (WERE) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 |  |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-131 (29.6 MW/Battery), into the Point of Interconnection (POI) at Altoona - NE Parson 138kV | 138
| 92015 | 143375 | WR | KS | Altoona- NE Parson 138kV GEN-2017-131 Interconnection Costs | Altoona - NE Parson 138kV GEN-2017-131 Interconnection (TOIF) (WERE) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 24762 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-131 (29.6 MW/Battery), into the Point of Interconnection (POI) at Altoona - NE Parson 138kV | 138
| 92016 | 143376 | OGE | OK | Arcadia 345kV GEN-2017-132 Interconnection Costs | Arcadia 345kV Interconnection Expansion (DISIS-2017-002) | Generation Interconnection | 2028-06-29 |  |  | GI STUDIES |  |  | 0 | 11894705 |  | On Schedule > 4 |  |  |  |  | Expand the Arcadia 345kV substation to accommodate the interconnection of GEN-2017-132, GEN-2017-133, GEN-2017-134, GEN-2017-137 | 345
| 92017 | 143379 | OGE | OK | Arcadia 345kV GEN-2017-133 Interconnection Costs | Arcadia 345kV GEN-2017-133 Interconnection (TOIF) (OGE) | Generation Interconnection | 2028-06-29 |  |  | GI STUDIES |  |  | 0 | 397914 |  | On Schedule > 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-133 (200 MW/Wind), into the Point of Interconnection (POI) at Arcadia 345kV | 345
| 92018 | 143381 | OGE | OK | Arcadia 345kV GEN-2017-134 Interconnection Costs | Arcadia 345kV GEN-2017-134 Interconnection (TOIF) (OGE) | Generation Interconnection | 2028-06-29 |  |  | GI STUDIES |  |  | 0 | 397913 |  | On Schedule > 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-134 (250 MW/Wind), into the Point of Interconnection (POI) at Arcadia 345kV | 345
| 92019 | 143383 | OGE | OK | Arcadia 345kV GEN-2017-137 Interconnection Costs | Arcadia 345kV GEN-2017-137 Interconnection (TOIF) (OGE) | Generation Interconnection | 2028-06-29 |  |  | GI STUDIES |  |  | 0 | 397913 |  | On Schedule > 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-137 (295 MW/Wind), into the Point of Interconnection (POI) at Arcadia 345kV | 345
| 92020 | 143384 | AEP | OK | Clarksville 345kV Switching Station GEN-2017-140 Interconnection Costs | Clarksville 345kV Interconnection Expansion (DISIS-2017-002) | Generation Interconnection | 2027-06-30 |  |  | GI STUDIES |  |  | 0 | 8281070 |  | On Schedule < 4 |  |  |  |  | Expand the Clarksville 345kV substation to accommodate the interconnection of GEN-2017-140, GEN-2017-141, and GEN-2017-213 | 345
| 92020 | 143385 | AEP | OK | Clarksville 345kV Switching Station GEN-2017-140 Interconnection Costs | Clarksville 345kV GEN-2017-140 Interconnection (TOIF) (AEP) | Generation Interconnection | 2027-06-30 |  |  | GI STUDIES |  |  | 0 | 2936547 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-140 (160 MW/Solar), into the Point of Interconnection (POI) at Clarksville 345kV | 345
| 92021 | 143387 | AEP | OK | Clarksville 345kV Switching Station GEN-2017-141 Interconnection Costs | Clarksville 345kV GEN-2017-141 Interconnection (TOIF) (AEP) | Generation Interconnection | 2027-06-30 |  |  | GI STUDIES |  |  | 0 | 2936547 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-141 (241.7 MW/Solar), into the Point of Interconnection (POI) at Clarksville 345kV | 345
| 92023 | 143390 | NPPD | NE | Holt County 345kV GEN-2017-144 Interconnection Costs | Holt County 345kV GEN-2017-144 Interconnection (Non-Shared NU) (NPPD) | Generation Interconnection | 2028-05-01 |  |  | GI STUDIES |  |  | 0 | 2500000 |  | On Schedule > 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-144 (200 MW/Wind), into the Point of Interconnection (POI) at Holt County 345kV | 345
| 92025 | 143395 | SPS | TX | Deaf Smith-Plant X 230kV GEN-2017-146 Interconnection Costs | Deaf Smith - Plant X 230kV GEN-2017-146 Interconnection (TOIF) (SPS) | Generation Interconnection | 2026-08-01 |  |  | GI STUDIES |  |  | 0 | 1284071 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-146 (151.8 MW/Wind), into the Point of Interconnection (POI) at Deaf Smith - Plant X 230kV | 230
| 92027 | 143398 | EDE | KS | Joplin 161kV sub GEN-2017-148 Interconnection Costs | Joplin 161kV GEN-2017-148 Interconnection (Non-Shared NU) (EDE) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 17000000 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-148 (202 MW/Wind), into the Point of Interconnection (POI) at Joplin 161kV | 161
| 92027 | 143399 | EDE | KS | Joplin 161kV sub GEN-2017-148 Interconnection Costs | Joplin 161kV GEN-2017-148 Interconnection (TOIF) (EDE) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 2901000 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-148 (202 MW/Wind), into the Point of Interconnection (POI) at Joplin 161kV | 161
| 92028 | 143400 | OGE | OK | Johnson County 345kV Substation GEN-2017-149 Interconnection Costs | Johnson County 345kV Interconnection Expansion (DISIS-2017-002) | Generation Interconnection | 2027-03-01 |  |  | GI STUDIES |  |  | 0 | 11024448 |  | In Service |  |  |  |  | Expand the Johnson County 345kV substation to accommodate the interconnection of GEN-2017-149 and GEN-2017-154 | 345
| 92028 | 143401 | OGE | OK | Johnson County 345kV Substation GEN-2017-149 Interconnection Costs | Johnson County 345kV GEN-2017-149 Interconnection (TOIF) (OGE) | Generation Interconnection | 2027-03-01 |  |  | GI STUDIES |  |  | 0 | 795827 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-149 (258 MW/Wind), into the Point of Interconnection (POI) at Johnson County 345kV | 345
| 92029 | 143402 | OGE | OK | Minco 345kV GEN-2017-150 Interconnection Costs | Minco 345kV Interconnection Expansion (DISIS-2017-002) | Generation Interconnection | 2025-01-29 |  |  | GI STUDIES |  |  | 0 | 4627433 |  | Complete |  |  |  |  | Expand the Minco 345kV substation to accommodate the interconnection of GEN-2017-150 and GEN-2017-233 | 345
| 92029 | 143403 | OGE | OK | Minco 345kV GEN-2017-150 Interconnection Costs | Minco 345kV GEN-2017-150 Interconnection (TOIF) (OGE) | Generation Interconnection | 2026-09-28 |  |  | GI STUDIES |  |  | 0 | 795827 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-150 (250 MW/Solar), into the Point of Interconnection (POI) at Minco 345kV | 345
| 92030 | 143404 | SPS | TX | TUCO-Oklaunion 345kV GEN-2017-151 Interconnection Costs | TUCO - Oklaunion 345kV GEN-2017-151 Interconnection (Non-Shared NU) (SPS) | Generation Interconnection | 2026-08-01 |  |  | GI STUDIES |  |  | 0 | 18991049 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-151 (300 MW/Wind), into the Point of Interconnection (POI) at TUCO - Oklaunion 345kV | 345
| 92030 | 143405 | SPS | TX | TUCO-Oklaunion 345kV GEN-2017-151 Interconnection Costs | TUCO - Oklaunion 345kV GEN-2017-151 Interconnection (TOIF) (SPS) | Generation Interconnection | 2026-08-01 |  |  | GI STUDIES |  |  | 0 | 1569115 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-151 (300 MW/Wind), into the Point of Interconnection (POI) at TUCO - Oklaunion 345kV | 345
| 92033 | 143411 | OGE | OK | Johnson County 345kV Substation GEN-2017-154 Interconnection Costs | Johnson County 345kV GEN-2017-154 Interconnection (TOIF) (OGE) | Generation Interconnection | 2027-03-01 |  |  | GI STUDIES |  |  | 0 | 795827 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-154 (255 MW/Wind), into the Point of Interconnection (POI) at Johnson County 345kV | 345
| 92037 | 143418 | SPS | TX | Tolk 230kV Substation GEN-2017-158 Interconnection Costs | Tolk 230kV GEN-2017-158 Interconnection (Non-Shared NU) (SPS) | Generation Interconnection | 2026-05-01 |  |  | GI STUDIES |  |  | 0 | 3935078 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-158 (265 MW/Wind), into the Point of Interconnection (POI) at Tolk 230kV | 230
| 92037 | 143419 | SPS | TX | Tolk 230kV Substation GEN-2017-158 Interconnection Costs | Tolk 230kV GEN-2017-158 Interconnection (TOIF) (SPS) | Generation Interconnection | 2026-05-01 |  |  | GI STUDIES |  |  | 0 | 1329304 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-158 (265 MW/Wind), into the Point of Interconnection (POI) at Tolk 230kV | 230
| 92040 | 143424 | OGE | OK | Woodring 345kV Substation GEN-2017-164 Interconnection Costs | Woodring 345kV Interconnection Expansion (DISIS-2017-002) | Generation Interconnection | 2025-08-18 |  |  | GI STUDIES |  |  | 0 | 1790448 |  | Complete |  |  |  |  | Expand the Woodring 345kV substation to accommodate the interconnection of GEN-2017-164 and GEN-2017-178 | 345
| 92040 | 143425 | OGE | OK | Woodring 345kV Substation GEN-2017-164 Interconnection Costs | Woodring 345kV GEN-2017-164 Interconnection (TOIF) (OGE) | Generation Interconnection | 2025-08-18 |  |  | GI STUDIES |  |  | 0 | 795827 |  | Complete |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-164 (250 MW/Solar), into the Point of Interconnection (POI) at Woodring 345kV | 345
| 92041 | 143426 | OGE | OK | Sunnyside 345kV GEN-2017-166 Interconnection Costs | Sunnyside 345kV Interconnection Expansion (DISIS-2017-002) | Generation Interconnection | 2027-09-01 |  |  | GI STUDIES |  |  | 0 | 8195816 |  | On Schedule < 4 |  |  |  |  | Expand the Sunnyside 345kV substation to accommodate the interconnection of GEN-2017-166 and GEN-2017-167 | 345
| 92042 | 143429 | OGE | OK | Sunnyside 345kV GEN-2017-167 Interconnection Costs | Sunnyside 345kV GEN-2017-167 Interconnection (TOIF) (OGE) | Generation Interconnection | 2027-09-01 |  |  | GI STUDIES |  |  | 0 | 795827 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-167 (52 MW/Battery), into the Point of Interconnection (POI) at Sunnyside 345kV | 345
| 92045 | 143434 | AEP | OK | Lawton Eastside - Terry Road 345kV GEN-2017-171 Interconnection Costs | Lawton Eastside - Terry Road 345kV New Interconnection Substation (DISIS-2017-002) | Generation Interconnection | 2027-10-15 |  |  | GI STUDIES |  |  | 0 | 19222384 |  | On Schedule < 4 |  |  |  |  | Construct a new Lawton Eastside - Terry Road 345kV substation to accommodate the interconnection of GEN-2017-171, GEN-2017-172, and GEN-2017-173 | 345
| 92048 | 143440 | WAPA | SD | Vfodnes-Utica Jct. 230kV GEN-2017-175 Interconnection Costs | Vfodnes - Utica Jct. 230kV GEN-2017-175 Interconnection (Non-Shared NU) (WAPA) | Generation Interconnection | 2029-11-30 |  |  | GI STUDIES |  |  | 0 | 16085000 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-175 (300 MW/Wind), into the Point of Interconnection (POI) at Vfodnes - Utica Jct. 230kV | 230
| 92048 | 143441 | WAPA | SD | Vfodnes-Utica Jct. 230kV GEN-2017-175 Interconnection Costs | Vfodnes - Utica Jct. 230kV GEN-2017-175 Interconnection (TOIF) (WAPA) | Generation Interconnection | 2029-11-30 |  |  | GI STUDIES |  |  | 0 | 515000 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-175 (300 MW/Wind), into the Point of Interconnection (POI) at Vfodnes - Utica Jct. 230kV | 230
| 92050 | 143445 | OGE | OK | Woodring 345kV Substation GEN-2017-178 Interconnection Costs | Woodring 345kV GEN-2017-178 Interconnection (TOIF) (OGE) | Generation Interconnection | 2025-06-02 |  |  | GI STUDIES |  |  | 0 | 795827 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-178 (52 MW/Battery), into the Point of Interconnection (POI) at Woodring 345kV | 345
| 92051 | 143446 | WR | KS | Gordon Evans 138kV Substation GEN-2017-179 Interconnection Costs | Gordon Evans 138kV Interconnection Expansion (DISIS-2017-002) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 1386630 |  | On Schedule < 4 |  |  |  |  | Expand the Gordon Evans 138kV substation to accommodate the interconnection of GEN-2017-179, GEN-2017-226, and GEN-2017-227 | 138
| 92052 | 143448 | NPPD | NE | Tobias 345kV Substation GEN-2017-181 Interconnection Costs | Tobias 345kV Interconnection Expansion (DISIS-2017-002) | Generation Interconnection | 2028-06-01 |  |  | GI STUDIES |  |  | 0 | 7200000 |  | On Schedule < 4 |  |  |  |  | Expands the Tobias 345kV substation to accommodate the interconnection of GEN-2017-181 and GEN-2017-182 | 345
| 92052 | 143449 | NPPD | NE | Tobias 345kV Substation GEN-2017-181 Interconnection Costs | Tobias 345kV GEN-2017-181 Interconnection (TOIF) (NPPD) | Generation Interconnection | 2028-06-01 |  |  | GI STUDIES |  |  | 0 | 0 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-181 (300 MW/Wind), into the Point of Interconnection (POI) at Tobias 345kV | 345
| 92053 | 143451 | NPPD | NE | Moore 345kV Substation GEN-2017-182 Interconnection Costs | Tobias 345kV GEN-2017-182 Interconnection (TOIF) (NPPD) | Generation Interconnection | 2028-06-01 |  |  | GI STUDIES |  |  | 0 | 0 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-182 (128 MW/Wind), into the Point of Interconnection (POI) at Moore 345kV | 345
| 92054 | 143452 | EMW | KS | Nashua-St. Joe 345kV GEN-2017-183 Interconnection Costs | Nashua - St. Joe 345kV New Interconnection Substation (DISIS-2017-002) | Generation Interconnection | 2028-12-01 |  |  | GI STUDIES |  |  | 0 | 33984046 |  | In Service |  |  |  |  | Construct a new Nashua - St. Joe 345kV substation to accommodate the interconnection of GEN-2017-183 and GEN-2017-184 | 345
| 92054 | 143453 | EMW | KS | Nashua-St. Joe 345kV GEN-2017-183 Interconnection Costs | Nashua - St. Joe 345kV GEN-2017-183 Interconnection (TOIF) (KCPL) | Generation Interconnection | 2028-12-01 |  |  | GI STUDIES |  |  | 0 | 679435 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-183 (400 MW/Wind), into the Point of Interconnection (POI) at Nashua - St. Joe 345kV | 345
| 92055 | 143455 | EMW | KS | Nashua-St. Joe 345kV GEN-2017-184 Interconnection Costs | Nashua -St. Joe 345kV GEN-2017-184 Interconnection (TOIF) (KCPL) | Generation Interconnection | 2028-12-01 |  |  | GI STUDIES |  |  | 0 | 679435 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-184 (400 MW/Solar), into the Point of Interconnection (POI) at Nashua -St. Joe 345kV | 345
| 92058 | 143460 | SPS | TX | Sulphur Springs 115kV Substation GEN-2017-187 Interconnection Costs | Sulphur Springs 115kV GEN-2017-187 Interconnection (Non-Shared NU) (SPS) | Generation Interconnection | 2026-02-01 |  |  | GI STUDIES |  |  | 0 | 16197956 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-187 (199.5 MW/Solar), into the Point of Interconnection (POI) at Sulphur Springs 115kV | 115
| 92058 | 143461 | SPS | TX | Sulphur Springs 115kV Substation GEN-2017-187 Interconnection Costs | Sulphur Springs 115kV GEN-2017-187 Interconnection (TOIF) (SPS) | Generation Interconnection | 2026-02-01 |  |  | GI STUDIES |  |  | 0 | 841906 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-187 (199.5 MW/Solar), into the Point of Interconnection (POI) at Sulphur Springs 115kV | 115
| 92059 | 143462 | EDE | MO | Asbury 161 kV GEN-2017-188 Interconnection Costs | Asbury 161 kV GEN-2017-188 Interconnection (Non-Shared NU) (EDE) | Generation Interconnection | 2025-12-01 |  |  | GI STUDIES |  |  | 0 | 1520000 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-188 (170 MW/Solar), into the Point of Interconnection (POI) at Asbury 161 kV | 161
| 92059 | 143463 | EDE | MO | Asbury 161 kV GEN-2017-188 Interconnection Costs | Asbury 161 kV GEN-2017-188 Interconnection (TOIF) (EDE) | Generation Interconnection | 2025-12-01 |  |  | GI STUDIES |  |  | 0 |  |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-188 (170 MW/Solar), into the Point of Interconnection (POI) at Asbury 161 kV | 161
| 92066 | 143476 | EMW | KS | West Gardner 345kV GEN-2017-195 Interconnection Costs | West Gardner 345kV Interconnection Expansion (DISIS-2017-002) | Generation Interconnection | 2030-11-01 |  |  | GI STUDIES |  |  | 0 | 43489866 |  | On Schedule < 4 |  |  |  |  | Expand the West Gardner 345kV substation to accommodate the interconnection of GEN-2017-195 and GEN-2017-196 | 345
| 92066 | 143477 | EMW | KS | West Gardner 345kV GEN-2017-195 Interconnection Costs | West Gardner 345kV GEN-2017-195 Interconnection (TOIF) (KCPL) | Generation Interconnection | 2030-11-01 |  |  | GI STUDIES |  |  | 0 | 1007918 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-195 (500.4 MW/Solar), into the Point of Interconnection (POI) at West Gardner 345kV | 345
| 92067 | 143479 | EMW | KS | West Gardner 345kV GEN-2017-196 Interconnection Costs | West Gardner 345kV GEN-2017-196 Interconnection (TOIF) (KCPL) | Generation Interconnection | 2030-11-01 |  |  | GI STUDIES |  |  | 0 | 1007918 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-196 (128 MW/Battery), into the Point of Interconnection (POI) at West Gardner 345kV | 345
| 92069 | 143482 | OPPD | NE | Jones St. No 901 69kV substation GEN-2017-198 Interconnection Costs | Jones St. No 901 69kV GEN-2017-198 Interconnection (Non-Shared NU) (OPPD) | Generation Interconnection | 2026-11-27 |  |  | GI STUDIES |  |  | 0 | 0 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-198 (20 MW/Battery), into the Point of Interconnection (POI) at Jones St. No 901 69kV | 69
| 92069 | 143483 | OPPD | NE | Jones St. No 901 69kV substation GEN-2017-198 Interconnection Costs | Jones St. No 901 69kV GEN-2017-198 Interconnection (TOIF) (OPPD) | Generation Interconnection | 2026-11-27 |  |  | GI STUDIES |  |  | 0 | 923949 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-198 (20 MW/Battery), into the Point of Interconnection (POI) at Jones St. No 901 69kV | 69
| 92072 | 143488 | NPPD | NE | Hoskins 345kV Substation GEN-2017-201 Interconnection Costs | Hoskins 345k GEN-2017-201 Interconnection (Non-Shared NU) (NPPD) | Generation Interconnection | 2028-06-01 |  |  | GI STUDIES |  |  | 0 | 50000 |  | On Schedule > 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-201 (250 MW/Wind), into the Point of Interconnection (POI) at Hoskins 345k | 34
| 92072 | 143489 | NPPD | NE | Hoskins 345kV Substation GEN-2017-201 Interconnection Costs | Hoskins 345k GEN-2017-201 Interconnection (TOIF) (NPPD) | Generation Interconnection | 2028-06-01 |  |  | GI STUDIES |  |  | 0 |  |  | On Schedule > 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-201 (250 MW/Wind), into the Point of Interconnection (POI) at Hoskins 345k | 34
| 92073 | 143490 | SWPA | MO | New Madrid - Sikeston 161kV GEN-2017-202 Interconnection Costs | New Madrid - Sikeston 161kV GEN-2017-202 Interconnection (Non-Shared NU) (SWPA) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 7069000 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-202 (200 MW/Solar), into the Point of Interconnection (POI) at New Madrid - Sikeston 161kV | 161
| 92073 | 143491 | SWPA | MO | New Madrid - Sikeston 161kV GEN-2017-202 Interconnection Costs | New Madrid - Sikeston 161kV GEN-2017-202 Interconnection (TOIF) (SWPA) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 746000 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-202 (200 MW/Solar), into the Point of Interconnection (POI) at New Madrid - Sikeston 161kV | 161
| 92074 | 143492 | OGE | OK | Renfrow 345kV Substation GEN-2017-203 Interconnection Costs | Renfrow 345kV GEN-2017-203 Interconnection (Non-Shared NU) (OGE) | Generation Interconnection | 2026-09-15 |  |  | GI STUDIES |  |  | 0 | 1790448 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-203 (210 MW/Hybrid), into the Point of Interconnection (POI) at Renfrow 345kV | 345
| 92074 | 143493 | OGE | OK | Renfrow 345kV Substation GEN-2017-203 Interconnection Costs | Renfrow 345kV GEN-2017-203 Interconnection (TOIF) (OGE) | Generation Interconnection | 2026-09-15 |  |  | GI STUDIES |  |  | 0 | 1591654 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-203 (210 MW/Hybrid), into the Point of Interconnection (POI) at Renfrow 345kV | 345
| 92078 | 143500 | WR | MO | LaCygne - Neosho 345kV GEN-2017-209 Interconnection Costs | LaCygne - Neosho 345kV GEN-2017-209 Interconnection (Non-Shared NU) (WERE) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 |  |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-209 (300 MW/Hybrid), into the Point of Interconnection (POI) at LaCygne - Neosho 345kV | 345
| 92078 | 143501 | WR | MO | LaCygne - Neosho 345kV GEN-2017-209 Interconnection Costs | LaCygne - Neosho 345kV GEN-2017-209 Interconnection (TOIF) (WERE) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 0 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-209 (300 MW/Hybrid), into the Point of Interconnection (POI) at LaCygne - Neosho 345kV | 345
| 92079 | 143502 | NPPD | NE | McCool 345kV Substation GEN-2017-210 Interconnection Costs | McCool 345kV GEN-2017-210 Interconnection (Non-Shared NU) (NPPD) | Generation Interconnection | 2026-10-01 |  |  | GI STUDIES |  |  | 0 | 9900000 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-210 (310 MW/Hybrid), into the Point of Interconnection (POI) at McCool 345kV | 345
| 92079 | 143503 | NPPD | NE | McCool 345kV Substation GEN-2017-210 Interconnection Costs | McCool 345kV GEN-2017-210 Interconnection (TOIF) (NPPD) | Generation Interconnection | 2026-10-01 |  |  | GI STUDIES |  |  | 0 |  |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-210 (310 MW/Hybrid), into the Point of Interconnection (POI) at McCool 345kV | 345
| 92081 | 143506 | BEPC | ND | Logan 230kV Substation GEN-2017-214 Interconnection Costs | Logan 230kV Interconnection Expansion (DISIS-2017-002) | Generation Interconnection | 2027-06-18 |  |  | GI STUDIES |  |  | 0 | 1317063 |  | On Schedule < 4 |  |  |  |  | Expand the Logan 230kV substation to accommodate the interconnection of GEN-2017-214, GEN-2017-215, GEN-2017-216, GEN-2017-235, and GEN-2017-236 | 230
| 92081 | 143507 | BEPC | ND | Logan 230kV Substation GEN-2017-214 Interconnection Costs | Logan 230kV GEN-2017-214 Interconnection (TOIF) (BEPC) | Generation Interconnection | 2027-06-18 |  |  | GI STUDIES |  |  | 0 | 937785 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-214 (100 MW/Wind), into the Point of Interconnection (POI) at Logan 230kV | 230
| 92082 | 143509 | BEPC | ND | Logan 230kV Substation GEN-2017-215 Interconnection Costs | Logan 230kV GEN-2017-215 Interconnection (TOIF) (BEPC) | Generation Interconnection | 2027-06-18 |  |  | GI STUDIES |  |  | 0 | 100000 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-215 (100 MW/Wind), into the Point of Interconnection (POI) at Logan 230kV | 230
| 92087 | 143518 | WR | KS | Buffalo Flats 345kV Substation GEN-2017-220 Interconnection Costs | Buffalo Flats 345kV Interconnection Expansion (DISIS-2017-002) | Generation Interconnection | 2029-08-30 |  |  | GI STUDIES |  |  | 0 | 225823 |  | In Service |  |  |  |  | Expand the Buffalo Flats 345kV substation to accommodate the interconnection of GEN-2017-220 and GEN-2017-221 | 345
| 92088 | 143521 | WR | KS | Buffalo Flats 345kV Substation GEN-2017-221 Interconnection Costs | Buffalo Flats 345kV GEN-2017-221 Interconnection (TOIF) (WERE) | Generation Interconnection | 2029-08-30 |  |  | GI STUDIES |  |  | 0 | 0 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-221 (152 MW/Battery), into the Point of Interconnection (POI) at Buffalo Flats 345kV | 345
| 92089 | 143522 | WAPA | IA | Denison 230kV Substation GEN-2017-222 Interconnection Costs | Denison 230kV GEN-2017-222 Interconnection (Non-Shared NU) (WAPA) | Generation Interconnection | 2027-08-01 |  |  | GI STUDIES |  |  | 0 | 13460000 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-222 (180 MW/Wind), into the Point of Interconnection (POI) at Denison 230kV | 230
| 92089 | 143523 | WAPA | IA | Denison 230kV Substation GEN-2017-222 Interconnection Costs | Denison 230kV GEN-2017-222 Interconnection (TOIF) (WAPA) | Generation Interconnection | 2027-08-01 |  |  | GI STUDIES |  |  | 0 | 265000 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-222 (180 MW/Wind), into the Point of Interconnection (POI) at Denison 230kV | 230
| 92092 | 143529 | WR | KS | Gordon Evans 138kV Substation GEN-2017-226 Interconnection Costs | Gordon Evans 138kV GEN-2017-226 Interconnection (TOIF) (WERE) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 750415 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-226 (201.6 MW/Solar), into the Point of Interconnection (POI) at Gordon Evans 138kV | 138
| 92093 | 143531 | WR | KS | Gordon Evans 138kV Substation GEN-2017-227 Interconnection Costs | Gordon Evans 138kV GEN-2017-227 Interconnection (TOIF) (WERE) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 744762 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-227 (201.6 MW/Storage), into the Point of Interconnection (POI) at Gordon Evans 138kV | 138
| 92095 | 143534 | KCPL | MO | Stilwell 345kV Substation GEN-2017-229 Interconnection Costs | Stilwell 345kV GEN-2017-229 Interconnection (Non-Shared NU) (KCPL) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 23703089 |  | Identified |  |  |  |  | Cancelled to consolidate costs under 143396 | 345
| 92096 | 143536 | OGE | OK | Tryon 138kV Substation GEN-2017-230 Interconnection Costs | Tryon 138kV GEN-2017-230 Interconnection (Non-Shared NU) (OGE) | Generation Interconnection | 2027-09-01 |  |  | GI STUDIES |  |  | 0 | 1133420 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-230 (72.5 MW/Solar), into the Point of Interconnection (POI) at Tryon 138kV | 138
| 92096 | 143537 | OGE | OK | Tryon 138kV Substation GEN-2017-230 Interconnection Costs | Tryon 138kV GEN-2017-230 Interconnection (TOIF) (OGE) | Generation Interconnection | 2027-09-01 |  |  | GI STUDIES |  |  | 0 | 934626 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-230 (72.5 MW/Solar), into the Point of Interconnection (POI) at Tryon 138kV | 138
| 92097 | 143538 | OGE | OK | Branch 161kV Substation GEN-2017-231 Interconnection Costs | Branch 161kV GEN-2017-231 Interconnection (Non-Shared NU) (OGE) | Generation Interconnection | 2026-09-01 |  |  | GI STUDIES |  |  | 0 | 6030786 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-231 (72.5 MW/Solar), into the Point of Interconnection (POI) at Branch 161kV | 161
| 92097 | 143539 | OGE | OK | Branch 161kV Substation GEN-2017-231 Interconnection Costs | Branch 161kV GEN-2017-231 Interconnection (TOIF) (OGE) | Generation Interconnection | 2026-09-30 |  |  | GI STUDIES |  |  | 0 | 934626 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-231 (72.5 MW/Solar), into the Point of Interconnection (POI) at Branch 161kV | 161
| 92098 | 143540 | OGE | OK | Brown 138kV Substation GEN-2017-232 Interconnection Costs | Brown 138kV GEN-2017-232 Interconnection (Non-Shared NU) (OGE) | Generation Interconnection | 2025-11-13 |  |  | GI STUDIES |  |  | 0 | 3299998 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-232 (52.2 MW/Solar), into the Point of Interconnection (POI) at Brown 138kV | 138
| 92098 | 143541 | OGE | OK | Brown 138kV Substation GEN-2017-232 Interconnection Costs | Brown 138kV GEN-2017-232 Interconnection (TOIF) (OGE) | Generation Interconnection | 2025-11-13 |  |  | GI STUDIES |  |  | 0 | 3300000 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-232 (52.2 MW/Solar), into the Point of Interconnection (POI) at Brown 138kV | 138
| 92099 | 143543 | OGE | OK | Minco 345kV GEN-2017-233 Interconnection Costs | Minco 345kV GEN-2017-233 Interconnection (TOIF) (OGE) | Generation Interconnection | 2026-09-28 |  |  | GI STUDIES |  |  | 0 | 1691051 |  | In Service |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-233 (215 MW/Wind), into the Point of Interconnection (POI) at Minco 345kV | 345
| 92100 | 143544 | NPPD | NE | Spalding to North Loup 115kV GEN-2017-234 Interconnection Costs | Spalding to North Loup 115kV GEN-2017-234 Interconnection (Non-Shared NU) (NPPD) | Generation Interconnection | 2028-06-01 |  |  | GI STUDIES |  |  | 0 | 12500000 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-234 (115 MW/Wind), into the Point of Interconnection (POI) at Spalding to North Loup 115kV | 115
| 92100 | 143545 | NPPD | NE | Spalding to North Loup 115kV GEN-2017-234 Interconnection Costs | Spalding to North Loup 115kV GEN-2017-234 Interconnection (TOIF) (NPPD) | Generation Interconnection | 2028-06-01 |  |  | GI STUDIES |  |  | 0 |  |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-234 (115 MW/Wind), into the Point of Interconnection (POI) at Spalding to North Loup 115kV | 115
| 92105 | 143552 | SPS | TX | Mahoney 230kV Substation GEN-2017-239 Interconnection Costs | Mahoney 230kV GEN-2017-239 Interconnection (Non-Shared NU) (SPS) | Generation Interconnection | 2026-02-01 |  |  | GI STUDIES |  |  | 0 | 820698 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-239 (300 MW/Solar), into the Point of Interconnection (POI) at Mahoney 230kV | 230
| 92105 | 143553 | SPS | TX | Mahoney 230kV Substation GEN-2017-239 Interconnection Costs | Mahoney 230kV GEN-2017-239 Interconnection (TOIF) (SPS) | Generation Interconnection | 2026-02-01 |  |  | GI STUDIES |  |  | 0 | 1049789 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2017-239 (300 MW/Solar), into the Point of Interconnection (POI) at Mahoney 230kV | 230
220720 | 92113 | 143588 | BEPC | ND | Line - Kummer Ridge - Round Up 345 kV | Kummer Ridge - Round Up 345 kV | Regional Reliability | 2024-12-17 | 2023-01-01 | 2023-03-16 | 2021 ITP | 78293357 | 2022 | 82256958.1981 | 83598385 |  | Complete |  |  |  |  | Build 33.2 mile new 345 kV line from Kummer Ridge to Round Up | 345 | 33.2
220720 | 92113 | 143589 | BEPC | ND | Line - Kummer Ridge - Round Up 345 kV | Kummer Ridge 345 kV Terminal Upgrades | Regional Reliability | 2024-12-17 | 2023-01-01 | 2023-03-16 | 2021 ITP | 342000 | 2022 | 359313.75 | 65100 |  | Complete |  |  |  |  | Install terminal equipment at Kummer Ridge substation 345 kV to support a new 345 kV line from Round Up | 345
220720 | 92113 | 143590 | BEPC | ND | Line - Kummer Ridge - Round Up 345 kV | Round Up 345 kV Terminal Upgrades | Regional Reliability | 2024-12-17 | 2023-01-01 | 2023-03-16 | 2021 ITP | 342000 | 2022 | 359313.75 | 100000 |  | Complete |  |  |  |  | Install terminal equipment at Round Up substation 345 kV to support a new 345 kV line from Kummer Ridge | 345
210633 | 92114 | 143591 | AEP | OK | Line- Catoosa - Blue Circle 69 kV | Blue Circle - Catoosa 69 kV Ckt 1 Rebuild | Regional Reliability | 2024-12-18 | 2023-06-01 | 2022-03-09 | 2021 ITP | 9020000 | 2022 | 9476637.5 | 10602174 |  | Complete |  |  |  |  | Rebuild 3.5 miles of 69 kV line from Catoosa to Blue Circle and upgrade any necessary terminal equipment at Catoosa and/or Blue Circle | 69 |  | 3.5
210645 | 81769 | 143599 | NPPD | NE | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Scottsbluff 115 kV Ckt 2 Terminal Upgrades | Economic | 2025-06-25 | 2023-01-01 | 2022-03-09 | 2021 ITP | 1194000 | 2022 | 1285807.4003 | 1664223 | 1664223 | Complete |  |  |  |  | Install terminal equipment at Scottsbluff 115 kV to support a second 115 kV line from Victory Hill. | 115
210645 | 81769 | 143600 | NPPD | NE | Line - Scottsbluff - Victory Hill 115 kV Ckt 2 | Victory Hill 115 kV Ckt 2 Terminal Upgrades | Economic | 2025-06-01 | 2023-01-01 | 2022-03-09 | 2021 ITP | 1129000 | 2022 | 1215809.51 | 2637266 |  | Complete |  |  |  |  | Install terminal equipment at Victory Hill 115 kV to support a second 115 kV line from Scottsbluff with a summer emergency rating of 264 MVA | 115
210648 | 81691 | 143613 | WAPA | SD | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Sully Buttes - Whitlock 230 kV Line Clearance Increase | Economic | 2025-04-17 | 2025-01-01 | 2022-03-11 | 2021 ITP | 1744800 | 2022 | 1878958.7538 | 0 |  | Complete |  |  |  |  | Increase ground clearance of the Sully Buttes to Whitlock 230 kV line. | 230
210648 | 81691 | 143614 | WAPA | SD | Line - Oahe - Sully Buttes - Whitlock - Glenham 230 kV | Whitlock - Glenham 230 kV Clearance Increase | Economic | 2025-04-17 | 2025-01-01 | 2022-03-11 | 2021 ITP | 5845900 | 2022 | 6295394.8755 | 323364 |  | Complete |  |  |  |  | Increase ground clearance of the Whitlock - Glenham 230 kV. | 230
210680 | 92123 | 143660 | OPPD | NE | Line - S3454 - S3740 345 kV | S3454 - S3740 345 kV New Line | Regional Reliability | 2026-12-31 | 2024-06-01 | 2022-07-19 | 2021 ITP | 138783923 | 2025 | 142253521.075 | 138783923 |  | Delay - Mitigation Window |  |  |  |  | Build an approximately 29 mile 345 kV line from S3454 to S3740 Ckt 1. | 345 | 29
210680 | 92123 | 143661 | OPPD | NE/ | Line - S3454 - S3740 345 kV | S3454 345 kV Terminal Upgrades | Regional Reliability | 2026-12-31 | 2024-06-01 | 2022-07-19 | 2021 ITP | 6687060 | 2025 | 6854236.5 | 6687060 |  | Delay - Mitigation Window |  |  |  |  | Install terminal equipment at S3454 substation 345 kV to support a new 345 kV line from S3454 to S3740. | 345
210680 | 92123 | 143662 | OPPD | NE/ | Line - S3454 - S3740 345 kV | S3740 345 kV Terminal Upgrades | Regional Reliability | 2026-12-31 | 2024-06-01 | 2022-07-19 | 2021 ITP | 5698724 | 2025 | 5841192.1 | 5698724 |  | Delay - Mitigation Window |  |  |  |  | Install terminal equipment at S3740 substation 345 kV to support a new 345 kV line from S3454 to S3740. | 345
210619 | 92180 | 143705 | NPPD | NE | Line - Kearney NE - Tower 115 kV | Kearney NE - Tower 115 kV Ckt 1 New Line | Regional Reliability | 2025-06-06 | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 | 11250834 | 2022 | 12115917.6018 | 11915911 | 11915911 | Complete | 640248 | Kearney Northeast | 640383 | Tower | Build a new 115 kV 10 mile line from Kearney to Tower with a minimum summer emergency rating of 160 MVA
210675 | 92168 | 143714 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad - Tande 345 kV New Line | Regional Reliability | 2026-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 67411405 | 2022 | 74409577.772 | 86953680 |  | Delay - Mitigation |  |  |  |  | Build a 48 mile 345 kV line from Finstad to Tande.
210656 | 92190 | 143806 | OGE | OK/ | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Marietta Tap (OKGE) – Marietta Switchyard (WFEC) 138 kV Ckt 1 New Line (OGE) | Regional Reliability | 2025-06-30 | 2023-06-01 | 2022-03-11 | 2021 ITP | 1575000 | 2022 | 1696102.7265 | 892961 |  | Complete |  |  |  |  | Build new 2.1 mile 138 kV line from Marietta Tap (OKGE) – Marietta Switchyard (WFEC) | 138
210656 | 92190 | 143815 | OGE | OK/ | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Marietta 2 138 kV Voltage Conversion | Regional Reliability | 2025-07-30 | 2023-06-01 | 2022-03-11 | 2021 ITP | 5000000 | 2022 | 5384453.1 | 3340351 |  | Complete |  |  |  |  | Convert the Marietta 2 substation from 69 kV to 138 kV and install terminal equipment to support a new 138 kV line from Marietta 4 | 69
210656 | 92190 | 143816 | OGE | OK | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Rocky Point - Marietta 2 138 kV Ckt 1 Rebuild | Regional Reliability | 2025-09-19 | 2023-06-01 | 2022-03-11 | 2021 ITP | 8806000 | 2022 | 9483098.7997 | 29559659 |  | Complete |  |  |  |  | Rebuild the existing 69 kV line from Rocky Point to Marietta 2 as a 138 kV line | 69
210656 | 92190 | 143817 | OGE | OK | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Rocky Point 69 kV Replace Relays | Regional Reliability | 2025-03-15 | 2023-06-01 | 2022-03-11 | 2021 ITP | 250000 | 2022 | 269222.655 | 230807 |  | Complete |  |  |  |  | Replace the existing relays at Rocky Point | 69
210644 | 92238 | 144142 | TSGT | NE | Line - Ogallala Tri State - Ogallala NPPD 115 kV | Ogallala (Tri State) - Ogallala (NPPD) 115 kV (TSGT) | Economic | 2023-12-06 | 2023-01-01 | 2022-03-11 | 2021 ITP | 380321 | 2022 | 389829.025 | 380321 | 195983.81 | Complete |  |  |  |  | Upgrade the 115 kV tie from Ogallala Tri State to Ogallala NPPD.
210645 | 92238 | 144143 | NPPD | NE | Line - Ogallala Tri State - Ogallala NPPD 115 kV | Ogallala (Tri State) - Ogallala (NPPD) 115 kV (NPPD) | Economic | 2023-12-31 | 2023-01-01 | 2022-03-09 | 2021 ITP | 281000 | 2022 | 288025 | 326708 | 326708 | Complete |  |  |  |  | Upgrade the 115 kV tie from Ogallala Tri State to Ogallala NPPD.
210663 | 92178 | 144148 | MWE | ND | Multi - E Newtown 115 kV | E Newtown 115 kV New Statcom | Regional Reliability | 2025-02-25 | 2023-01-01 | 2022-07-12 | 2021 ITP | 22213115 | 2022 | 23921095.1845 | 19500000 |  | Complete |  |  |  |  | Install a 150 MVAR statcom and supporting equipment at E Newtown to control voltage on the 115 kV transmission system
210663 | 92211 | 144163 | MWE | ND | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | Folvag 115 kV Terminal Equipment | Regional Reliability | 2024-12-03 | 2023-01-01 | 2022-07-12 | 2021 ITP | 613746 | 2022 | 644816.8912 | 500000 |  | Complete |  |  |  |  | Install terminal equipment at Folvag 115 kV sub to accommodate new 115 kV line from NE Williston 115 kV sub.
210675 | 92211 | 144171 | BEPC | ND/ | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | East Fork 345/115 kV Substation | Regional Reliability | 2025-12-31 | 2023-01-01 | 2022-07-12 | 2021 ITP | 17766381 | 2022 | 19132449.0502 | 17821363 |  | Delay - Mitigation |  |  |  |  | Bisect the Judson to Tande 345 kV line approximately 18 miles from Judson and build a new 345 kV Substation.
210657 | 92190 | 144173 | WFEC | OK | Multi - Rocky Point - OG&E Marietta - WFEC Marietta 138 kV Rebuild | Marietta Switchyard 138 kV Ckt 1 Terminal Equipment | Regional Reliability | 2025-07-30 | 2023-06-01 | 2022-03-11 | 2021 ITP | 736000 | 2022 | 792591.4963 | 704000 |  | Complete |  |  |  |  | Install terminal equipment at WFEC Marietta Switch to support a new 138 kV line from OG&E Marietta.
210663 | 92211 | 144177 | MWE | ND | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | NE Williston - Folvag 115 kV New Line | Regional Reliability | 2024-12-03 | 2023-01-01 | 2022-07-12 | 2021 ITP | 6490000 | 2022 | 6818556.25 | 8700000 |  | Complete |  |  |  |  | Build a new 4.5 mile 115 kV line from NE Williston to Folvag. | 115 | 4.5
210663 | 92211 | 144178 | MWE | ND | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | NE Williston 115 kV Terminal Equipment | Regional Reliability | 2024-12-03 | 2023-01-01 | 2022-07-12 | 2021 ITP | 596597 | 2022 | 626799.7231 | 500000 |  | Complete |  |  |  |  | Install terminal equipment at NE Williston 115 kV sub to accommodate new 115 kV line from Folvag 115 kV sub.
210675 | 92211 | 144198 | BEPC | ND | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | East Fork 345/115 kV Transformer | Regional Reliability | 2025-12-31 | 2023-01-01 | 2022-07-12 | 2021 ITP | 5904650 | 2022 | 6358662.1994 | 6255443 |  | Delay - Mitigation |  |  |  |  | Install a 345/115 kV Transformer at the new East Fork 345/115 kV Substation.
210663 | 92211 | 144199 | MWE | ND/ | Multi - NE Williston - Folvag 115 kV - Judson - East Fork - Tande 345 kV | East Fork 115 kV Terminal Equipment | Regional Reliability | 2026-03-31 | 2023-01-01 | 2022-07-12 | 2021 ITP | 2511246 | 2022 | 2771945.7048 | 4092000 |  | Delay - Mitigation |  |  |  |  | Install 115 kV terminal equipment at MWEC’s East Fork 115 kV substation to accommodate a 115 kV tie line from the East Fork 345/115 kV substation. Construct a 115 kV tie line from the East Fork 115 kV substation to the proposed BEPC East Fork 345/115 kV substation.
210663 | 92178 | 144202 | MWE | ND | Multi - E Newtown 115 kV | E Newtown 115 kV Substation | Regional Reliability | 2025-02-25 | 2023-01-01 | 2022-07-12 | 2021 ITP | 1087789 | 2022 | 1171429.7706 | 1500000 |  | Complete |  |  |  |  | Expand existing 115 kV E Newtown substation to accommodate the statcom interconnection.
220727 | 92237 | 144206 | SPS | TX | Line - Twist - Wilco 115 kV | Twist 115 kV Substation | Regional Reliability | 2025-10-31 | 2022-06-01 | 2023-12-05 | DPA-2021-Feb-1279-1280 | 9087788 | 2023 | 9547857.2675 | 8194459 |  | Complete |  |  |  |  | Build a new 115 kV substation at Twist Substation, located 4 miles west and 2 miles south of RB-Exum, along the RB Exum-Hilmar Cheese Plant 115 kV line.
220727 | 92237 | 144207 | SPS | TX// | Line - Twist - Wilco 115 kV | RB-Exum - Hilmar Cheese Ckt 1, Twist 115 kV New Lines, North Side | Regional Reliability | 2025-12-19 | 2022-06-01 | 2023-12-05 | DPA-2021-Feb-1279-1280 | 3909647 | 2023 | 4107572.8794 | 4905051 |  | Delay - Mitigation |  |  |  |  | Cut into the RB-Exum to Hilmar Cheese Plant 115 kV line, 4 miles west of RB-Exum, and build a new 2-mile double circuit 115 kV line south into the new Twist substation.
220727 | 92237 | 144208 | SPS | TX | Line - Twist - Wilco 115 kV | RB-Kemp - Moore County Ckt 1, Twist 115 kV New Lines, south side. | Regional Reliability | 2025-10-15 | 2022-06-01 | 2023-12-05 | DPA-2021-Feb-1279-1280 | 3561243 | 2023 | 3741530.9269 | 4573961 |  | Complete |  |  |  |  | Cut into the RB-Kemp - Moore County 115 kV line, 2 miles east of RB-Kemp, and build a new 1.8-mile double circuit 115kV line north into the new Twist 115 kV substation.
210663 | 92168 | 144226 | MWE | ND/ | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad - Vanhook 115 kV New Line | Regional Reliability | 2026-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 4702500 | 2022 | 5190680.1152 | 4702500 |  | Delay - Mitigation |  |  |  |  | Build a 5-mile 115 kV line from Finstad to Vanhook. | 345 | 5
210675 | 92168 | 144227 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 115 kV Substation | Regional Reliability | 2026-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 4675697 | 2022 | 5161094.6183 | 4460300 |  | Delay - Mitigation |  |  |  |  | Build a new 115 kV Substation with terminal equipment to support a line from Vanhook 115 kV substation.
210675 | 92168 | 144230 | BEPC | ND/ | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345 kV New Substation | Regional Reliability | 2026-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 18822018 | 2022 | 20775986.0842 | 19545748 |  | Delay - Mitigation |  |  |  |  | Build a new 345 kV Substation including 345 kV terminals for lines from Leland Olds 345 kV substation, Tande 345 kV substation and high side terminal equipment for Finstad 345/115 kV Ckt 1 transformer and Finstad 345/115 kV Ckt 2 transformer
210675 | 92168 | 144231 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad Switched Shunt | Regional Reliability | 2026-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 385021 | 2022 | 424991.1427 | 483601 |  | Delay - Mitigation |  |  |  |  | Install a switched shunt at Finstad.
210675 | 92168 | 144233 | BEPC | ND/ | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345/115 kV Ckt 1 Transformer | Regional Reliability | 2026-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 5315254 | 2022 | 5867045.8788 | 5921981 |  | Delay - Mitigation |  |  |  |  | Install a 345/115 kV Ckt 1 Transformer at Finstad 345 | 345/115
210675 | 92168 | 144235 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Finstad 345/115 kV Ckt 2 Transformer | Regional Reliability | 2026-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 5315254 | 2022 | 5867045.8788 | 5966426 |  | Delay - Mitigation |  |  |  |  | Install a 345/115 kV Ckt 2 transformer at Finstad 115 and upgrade any necessary 115 kV terminal equipment. | 345/115
210675 | 92168 | 144236 | BEPC | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Leland Olds - Finstad - 345 kV New Line | Regional Reliability | 2026-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 200761539 | 2022 | 221603174.5644 | 211632531 |  | Delay - Mitigation |  |  |  |  | Build a 123 mile 345 kV line from Leland Olds to Finstad. | 345
210675 | 92168 | 144237 | BEPC | ND/ | Multi - Tande - Finstad - Leland Olds 345 kV | Leland Olds 345 kV Substation | Regional Reliability | 2026-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 9277339 | 2022 | 10240446.3731 | 11908819 |  | Delay - Mitigation |  |  |  |  | Build a new 345 kV Substation with terminal equipment to support a new line from Finstad 345 kV substation.
210675 | 92168 | 144238 | BEPC | ND/ | Multi - Tande - Finstad - Leland Olds 345 kV | Tande 345 kV Terminal Equipment | Regional Reliability | 2026-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 5085047 | 2022 | 5612940.4249 | 5085047 |  | Delay - Mitigation |  |  |  |  | Install new terminal equipment at Tande to support a new 345 kV line from Finstad. Install a series compensation device at Finstad or Tande.
210663 | 92168 | 144239 | MWE | ND | Multi - Tande - Finstad - Leland Olds 345 kV | Vanhook 115 kV Terminal Equipment | Regional Reliability | 2026-11-30 | 2023-01-01 | 2022-07-12 | 2021 ITP | 3811190 | 2022 | 4206840.6482 | 2334441 |  | Delay - Mitigation |  |  |  |  | Install new 115 kV terminal equipment at Vanhook to support a new 115 kV line from Finstad.
210665 | 92268 | 144277 | WFEC | OK | Multi - Elmore - Bradly 69 kV | Bradly Tap 69 kV Cap Bank | Regional Reliability | 2026-05-31 | 2022-06-01 | 2022-04-18 | DPA-2021-June-1332 | 803000 | 2022 | 886361.7507 | 1019000 |  | Delay - Mitigation |  |  |  |  | Install new 12 MVAR capacitor bank at Bradly Tap 69 kV.
210664 | 92271 | 144279 | OGE | OK | Multi - West Oaks - Council - Classen 138 kV Reconductor | Classen 138 kV Terminal Upgrades | Regional Reliability | 2025-11-28 | 2024-04-01 | 2022-04-14 | DPA-2021-March-1296 | 600000 | 2022 | 646134.372 | 600000 |  | Complete |  |  |  |  | Upgrade any necessary terminal equipment at Classen substation.
210664 | 92271 | 144280 | OGE | OK | Multi - West Oaks - Council - Classen 138 kV Reconductor | Council - Mustang 138 kV Ckt 1 Reconductor | Regional Reliability | 2025-08-01 | 2024-04-01 | 2022-04-14 | DPA-2021-March-1296 | 1390000 | 2022 | 1496877.9618 | 1390000 |  | Complete |  |  |  |  | Reconductor of Mustang to Council 138 kV transmission line.
210664 | 92271 | 144281 | OGE | OK | Multi - West Oaks - Council - Classen 138 kV Reconductor | Classen - Douglas Tap 138 kV Reconductor | Regional Reliability | 2025-11-28 | 2024-04-01 | 2022-04-14 | DPA-2021-March-1296 | 790000 | 2022 | 850743.5898 | 790000 |  | Complete |  |  |  |  | Reconductor of Douglas Tap to Classen 138 kV transmission line.
210619 | 92180 | 144283 | NPPD | NE | Line - Kearney NE - Tower 115 kV | Tower 115 kV Terminal Equipment | Regional Reliability | 2025-06-06 | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 | 1288644 | 2022 | 1387728.6361 | 3689073 | 3689073 | Complete |  |  |  |  | Install terminal equipment at Tower 115 kV sub to support new line from Kearney 115 kV sub.
210619 | 92180 | 144284 | NPPD | NE | Line - Kearney NE - Tower 115 kV | Kearney 115 kV Terminal Equipment | Regional Reliability | 2025-06-06 | 2022-06-01 | 2021-11-04 | DPA-2021-February-1278 | 2692377 | 2022 | 2899395.5368 | 5744680 | 5744680 | Complete |  |  |  |  | Install 115 kV terminal equipment at Kearney 115 kV sub to support a new line from Tower 115 kV sub.
210661 | 92308 | 144328 | EREC | SD// | Line Carpenter – Willow Lake 69 kV | Carpenter – Willow Lake 69 kV | Sponsored Upgrade | 2025-10-01 | 2021-11-23 | 2022-03-21 | SUS-018 | 13720246 | 2022 | 14775204.2215 | 0 |  | Complete |  |  |  |  | Build a new 14-mile 69 kV line from Carpenter – Willow Lake with a minimal emergency rating of 114 MVA | 69
| 92331 | 156034 | NPPD | NE | Gerald Gentlemen - Red Willow 345kV GEN-2018-45 and GEN-2018-046 Interconnection Costs | Build Gentleman Satellite substation | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 139900000 |  | In Service |  |  |  |  | Build Gentleman Satellite substation to facilitate the Build Keystone to Gentleman Second Line_345 kV | 345/345
| 92354 | 156183 | SPS | AR | Roadrunner 115kV Substation GEN-2018-052 Interconnection Costs | Roadrunner 115kV Substation GEN-2018-052 Interconnection (TOIF) (SWPS) | Generation Interconnection | 2026-06-30 |  |  | GI STUDIES |  |  | 0 | 1128837 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2018-052 (70MW/Battery/Storage), into the Point of Interconnection (POI) at Roadrunner 115kV Substation | 115/115
| 92354 | 156184 | SPS | AR | Roadrunner 115kV Substation GEN-2018-052 Interconnection Costs | Roadrunner 115kV Substation Interconnection Expansion (DISIS-2018-001) | Generation Interconnection | 2026-06-30 |  |  | GI STUDIES |  |  | 0 | 1039552 |  | On Schedule < 4 |  |  |  |  | Expand the Roadrunner 115kV Substation to accommodate the interconnection of GEN-2018-052 | 115/115
| 92368 | 156219 | SPS | TX | Tuco-Oklaunion 345kV GEN-2017-151 Interconnection Costs | Tuco-Oklaunion 345kV GEN-2018-015 Interconnection (TOIF) (SWPS) | Generation Interconnection | 2027-06-15 |  |  | GI STUDIES |  |  | 0 | 1860250 |  | On Schedule < 4 |  |  |  |  | Interconnection upgrades and cost estimates needed to interconnect the following Interconnection Customer facility, GEN-2018-015 (252MW/Solar), into the Point of Interconnection (POI) at Tuco-Oklaunion 345kV | 345/345
| 92368 | 156220 | SPS | TX | Tuco-Oklaunion 345kV GEN-2017-151 Interconnection Costs | Tuco-Oklaunion 345kV Line Tap (DISIS-2018-001) | Generation Interconnection | 2027-06-15 |  |  | GI STUDIES |  |  | 0 | 18641931 |  | On Schedule < 4 |  |  |  |  | Tap the Tuco-Oklaunion 345kV Line to accommodate the interconnection of GEN-2018-015 | 345/345
220722 | 92371 | 156240 | BEPC | ND | Line - North Dakota/Saskatchewan Border (Tableland) - Tande 230 kV | North Dakota/Saskatchewan Border (Tableland) - Tande 230 kV Ckt 1 | Transmission Service | 2027-10-01 | 2027-10-01 | 2023-05-24 | SPP- 2021-AG2 | 78880406 | 2023 | 84945569.3232 | 84734949 |  | On Schedule < 4 |  |  |  |  | Build new 67 mile 230 kV line from Tande substation to the United Sates/Canada border toward Sask Power’s Tableland substation. | 230
220722 | 92371 | 156241 | BEPC | ND | Line - North Dakota/Saskatchewan Border (Tableland) - Tande 230 kV | Tande 230 kV Terminal Equipment | Transmission Service | 2027-10-01 | 2027-10-01 | 2023-05-24 | SPP- 2021-AG2 | 2562090 | 2023 | 2759090.6886 | 2562090 |  | On Schedule < 4 |  |  |  |  | Install any necessary terminal equipment at the Tande substation to accommodate a terminal for the North Dakota/Saskatchewan Border (Tableland) - Tande 230 kV Ckt 1. | 230
220722 | 92372 | 156248 | BEPC | ND | Line - North Dakota/Saskatchewan Border (Tableland) - Wheelock 230 kV | North Dakota/Saskatchewan Border (Tableland) - Wheelock 230 kV Ckt 1 | Transmission Service | 2027-10-01 | 2027-10-01 | 2023-05-24 | SPP- 2021-AG2 | 65123051 | 2023 | 70130402.7677 | 73055656 |  | On Schedule < 4 |  |  |  |  | Build new 70 mile 230 kV line from Wheelock substation to the United States/Canada border toward Sask Power’s Tableland substation. | 230
220722 | 92372 | 156249 | BEPC | ND | Line - North Dakota/Saskatchewan Border (Tableland) - Wheelock 230 kV | Wheelock 230 kV Terminal Upgrade | Transmission Service | 2027-10-01 | 2027-10-01 | 2023-05-24 | SPP- 2021-AG2 | 2476563 | 2023 | 2666987.4645 | 2476563 |  | On Schedule < 4 |  |  |  |  | Install any necessary terminal equipment at Wheelock substation to accommodate a new terminal for the North Dakota/Saskatchewan Border (Tableland) - Wheelock 230 kV Ckt 1. | 230
210715 | 92394 | 156282 | WAPA | ND | Sub - Fargo 230 kV Terminal Upgrade | Fargo 230 kV Terminal Upgrade | Regional Reliability | 2025-12-31 | 2024-06-01 | 2022-12-09 | 2022 ITP | 3119998 | 2023 | 3277947.8988 | 243120 |  | Delay - Mitigation | 652435 | FARGO |  |  | Upgrade terminal conductor at Fargo 230 kV substation to support the line to Sheyenne | 230
210710 | 92381 | 156289 | EM | KS | Device - Craig 345 kV Relay | Craig 345 kV Relay | Regional Reliability | 2025-04-01 | 2024-06-01 | 2022-12-09 | 2022 ITP | 200000 | 2022 | 215378.124 | 181260 |  | Complete |  |  |  |  | Install a redundant relay at the Craig 345 kV substation | 345
210711 | 92393 | 156294 | GRDA | AR | Multi - Siloam Springs-Siloam Springs City 161 kV Terminal Upgrades | Siloam Springs City 161 kV Terminal Upgrade | Regional Reliability | 2024-12-11 | 2024-06-01 | 2022-12-09 | 2022 ITP | 324000 | 2023 | 332100 | 453000 | 109609.86 | Complete |  |  |  |  | Upgrade terminal equipment at Siloam Springs City 161 kV substation | 161
210708 | 92386 | 156299 | AEP | OK | Line - 36th & Lewis - 52nd & Delaware Tap 138 kV Rebuild | 36th & Lewis - 52nd & Delaware Tap 138 kV Ckt 1 Rebuild | Regional Reliability | 2027-06-01 | 2027-06-01 | 2022-12-09 | 2022 ITP | 951250 | 2023 | 1024392.2023 | 4951250 |  | On Schedule < 4 |  |  |  |  | Rebuild 138 kV line from 36th & Lewis to 52nd & Delaware Tap | 138
210708 | 92386 | 156300 | AEP | OK | Line - 36th & Lewis - 52nd & Delaware Tap 138 kV Rebuild | 36th & Lewis 138 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2027-06-01 | 2027-06-01 | 2022-12-09 | 2022 ITP | 540691 | 2023 | 582265.0662 | 540691 |  | On Schedule < 4 | 509800 | 36th & LEWIS |  |  | Replace wave traps at 36th & Lewis 138 kV substation | 138
220741 | 92400 | 156301 | GRDA | OK/ | Line - Kerr 161 kV - Maid 161 kV Ckt 1 & Ckt 2 Rebuild | Kerr - Maid 161 kV Ckt 1 Rebuild #2 | Regional Reliability | 2026-12-31 | 2024-04-01 | 2023-11-15 | 2023 ITP | 4923250 | 2024 | 5172489.5312 | 5846250 |  | Delay - Mitigation | 512635 | KERR 161 | 512648 | MAID 161 | Rebuild 5.5 miles of 161 kV Ckt 1 line from Kerr 161 kV substation to Maid 161 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 557 MVA. | 161
220741 | 92400 | 156302 | GRDA | OK | Line - Kerr 161 kV - Maid 161 kV Ckt 1 & Ckt 2 Rebuild | Kerr 161 kV Terminal Equipment | Regional Reliability | 2026-12-31 | 2024-04-01 | 2023-11-15 | 2023 ITP | 730200 | 2024 | 767166.375 | 730200 |  | Delay - Mitigation | 512635 | KERR 161 |  |  | Install any necessary terminal equipment at Kerr 161 kV substation to support the line from Kerr 161 kV substation to Maid 161 kV substation with a summer emergency rating of 557 MVA. | 161
220741 | 92400 | 156303 | GRDA | OK | Line - Kerr 161 kV - Maid 161 kV Ckt 1 & Ckt 2 Rebuild | Maid 161 kV Terminal Equipment | Regional Reliability | 2026-12-31 | 2024-04-01 | 2023-11-15 | 2023 ITP | 1107600 | 2024 | 1163672.25 | 1107600 |  | Delay - Mitigation | 512648 | MAID 161 |  |  | Install any necessary terminal equipment at Maid 161 kV substation to support the line from Maid 161 kV substation to Kerr 161 kV substation with a summer emergency rating of 557 MVA | 161
220741 | 92400 | 156304 | GRDA | OK/ | Line - Kerr 161 kV - Maid 161 kV Ckt 1 & Ckt 2 Rebuild | Kerr - Maid 161 kV Ckt 2 Rebuild | Regional Reliability | 2026-12-31 | 2024-04-01 | 2023-11-15 | 2023 ITP | 4923250 | 2024 | 5172489.5312 | 5846250 |  | Delay - Mitigation | 512635 | KERR 161 | 512648 | MAID 161 | Rebuild 5.5 miles of 161 kV Ckt 2 line from Kerr 161 kV to Maid 161 kV and upgrade any necessary terminal equipment to achieve a summer emergency rating of 557 MVA. | 161
220741 | 92400 | 156305 | GRDA | OK/ | Line - Kerr 161 kV - Maid 161 kV Ckt 1 & Ckt 2 Rebuild | Kerr 161 kV Terminal Equipment Ckt 2 | Regional Reliability | 2026-12-31 | 2024-04-01 | 2023-11-15 | 2023 ITP | 730200 | 2024 | 767166.375 | 730200 |  | Delay - Mitigation | 512635 | KERR 161 |  |  | Install any necessary terminal equipment at Kerr 161 kV substation to support the line from Kerr 161 kV substation to Maid 161 kV substation with a summer emergency rating of 557 MVA. | 161
220741 | 92400 | 156306 | GRDA | OK | Line - Kerr 161 kV - Maid 161 kV Ckt 1 & Ckt 2 Rebuild | Maid 161 kV Terminal Upgrade Ckt 2 | Regional Reliability | 2026-12-31 | 2024-04-01 | 2023-11-15 | 2023 ITP | 1107600 | 2024 | 1163672.25 | 1107600 |  | Delay - Mitigation | 512648 | MAID 161 |  |  | Install any necessary terminal equipment at Maid 161 kV substation to support the line from Maid 161 kV substation to Kerr 161 kV substation with a summer emergency rating of 557 MVA. | 161
210679 | 92402 | 156334 | MWE | ND | Device - Twelve Mile 115 kV Capacitor Bank | Twelve Mile 115 kV Capacitor Bank | Transmission Service | 2029-10-01 | 2029-10-01 | 2022-06-30 | SPP- 2021-AG2 | 571195 | 2022 | 630492.4037 | 571195 |  | On Schedule > 4 |  |  |  |  | Install 12 MVAR capacitor bank at Twelve Mile 115 kV substation. | 115
210713 | 92411 | 156372 | OGE | OK | Device - West Oak 138 kV Breakers | West Oak 138 kV Breaker #1 | Regional Reliability | 2024-02-29 | 2014-06-01 | 2022-12-09 | 2022 ITP | 166722 | 2023 | 170890.05 | 462388 |  | Complete | 514866 | WESTOAKS 138 |  |  | Upgrade breaker 4349 at West Oak 138 kV substation | 138
210713 | 92411 | 156373 | OGE | OK | Device - West Oak 138 kV Breakers | West Oak 138 kV Breaker #2 | Regional Reliability | 2024-02-29 | 2024-06-01 | 2022-12-09 | 2022 ITP | 166722 | 2023 | 170890.05 | 462388 |  | Complete | 514866 | WESTOAKS 138 |  |  | Upgrade breaker 4350 at West Oak 138 kV substation | 138
210713 | 92413 | 156375 | OGE | OK | Device - Cherry Creek 138 kV Breaker | Cherry Creek 138 kV Breaker | Regional Reliability | 2024-02-29 | 2024-06-01 | 2022-12-09 | 2022 ITP | 157787 | 2023 | 161731.675 | 462388 |  | In Service | 514957 | CHERRY CREEK 138 |  |  | Upgrade breaker 3848 at Cherry Creek 138 kV substation | 138
210713 | 92414 | 156376 | OGE | OK | Device - Indian Hill 138 kV Breaker | Indian Hill 138 kV Breaker | Regional Reliability | 2024-05-28 | 2024-06-01 | 2022-12-09 | 2022 ITP | 157506 | 2023 | 161443.65 | 112793 |  | In Service | 515380 | Indian Hills 138kv |  |  | Upgrade breaker 4852 at Indian Hill 138 kV substation | 138
210681 | 92421 | 156407 | SPS | NM | Multi - Crossroads - Hobbs - Roadrunner 345 kV dbl ckt | Crossroads 345 kV ckts 1 & 2 Terminal Equipment | Economic | 2025-05-13 | 2023-01-01 | 2022-09-12 | 2021 ITP | 16799460 | 2022 | 18091180.8951 | 22249517 |  | Complete |  |  |  |  | Install any necessary terminal equipment at Crossroads 345 kV to support a new double-circuit line to Hobbs 345 kV | 345
210681 | 92421 | 156408 | SPS | NM | Multi - Crossroads - Hobbs - Roadrunner 345 kV dbl ckt | Hobbs 345 kV ckts 1 & 2 Terminal Equipment #1 | Economic | 2025-11-07 | 2023-01-01 | 2022-09-12 | 2021 ITP | 14586640 | 2022 | 15708215.7933 | 24038399 |  | Closed Out |  |  |  |  | Install any necessary terminal equipment at Hobbs 345 kV to support a new double-circuit line from Crossroads 345 kV | 345
210681 | 92421 | 156409 | SPS | NM | Multi - Crossroads - Hobbs - Roadrunner 345 kV dbl ckt | Hobbs 345 kV ckts 1 & 2 Terminal Equipment #2 | Economic | 2025-04-25 | 2023-01-01 | 2022-09-12 | 2021 ITP | 27053744 | 2022 | 29133923.1495 | 17368687 |  | Complete |  |  |  |  | Install any necessary terminal equipment at Hobbs 345 kV to support a new double-circuit line from Roadrunner 345 kV | 345
210681 | 92421 | 156410 | SPS | NM | Multi - Crossroads - Hobbs - Roadrunner 345 kV dbl ckt | Roadrunner 345 kV ckts 1 & 2 Terminal Equipment | Economic | 2025-04-10 | 2023-01-01 | 2022-09-12 | 2021 ITP | 15831264 | 2022 | 17048539.7043 | 12173404 |  | Complete |  |  |  |  | Install any necessary terminal equipment at Roadrunner 345 kV to support a new double-circuit line from Hobbs 345 kV | 345
220726 | 92421 | 156411 | NEET | NM | Multi - Crossroads - Hobbs - Roadrunner 345 kV dbl ckt | Crossroads - Hobbs 345 kV ckts 1 & 2 | Economic | 2026-05-15 | 2023-01-01 | 2023-10-03 | 2021 ITP | 196135073 | 2023 | 211216020.3667 | 195489770.96 |  | Delay - Mitigation |  |  |  |  | Build a new 90.5 mile 345 kV double-circuit line from Crossroads 345 kV substation to Hobbs 345 kV substation with a summer rating of at least 2640 MVA.. | 345
220726 | 92421 | 156412 | NEET | NM | Multi - Crossroads - Hobbs - Roadrunner 345 kV dbl ckt | Hobbs - Roadrunner 345 kV ckts 1 & 2 | Economic | 2026-05-15 | 2023-01-01 | 2023-10-03 | 2021 ITP | 95479502 | 2023 | 102820980.1061 | 96124804.51 |  | Delay - Mitigation |  |  |  |  | Build a new 44.5 mile 345 kV double-circuit line from Hobbs 345 kV substation to Roadrunner 345 kV substation with a summer rating of at least 2640 MVA | 345
220751 | 92940 | 157186 | SEPC | KS | Device - Ellsworth Tap - Great Bend 115 kV Ckt 1 Structure Upgrade | Ellsworth Tap - Great Bend 115 kV Ckt 1 Structure Upgrade | Economic | 2027-06-30 | 2028-01-01 | 2023-11-19 | 2023 ITP | 750000 | 2024 | 787968.75 | 593064 |  | On Schedule < 4 | 539642 | Ellsworth Tap | 539678 | Mullergren 115 KV | Upgrade 25 structures of the 30.2 mile 115 kV line from Ellsworth Tap substation to Great Bend substation | 115
220746 | 92947 | 157202 | EM | KS | Sub - Craig 161 kV - Lenexa South 161 kV Ckt 2 Terminal Upgrades | Craig 161 kV Ckt 2 Terminal Upgrade | Economic | 2026-06-01 | 2025-01-01 | 2023-12-15 | 2023 ITP | 1329162 | 2024 | 1396450.8262 | 115898 |  | Delay - Mitigation | 542978 | CRAIG 161 KV |  |  | Upgrade any necessary terminal equipment at Craig 161 kV substation on the Lenexa South to Craig 161 kV line to achieve a summer emergency rating of 557 MVA. | 161
220746 | 92947 | 157203 | EM | KS | Sub - Craig 161 kV - Lenexa South 161 kV Ckt 2 Terminal Upgrades | Lenexa South 161 kV Ckt 2 Terminal Upgrade | Economic | 2026-06-01 | 2025-01-01 | 2023-12-15 | 2023 ITP | 1329161 | 2024 | 1396449.7756 | 37096 |  | Delay - Mitigation | 543038 | LENEXA SOUTH 161 KV |  |  | Upgrade any necessary terminal equipment at Lenexa South 161 kV substation on the Craig to Lenexa South 161 kV line to achieve a summer emergency rating of 557 MVA. | 161
220739 | 92955 | 157241 | OGE | OK | XFR - Seminole 345/138 kV Ckt3 | Seminole 345/138 kV Transformer Ckt 3 (138 kV) | Regional Reliability | 2025-12-01 | 2024-06-01 | 2023-12-15 | 2023 ITP | 9281667 | 2024 | 9513708.675 | 9281667 |  | Complete | 515045 | SEMINOLE 345 |  |  | Install a new 345/138 kV transformer at Seminole 138 kV substation to achieve a summer emergency rating of 448 MVA. | 345/138
220739 | 92955 | 157242 | OGE | OK | XFR - Seminole 345/138 kV Ckt3 | Seminole 345/138 kV Transformer Ckt 3 (345 kV) | Regional Reliability | 2025-12-01 | 2024-06-01 | 2023-12-15 | 2023 ITP | 5613374 | 2024 | 5753708.35 | 5613374 |  | Complete | 515044 | SEMINOLE 138 |  |  | Install a new 345/138 kV transformer at Seminole 345 kV substation to achieve a summer emergency rating of 675 MVA. | 345/138
220746 | 92969 | 157255 | EM | OK | Device - Blue Valley 161 kV Breaker | Blue Valley 161 kV Breaker #1 | Regional Reliability | 2025-09-26 | 2024-06-01 | 2023-12-15 | 2023 ITP | 310000 | 2024 | 317750 | 535352 |  | Complete | 543000 | BLUE VALLEY 161 KV |  |  | Upgrade breaker R8-14 at the Blue Valley 161 kV substation with 63 kA breakers. | 161
220746 | 92970 | 157256 | EM | KS | Device - Craig 161 kV Breaker | Craig 161 kV Breaker #1 | Regional Reliability | 2026-06-01 | 2024-06-01 | 2023-12-15 | 2023 ITP | 609491 | 2024 | 640346.4819 | 683403 |  | Delay - Mitigation | 542978 | CRAIG 161 KV |  |  | Upgrade breaker R1-11 at Craig 161 kV substation with 63 kA breakers. | 161
220746 | 92970 | 157257 | EM | KS | Device - Craig 161 kV Breaker | Craig 161 kV Breaker #3 | Regional Reliability | 2026-06-01 | 2024-06-01 | 2023-12-15 | 2023 ITP | 609490 | 2024 | 640345.4313 | 683403 |  | Delay - Mitigation | 542978 | CRAIG 161 KV |  |  | Upgrade breaker R3-6 at Craig 161 kV substation with 63 kA breakers | 161
220746 | 92970 | 157258 | EM | KS | Device - Craig 161 kV Breaker | Craig 161 kV Breaker #4 | Regional Reliability | 2026-06-01 | 2024-06-01 | 2023-12-15 | 2023 ITP | 609491 | 2024 | 640346.4819 | 683403 |  | Delay - Mitigation | 542978 | CRAIG 161 KV |  |  | Upgrade breaker R5-11 at Craig 161 kV substation with 63 kA breakers. | 161
220746 | 92970 | 157259 | EM | KS | Device - Craig 161 kV Breaker | Craig 161 kV Breaker #5 | Regional Reliability | 2026-06-01 | 2024-06-01 | 2023-12-15 | 2023 ITP | 609491 | 2024 | 640346.4819 | 683403 |  | Delay - Mitigation | 542978 | CRAIG 161 KV |  |  | Upgrade breaker R6-33 at Craig 161 kV substation with 63 kA breakers. | 161
220737 | 92974 | 157263 | AEP | OK | Line - Flournoy 138 kV- Oak Pan-Harr 138 kV - Longwood 138 kV | Longwood - Oak Pan-Harr 138 kV Ckt 1 Rebuild | Regional Reliability | 2028-06-01 | 2028-06-01 | 2023-12-15 | 2023 ITP | 4070000 | 2023 | 4382944.8234 | 4070000 |  | On Schedule > 4 | 508808 | LONGWOOD 138KV | 508816 | OAK PAN-HARR REC | Rebuild 1.8 miles of 138 kV line from Longwood 138 kV to Oak Pan-Harr 138 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 324 MVA. | 138 |  | 1.8
220737 | 92974 | 157264 | AEP | OK | Line - Flournoy 138 kV- Oak Pan-Harr 138 kV - Longwood 138 kV | Longwood 138 kV Terminal Upgrade | Regional Reliability | 2028-06-01 | 2028-06-01 | 2023-12-15 | 2023 ITP | 150000 | 2023 | 161533.593 | 150000 |  | On Schedule > 4 | 508808 | LONGWOOD 138KV |  |  | Upgrade any necessary terminal equipment at Longwood 138 kV substation on the Longwood to Oak Pan-Harr 138 kV line to achieve a summer emergency rating of 324 MVA. | 138
220737 | 92974 | 157266 | AEP | OK | Line - Flournoy 138 kV- Oak Pan-Harr 138 kV - Longwood 138 kV | Flournoy - Oak Pan-Harr 138 kV Ckt 1 Rebuild | Regional Reliability | 2028-06-01 | 2028-06-01 | 2023-12-15 | 2023 ITP | 15260000 | 2023 | 16433350.8612 | 15260000 |  | On Schedule > 4 | 507727 | FLOURNOY 138KV | 508816 | OAK PAN-HARR REC | Rebuild 10.4 miles of 138 kV line from Flournoy 138 kV substation to Oak Pan-Harr 138 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 287 MVA. | 138 |  | 10.4
220737 | 92976 | 157268 | AEP | AR | XFR - Turk 138/115 kV | Turk 138/115 kV Transformer Ckt 1 (138 kV) | Regional Reliability | 2027-04-25 | 2024-06-01 | 2023-12-15 | 2023 ITP | 5250000 | 2023 | 5653675.755 | 5250000 |  | Delay - Mitigation | 507454 | Turk 138 |  |  | Replace current 138/115 transformer Ckt 1 at Turk 138 kV substation to achieve a summer emergency rating of 250 MVA. | 138/115
220739 | 92980 | 157274 | OGE | OK | Sub - Newman Grace Tap - Woodward Nitrogen 69 kV Terminal Upgrade | Woodward Nitrogen 69 kV Terminal Upgrade | Regional Reliability | 2025-06-22 | 2024-06-01 | 2023-12-15 | 2023 ITP | 800000 | 2024 | 820000 | 800000 |  | Complete | 514779 | WOODWARD NITROGEN 69 |  |  | Upgrade any necessary terminal equipment at Woodward Nitrogen 69 kV substation on the Woodward Nitrogen to Newman Grace Tap 69 kV line to achieve a summer emergency rating of 71 MVA. | 69
220748 | 93107 | 157280 | WAPA | OK | Device Dawson County-Fort Peck 230 kV 40 MVAR Line Reactor | Dawson County-Fort Peck 230 kV Line Reactor | Regional Reliability | 2030-09-01 | 2024-06-01 | 2023-12-15 | 2023 ITP | 7300684 | 2024 | 7670281.1275 | 7300684 |  | Delay - Mitigation | 652405 | FT PECK |  |  | Install 40 MVAR reactor on the Dawson County-Fort Peck 230 kV Line | 230
220777 | 92986 | 157296 | SPS | NM | XFR - Phantom 345/115 kV Transformer & Capacitor Banks | XFR - Phantom 345/115 kV Transformer (345 kV) | Regional Reliability | 2026-06-15 | 2026-06-01 | 2024-05-06 | DPA-2022-March-1564 | 2777801 | 2024 | 2918427.1756 | 3224098 |  | Delay - Mitigation Window |  |  |  |  | Add new Phantom 345/115 kV transformer
220766 | 94550 | 157302 | SPS | NM | Line - Roadrunner - Red Bluff 115 kV Reconductor | Roadrunner - Red Bluff 115 kV Reconductor | Regional Reliability | 2025-02-13 | 2025-04-01 | 2024-01-31 | DPA-2022-March-1564 | 10491119 | 2024 | 10753396.975 | 10858947 |  | Complete |  |  |  |  | Reconductor the Roadrunner to Red Bluff 115 kV line and upgrade any necessary terminal equipment to increase the summer emergency rating above 203 MVA
220777 | 92986 | 157303 | SPS | NM | XFR - Phantom 345/115 kV Transformer & Capacitor Banks | Phantom 115 kV Cap Bank | Regional Reliability | 2025-12-15 | 2026-06-01 | 2024-05-06 | DPA-2022-March-1564 | 4706120 | 2024 | 4823773 | 6465378 |  | On Schedule < 4 |  |  |  |  | Add new 72 MVAR cap bank at Phantom 115 kV substation.
220766 | 94551 | 157304 | SPS | NM | Device - Livingston Ridge 115 kV Cap Bank | Livingston Ridge 115 kV Cap Bank | Regional Reliability | 2025-05-22 | 2025-06-01 | 2024-01-31 | DPA-2022-March-1564 | 6154470 | 2024 | 6308331.75 | 6515148 |  | Complete |  |  |  |  | Add new 57.6 MVAR cap bank at Livingston Ridge 115 kV substation.
220766 | 94552 | 157305 | SPS | NM | Device - Lynch 115 kV Cap Bank | Lynch 115 kV Cap Bank | Regional Reliability | 2026-05-15 | 2025-06-01 | 2024-01-31 | DPA-2022-March-1564 | 2796000 | 2024 | 2937547.5 | 3241331 |  | Delay - Mitigation |  |  |  |  | Add new 14.4 MVAR cap bank at Lynch 115 kV substation.
220777 | 92986 | 157307 | SPS | NM | XFR - Phantom 345/115 kV Transformer & Capacitor Banks | Phantom 345 kV Cap Bank | Regional Reliability | 2026-05-15 | 2026-06-01 | 2024-05-06 | DPA-2022-March-1564 | 23569618 | 2024 | 24762829.9112 | 33921929 |  | On Schedule < 4 |  |  |  |  | Add new 200 MVAR cap bank at Phantom 345 kV substation.
220766 | 94553 | 157308 | SPS | NM | Device - Malaga Bend115 kV Cap Bank | Malaga Bend 115 kV Cap Bank | Regional Reliability | 2025-04-04 | 2026-06-01 | 2024-01-31 | DPA-2022-March-1564 | 3598366 | 2024 | 3688325.15 | 4180163 |  | Complete |  |  |  |  | Add new 28.8 MVAR cap bank at Malaga Bend 115 kV substation.
220766 | 94554 | 157309 | SPS | NM | Device - North Loving 115/345 kV Cap Bank | North Loving 345 kV Cap Bank | Regional Reliability | 2026-05-15 | 2026-06-01 | 2024-01-31 | DPA-2022-March-1564 | 14842775 | 2024 | 15594190.4844 | 18957988 |  | On Schedule < 4 |  |  |  |  | Add new 100 MVAR cap bank at North Loving 345 kV substation.
220766 | 94554 | 157310 | SPS | NM | Device - North Loving 115/345 kV Cap Bank | North Loving 115 kV Cap Bank | Regional Reliability | 2025-08-27 | 2026-06-01 | 2024-01-31 | DPA-2022-March-1564 | 3735000 | 2024 | 3828375 | 3100327 |  | Complete |  |  |  |  | Add new 28.8 MVAR cap bank at North Loving 115 kV substation.
220747 | 92987 | 157375 | BEPC | ND | Device - Broadland 345 kV Reactor | Broadland 345 kV Reactor | Regional Reliability | 2029-09-12 | 2024-04-01 | 2023-12-15 | 2023 ITP | 9455440 | 2024 | 9934121.65 | 9455440 |  | Delay - Mitigation Window |  |  |  |  | Install 2nd 75 MVAR reactor at Broadland 345 kV substation | 345
220750 | 92989 | 157377 | SPS | TX | Sub - Moore Co 115 kV Terminal Upgrade | Moore Co 115 kV Terminal Upgrade | Regional Reliability | 2027-03-15 | 2027-06-01 | 2023-12-15 | 2023 ITP | 4163620 | 2024 | 4374403.2625 | 4108325 |  | On Schedule < 4 | 523304 | Moore County Interchange West Bus 115 kV |  |  | Upgrade any necessary terminal equipment at Moore Co 115 kV substation to achieve a summer emergency rating of 175 MVA. | 115
220743 | 92993 | 157383 | NPPD | NE | XFR - Fremont 115/69 kV & Sub 976 Terminal Upgrade | Sub 976 115/69 kV Transformer Ckt 2 (69 kV) | Economic | 2027-12-31 | 2025-01-01 | 2023-12-15 | 2023 ITP | 5700000 | 2024 | 5988562.5 | 5700000 |  | Delay - Mitigation | 640173 | Fremont |  |  | Install new 115/69 transformer at Fremont 115 kV substation | 115/69
220743 | 92993 | 157384 | NPPD | NE | XFR - Fremont 115/69 kV & Sub 976 Terminal Upgrade | Fremont 115/69 kV Transformer Ckt 2 (115 kV) | Economic | 2027-12-31 | 2025-01-01 | 2023-12-15 | 2023 ITP | 300000 | 2024 | 315187.5 | 300000 |  | Delay - Mitigation | 647976 | Sub 976 |  |  | Install 115 kV terminal equipment to support 115/69 transformer at Fremont 115 kV substation | 115/69
220745 | 92994 | 157385 | LES | NE | Multi - Sub 1214 - 70th & Bluff 161 kV Rebuild | Sub 1214 - 70th & Bluff 161 kV Ckt 1 Rebuild (LES) | Economic | 2029-03-01 | 2027-01-01 | 2023-12-15 | 2023 ITP | 1453879 | 2024 | 1527481.6244 | 1453879 |  | Delay - Mitigation | 646214 | Sub 1214 | 650169 | 70th & Bluff | Rebuild 17.7 miles of 161 kV Ckt 1 line from Sub 1214 161 kV substation to 70th & Bluff161 kV substation with a summer emergency rating of 215 MVA. | 161 |  | 17.7
220744 | 92994 | 157386 | OPPD | NE | Multi - Sub 1214 - 70th & Bluff 161 kV Rebuild | Sub 1214 161 kV Terminal Upgrade | Economic | 2027-01-01 | 2027-01-01 | 2023-12-15 | 2023 ITP | 114179 | 2024 | 119959.3119 | 114179 |  | On Schedule < 4 |  |  |  |  | Upgrade any necessary terminal equipment at Sub 1214 161 kV substation on the 70th & Bluff to Sub 1214 161 kV line to achieve a summer emergency rating of 215 MVA. | 161
220745 | 92994 | 157387 | LES | NE | Multi - Sub 1214 - 70th & Bluff 161 kV Rebuild | 70th & Bluff 161 kV Terminal Upgrade | Economic | 2029-12-31 | 2027-01-01 | 2023-12-15 | 2023 ITP | 2849669 | 2024 | 2993933.4931 | 2849669 |  | Delay - Mitigation | 650169 | 70th & Bluff |  |  | Upgrade any necessary terminal equipment at 70th & Bluff 161 kV substation on the Sub 1214 to 70th & Bluff 161 kV line to achieve a summer emergency rating of 215 MVA. | 161
220739 | 92996 | 157390 | OGE | OK | Multi - Southgate - Westmoore Tap - Pennsylvania 138 kV | Southgate - Westmoore Tap 138 kV Extend Line | Regional Reliability | 2025-12-01 | 2027-06-01 | 2023-12-15 | 2023 ITP | 6158692 | 2024 | 6312659.3 | 6158692 |  | Complete | 514887 | WESTMOORE 138 | 514928 | SOUTHGATE 138 | Extend Southgate - Westmoore Tap 138 kV 0.76 miles to Westmoore 138 kV substation, including structures suited for double circuit configuration. | 138
220739 | 92996 | 157392 | OGE | OK | Multi - Southgate - Westmoore Tap - Pennsylvania 138 kV | Westmoore 138 kV Terminal Upgrade #2 | Regional Reliability | 2025-12-01 | 2027-06-01 | 2023-12-15 | 2023 ITP | 3308294 | 2024 | 3391001.35 | 3308294 |  | Complete | 514887 | WESTMOORE 138 |  |  | Install any necessary terminal equipment at Westmoore 138 kV substation to support a new line from Westmoore substation to Southgate 138 kV substation with a summer emergency rating of 308 MVA. | 138
220739 | 92996 | 157393 | OGE | OK | Multi - Southgate - Westmoore Tap - Pennsylvania 138 kV | Pennsylvania 138 kV Terminal Upgrade | Regional Reliability | 2025-12-15 | 2027-06-01 | 2023-12-15 | 2023 ITP | 200000 | 2024 | 205000 | 200000 |  | Complete | 514925 | PENNSYLVANIA 138 |  |  | Install a 2000 Amp switch at the Pennsylvania 138 kV substation. | 138
220774 | 81701 | 157395 | OGE | OK | Line - Anadarko - Gracemont 138 kV double Ckt 2 & 3 | Gracemont 138 kV Ck 2 Terminal Upgrade | Economic | 2027-12-31 | 2023-11-14 | 2024-04-11 | 2023 ITP | 2177750 | 2024 | 2287998.5938 | 2177750 |  | Delay - Mitigation | 515802 | Gracemont 138 kV |  |  | Install any necessary terminal equipment at Gracemont 138 kV substation to support a second line from Gracemont to Anadarko 138 kV substation with a summer emergency rating of 286 MVA. | 138
220773 | 81701 | 157396 | WFEC | OK | Line - Anadarko - Gracemont 138 kV double Ckt 2 & 3 | Anadarko SPA 138 kV Ckt 3 Terminal Equipment | Economic | 2028-05-31 | 2023-11-14 | 2024-04-11 | 2023 ITP | 2500000 | 2023 | 2692226.55 | 483360 |  | Delay - Mitigation | 520814 | ANADARKO |  |  | Install any necessary terminal equipment at Anadarko SPA 138 kV substation to support a third line from Anadarko to Gracemont. | 138
220745 | 92994 | 157397 | LES | NE | Multi - Sub 1214 - 70th & Bluff 161 kV Rebuild | 70th & Bluff 161/115 kV Transformer Ckt 1 (115 kV) | Economic | 2029-12-31 | 2027-01-01 | 2023-12-15 | 2023 ITP | 6114594 | 2024 | 6424145.3213 | 6114594 |  | Delay - Mitigation | 650169 | 70th & Bluff |  |  | Upgrade 161/115 transformer Ckt 1 at 70th & Bluff 115 kV substation to achieve a summer emergency rating of 215 MVA. | 161/115
220749 | 92999 | 157403 | EKC | KS | Sub - Blackberry - Neosho 345 kV Terminal Equipment | Neosho 345 kV Terminal Upgrade | Economic | 2025-11-18 | 2025-01-01 | 2023-12-15 | 2023 ITP | 3415129 | 2024 | 3500507.225 | 1127466 |  | Complete | 532793 | NEOSHO 345 KV |  |  | Install any necessary terminal equipment at Neosho 345 kV substation on the Neosho to Blackberry 345 kV line to achieve a summer emergency rating of 870 MVA. | 345
220737 | 93019 | 157475 | AEP | OK | Line - Pine & Peoria Tap 138 kV - 46th Street Tap 138 kV - Tulsa North 138 kV Rebuild | Pine & Peoria Tap - 46th Street Tap 138 kV Ckt 1 Rebuild | Economic | 2026-05-02 | 2025-01-01 | 2023-12-15 | 2023 ITP | 1481809 | 2023 | 1595746.2127 | 1481809 |  | Delay - Mitigation | 509863 | PINE & PEORIA TAP | 509900 |  | Rebuild 0.5 miles of 138 kV Ckt 1 line from Pine & Peoria Tap 138 kV substation to 46th Street Tap 138 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 347 MVA. | 138 |  | 0.5
220737 | 93019 | 157517 | AEP | OK | Line - Pine & Peoria Tap 138 kV - 46th Street Tap 138 kV - Tulsa North 138 kV Rebuild | Tulsa North - 46th Street Tap 138 kV Ckt 1 Rebuild | Economic | 2027-01-21 | 2025-01-01 | 2023-12-15 | 2023 ITP | 14714997 | 2023 | 15846442.2426 | 14714997 |  | Delay - Mitigation | 509817 | TULSA NORTH | 509900 |  | Rebuild 5.2 miles of 138 kV Ckt 1 line from Tulsa North 138 kV substation to 46th Street Tap 138 kV substation to achieve a summer emergency rating of 278 MVA. | 138
220737 | 93019 | 157518 | AEP | OK | Line - Pine & Peoria Tap 138 kV - 46th Street Tap 138 kV - Tulsa North 138 kV Rebuild | Tulsa North 138 kV Terminal Upgrade | Economic | 2027-01-21 | 2025-01-01 | 2023-12-15 | 2023 ITP | 150000 | 2023 | 161533.593 | 150000 |  | Delay - Mitigation | 509817 | TULSA NORTH |  |  | Upgrade any necessary terminal equipment at Tulsa North 138 kV substation on the 46th Street Tap to Tulsa North 138 kV line to achieve a summer emergency rating of 278 MVA. | 138
220775 | 93038 | 157528 | AEP | OK | Line - Osage - Webb City Tap - Shidler 138 kV Rebuild | Shidler 138 kV Terminal Upgrade | Economic | 2024-07-31 | 2023-11-14 | 2024-04-11 | 2023 ITP | 150000 | 2024 | 150000 | 29515 | 36552 | Closed Out | 510403 | SHIDLER |  |  | Upgrade any necessary terminal equipment at Shidler 138 kV substation on the Webb City Tap to Shidler 138 kV line to achieve a summer emergency rating of 495 MVA. | 138
220774 | 93038 | 157530 | OGE | OK | Line - Osage - Webb City Tap - Shidler 138 kV Rebuild | Osage 138 kV Terminal Upgrade | Economic | 2026-12-01 | 2023-11-14 | 2024-04-11 | 2023 ITP | 1203344 | 2024 | 1264263.29 | 1203344 |  | Delay - Mitigation | 514743 | OSAGE 138 |  |  | Upgrade any necessary terminal equipment at Osage 138 kV substation on the Osage to Webb City Tap 138 kV line to achieve a summer emergency rating of 561 MVA. | 138
220743 | 93042 | 157594 | NPPD | NE | Multi - Gerald Gentleman Station - Ogallala 230 kV Terminal Upgrades | Gerald Gentleman Station - Ogallala 230 kV Line & Terminal Upgrades | Economic | 2025-12-10 | 2023-11-14 | 2023-12-15 | 2023 ITP | 1600000 | 2024 | 1640000 | 1758786 |  | Complete |  |  |  |  | Upgrade any necessary terminal equipment at Gerald Gentleman Station 230 kV substation on the Gerald Gentleman Station to Ogallala 230 kV line to achieve a summer emergency rating of 435 MVA. | 230
220743 | 93042 | 157595 | NPPD | NE | Multi - Gerald Gentleman Station - Ogallala 230 kV Terminal Upgrades | Ogallala 230 kV Terminal Upgrade | Economic | 2025-12-10 | 2023-11-14 | 2023-12-15 | 2023 ITP | 100000 | 2024 | 102500 | 103000 |  | Complete |  |  |  |  | Upgrade any necessary terminal equipment at Ogallala 230 kV substation on the Ogallala to Gerald Gentleman Station 230 kV line to achieve a summer emergency rating of 435 MVA. | 230
220749 | 93053 | 157620 | EKC | KS | XFR - Franklin 161/69 kV Ckt 2 | Franklin 161/69 kV Transformer Ckt 2 | Economic | 2026-12-31 | 2025-01-01 | 2023-12-15 | 2023 ITP | 3323769 | 2024 | 3492034.8056 | 6289328 |  | Delay - Mitigation |  |  |  |  | Install new 161/69 transformer Ckt 2 at Franklin 161/69 kV substation. | 161/69
220739 | 93062 | 157644 | OGE | OK | Line - Fitzgerald Creek - Kinze 138 kV | Fitzgerald Creek - Kinze 138 kV Line Tap | Economic | 2028-06-01 | 2025-01-01 | 2023-12-15 | 2023 ITP | 10673792 | 2024 | 11214152.72 | 10673792 |  | Delay - Mitigation | 514830 | FITZGERALD CREEK 138 | 515008 | KINZE 138 | Tap and extend the existing Fitzgerald Creek - Kinze 138 kV line by 2 miles to terminate at Valley 138 kV substation | 138
220826 | 93090 | 157696 | SPS | NM | Multi - Cunningham - Quahada 115 kV - Buckeye Tap New Line | Buckeye Tap 115 kV Ckt 1 Substation | Regional Reliability | 2029-10-15 | 2024-06-01 | 2024-11-14 | 2023 ITP | 16954186 | 2025 | 17378040.65 | 16954186 |  | Delay - Mitigation Window | 528348 | Buckeye Tap 115 kV |  |  | Build new substation at Buckeye Tap, with four new 115 kV line terminals, connecting the 115 kV lines to Buckeye Substation, Lea County REC, Cunningham Substation to support a new 115 kV line to the new Cunningham - Quahada 115 kV Tap substation with a summer emergency rating of 239 MVA. | 115
220825 | 93090 | 157697 | LEA | NM | Multi - Cunningham - Quahada 115 kV - Buckeye Tap New Line | Buckeye Tap to the Lea County REC Texaco Line Work | Regional Reliability | 2029-12-15 | 2024-06-01 | 2024-11-14 | 2023 ITP | 2347150 | 2025 | 2405828.75 |  |  | Delay - Mitigation | 528348 | Buckeye Tap 115 kV |  |  | Re-Terminate the Lea County REC 115kV line that connects at the Buckeye Tap, into the new SPS Buckeye Tap 115 Substation | 115
220755 | 93103 | 157736 | MGS | ND | Device - Devaul 2 115 kV Switched Shunt | Devaul 115 kV Reactor | Regional Reliability |  | 2024-04-01 | 2023-12-15 | 2023 ITP | 1671705 | 2024 | 1756335.0656 | 1671705 |  | Re-evaluation | 655747 |  |  |  | Install 15 MVAR reactor at Devaul 115 kV substation | 115
220826 | 93090 | 157794 | SPS | NM | Multi - Cunningham - Quahada 115 kV - Buckeye Tap New Line | Buckeye Tap - Cunningham - Quahada 115 kV Ckt 1 New Line. | Regional Reliability | 2029-10-15 | 2024-06-01 | 2024-11-14 | 2023 ITP | 3665669 | 2025 | 3757310.725 | 3665669 |  | Delay - Mitigation Window |  |  |  |  | Build a new 3.2-mile 115 kV Ckt 1 line from the Buckeye Tap 115 kV substation to the Cunningham - Quahada 115 kV New Substation. | 115 | 3.2
220826 | 93090 | 157796 | SPS | NM | Multi - Cunningham - Quahada 115 kV - Buckeye Tap New Line | Cunningham - Quahada 115 kV New Substation | Regional Reliability | 2029-10-15 | 2024-06-01 | 2024-11-14 | 2023 ITP | 15693322 | 2025 | 16085655.05 | 15693322 |  | Delay - Mitigation Window |  |  |  |  | Build a new 115 kV substation 8 miles west of Cunningham, cut-into the Cunningham - Quahada 115 kV line, with three new 115 kV line terminals, connecting the 115 kV lines to Buckeye Tap, Cunningham and Quahada. | 115
| 93109 | 157811 | TBD | AR/KS/OK | Line - Ft. Smith - Thistle 345 kV | Ft. Smith - Thistle 345 kV CKT 1 | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 461160280 |  | Identified |  |  |  |  | Build Ft. Smith - Thistle 345 kV circuit 1 | 345
| 93110 | 157812 | TBD | AR/KS/OK | Line - Flint Creek - Buffalo Flats 345 kV | Flint Creek - Buffalo Flats 345 kV | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 349831855 |  | Identified |  |  |  |  | Build Flint Creek - Buffalo Flats 345 kV | 345
| 93111 | 157813 | OGE | AR/OK | Line - Ft Smith - Sooner 345 kV | Ft Smith - Sooner 345 kV CKT 1 | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 290563847 |  | Identified |  |  |  |  | Build Ft Smith - Sooner 345 kV Circuit 1 | 345
| 93114 | 157824 | TBD | OK | Line - Matthewson - Riverside Station 345 kV | Riverside Station - Matthewson 345 kV (OGE) | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 180577999 |  | Identified |  |  |  |  | Riverside Station - Matthewson 345 kV circuit 1 New Line | 345
| 30823 | 157825 | SPS | TX | INACTIVES | Potter County Interchange - Tolk Station 345 kV | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 147667045 |  | Identified |  |  |  |  | Potter County Interchange - Tolk Station 345 kV circuit 1 New Line | 345
| 93116 | 157826 | MDU | SD | Multi - Twin Brooks 3 - Ellindale 3 - Groton Tap - Broadland 345 kV | Twin Brooks 3 to Ellendale 3 345 kV Tap | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 16467621 |  | Identified |  |  |  |  | Tap branch from Twin Brooks 3 to Ellendale 3 345 kV circuit 1 | 34
| 93116 | 157827 | WAPA | SD | Multi - Twin Brooks 3 - Ellindale 3 - Groton Tap - Broadland 345 kV | Groton Tap - Groton 345 kV | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 32935242 |  | Identified |  |  |  |  | New branch from Groton Tap to Groton 345 kV | 345
| 93116 | 157828 | WAPA | SD | Multi - Twin Brooks 3 - Ellindale 3 - Groton Tap - Broadland 345 kV | Broadland - Groton 345 kV | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 32935242 |  | Identified |  |  |  |  | New branch from Broadland to Groton 345 kV circuit 1 | 345
| 93117 | 157829 | EM | MO | Line - Nashua - Sibley 345 kV | Sibley - Nashua 345 kV | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 43969609 |  | Identified |  |  |  |  | Sibley - Nashua 345 kV Circuit 1 New Line | 345
| 93120 | 157846 | TBD | MO/OK/KS | Line - Hawthorne - Sibley 345 kV | Sibley - Hawthorn 345 kV CKT 2 | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 25368257 |  | Identified |  |  |  |  | Sibley - Hawthorn 345 kV Circuit 2 New Line | 345
| 93121 | 157847 | WFEC | OK | Multi - Anadarko - Gracemont 345 kV/138 kV | Anadarko 345/138 kV Transformer | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 4891214 |  | Identified |  |  |  |  | New 345/138 kV transformer at Anadarko circuit 1 | 345/138
| 93121 | 157848 | TBD | OK | Multi - Anadarko - Gracemont 345 kV/138 kV | Anadarko - Gracemont 345 kV | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 5619548 |  | Identified |  |  |  |  | Build new 345 kV line from Gracemont to Anadarko | 345
| 93121 | 157849 | WFEC | OK | Multi - Anadarko - Gracemont 345 kV/138 kV | Anadarko - Gracemont 345 kV (WFEC) | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 5619547 |  | Identified |  |  |  |  | New branch from Gracemont to Anadarko 345 kV circuit 1 | 345
| 93121 | 157850 | WFEC | OK | Multi - Anadarko - Gracemont 345 kV/138 kV | Anadarko 345 kV Substation | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 13972613 |  | Identified |  |  |  |  | New substation at Anadarko 345 kV | 345
| 93122 | 157851 | TBD | OK | Line - Cimarron - Norman Hill 345 kV Ckt 2 | Cimarron - Norman Hill 345 kV CKT 2 | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 20616250 |  | Identified |  |  |  |  | Cimarron - Norman Hill 345 kV circuit 2 New Line | 345
| 93116 | 157873 | TBD | SD | Multi - Twin Brooks 3 - Ellindale 3 - Groton Tap - Broadland 345 kV | Twin Brooks 3 to Ellendale 3 345 kV Tap (OTP) | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 16467621 |  | Identified |  |  |  |  | Tap branch from Twin Brooks 3 to Ellendale 3 345 kV circuit 1 | 345
| 93116 | 157875 | WAPA | SD | Multi - Twin Brooks 3 - Ellindale 3 - Groton Tap - Broadland 345 kV | Groton Tap 345 kV Sub | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 |  |  | Identified |  |  |  |  | Build new Groton Tap 345 kV substation | 345
220774 | 81701 | 157879 | OGE | OK | Line - Anadarko - Gracemont 138 kV double Ckt 2 & 3 | Anadarko - Gracemont 138 kV Ckt 3 New Line (OGE) | Economic | 2027-12-31 | 2023-11-14 | 2024-04-11 | 2023 ITP | 10000000 | 2024 | 10506250 | 10000000 |  | Delay - Mitigation | 515802 | Gracemont 138 kV | 520814 | ANADARKO | Build new 15 mile 138 kV Ckt 3 line from Anadarko 138 kV substation to Gracemont 138 kV substation as a double circuit to achieve a summer emergency rating of 478 MVA. | 138
220774 | 93038 | 157880 | OGE | OK | Line - Osage - Webb City Tap - Shidler 138 kV Rebuild | Webb City Tap - Osage 138 kV Ckt 1 Rebuild (OGE) | Economic | 2026-12-01 | 2023-11-14 | 2024-04-11 | 2023 ITP | 28880257 | 2024 | 30342320.0106 | 28880257 |  | Delay - Mitigation | 510376 | WEBB CITY TAP | 514743 | OSAGE 138 | Rebuild 20 miles of 138 kV line from Webb City Tap 138 kV substation to Osage 138 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 561 MV | 138
220774 | 81701 | 157897 | OGE | OK | Line - Anadarko - Gracemont 138 kV double Ckt 2 & 3 | Anadarko - Gracemont 138kV Ckt 2 New Line (OGE) | Economic | 2027-12-31 | 2023-11-14 | 2024-04-11 | 2023 ITP | 10000000 | 2024 | 10506250 | 10000000 |  | Delay - Mitigation |  |  |  |  | Build new 15-mile 138 kV Ckt 2 line from Anadarko 138 kV substation to Gracemont 138 kV substation as a double circuit to achieve a summer emergency rating of 478 MVA. | 138
220747 | 94080 | 158019 | BEPC | ND | Device - Groton 345 kV Reactor | Groton 345 kV Reactor | Regional Reliability | 2029-09-12 | 2024-04-01 | 2023-12-15 | 2023 ITP | 9263038 | 2024 | 9731979.2988 | 9263038 |  | Delay - Mitigation Window |  |  |  |  | Install 2nd 68 MVAR reactor at Groton 345 kV substation | 345
220762 | 93177 | 158042 | NPPD | NE | Multi - Norfolk-Stanton North 115 kV | Norfolk - Stanton North 115 kV line | Regional Reliability | 2026-11-01 | 2026-11-01 | 2023-12-20 | DPA-2021-October-1442 | 14436071 | 2024 | 15166897.0944 | 14436071 |  | On Schedule < 4 |  |  |  |  | Build new 7.5 mile 115 kV line from Norfolk to Stanton North | 115 | 7.5
220762 | 93177 | 158043 | NPPD | NE | Multi - Norfolk-Stanton North 115 kV | Hoskins 230/115 kV Transformer | Regional Reliability | 2026-11-01 | 2026-11-01 | 2023-12-20 | DPA-2021-October-1442 | 11617895 | 2024 | 12206050.9344 | 11617895 |  | On Schedule < 4 |  |  |  |  | Upgrade Hoskins 230/115 kV Transformer
220746 | 92970 | 158045 | EM | KS | Device - Craig 161 kV Breaker | Craig 161 kV Breaker #6 | Regional Reliability | 2026-06-01 | 2024-06-01 | 2023-12-15 | 2023 ITP | 609492 | 2024 | 640347.5325 | 683403 |  | Delay - Mitigation | 542978 | CRAIG 161 KV |  |  | Upgrade breaker R1-2 at Craig 161 kV substation with 63 kA breakers. | 161
220744 | 92993 | 158445 | OPPD | NE | XFR - Fremont 115/69 kV & Sub 976 Terminal Upgrade | Sub 976 69 kV Terminal Equipment | Economic | 2027-12-31 | 2025-01-01 | 2023-12-15 | 2023 ITP | 165695 | 2024 | 174083.3094 | 165695 |  | Delay - Mitigation Window |  |  |  |  | Install 69 kV terminal equipment at Sub 976 to support a new 115/69 kV transformer | 69
220723 | 93896 | 158447 | OPPD | NE | Line - S1281 - S1361 161 kV | S1281 - S1361 161 kV | Sponsored Upgrade | 2025-05-22 | 2024-12-31 | 2023-10-03 | SUS-038 | 3111647 | 2023 | 3269174.1294 | 3111647 |  | Closed Out |  |  |  |  | Replace S1361 - S1362 161 kV with new S1281 - S1361 161 kV line
220749 | 93900 | 158452 | EKC | KS | Sub - Benton 345 kV - Wichita 345 kV Terminal Upgrades | Benton 345 kV Terminal Upgrade | Economic | 2025-12-18 | 2023-11-14 | 2023-12-15 | 2023 ITP | 3415129 | 2024 | 3500507.225 | 783591 |  | Complete |  |  |  |  | Upgrade any necessary terminal equipment at Benton 345 kV substation on the Benton to Wichita 345 kV line to achieve a summer emergency rating of 1119 MVA. | 345
220749 | 93900 | 158453 | EKC | KS | Sub - Benton 345 kV - Wichita 345 kV Terminal Upgrades | Wichita 345 kV Terminal Upgrade | Economic | 2025-12-18 | 2023-11-14 | 2023-12-15 | 2023 ITP | 3415129 | 2024 | 3500507.225 | 147584 |  | Complete |  |  |  |  | Upgrade any necessary terminal equipment at Wichita 345 kV substation on the Wichita to Benton 345 kV line to achieve a summer emergency rating of 1119 MVA. | 345
| 93109 | 158510 | OGE | AR | Line - Ft. Smith - Thistle 345 kV | Ft. Smith 345 kV Terminal Equipment | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 2428753 |  | Identified |  |  |  |  | Install 345 kV terminal equipment at Ft. Smith to support new line from Thistle 345 kV
| 93109 | 158511 | SEPC | KS | Line - Ft. Smith - Thistle 345 kV | Thistle 345 kV Terminal Equipment | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 2428753 |  | Identified |  |  |  |  | Install 345 kV terminal equipment at Thistle to support new line from Ft. Smith 345 kV
| 93110 | 158512 | EM | KS | Line - Flint Creek - Buffalo Flats 345 kV | Buffalo Flats 345 kV Terminal Equipment | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 2428753 |  | Identified |  |  |  |  | Install 345 kV terminal equipment at Buffalo Flats to support new line from Flint Creek 345 kV
| 93110 | 158513 | AEP | AR | Line - Flint Creek - Buffalo Flats 345 kV | Flint Creek 345 kV Terminal Equipment | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 2428753 |  | Identified |  |  |  |  | Install 345 kV terminal equipment at Flint Creek to support new line from Buffalo Flats 345 kV
| 93111 | 158514 | OGE | AR | Line - Ft Smith - Sooner 345 kV | Ft. Smith 345 kV Terminal Equipment #2 | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 2428753 |  | Identified |  |  |  |  | Install 345 kV terminal equipment at Ft. Smith to support new line from Sooner 345 kV
| 93111 | 158515 | OGE | OK | Line - Ft Smith - Sooner 345 kV | Sooner 345 kV Terminal Equipment | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 2428753 |  | Identified |  |  |  |  | Install 345 kV terminal equipment at Sooner to support new line from Ft. Smith 345 kV
| 93113 | 158520 | AECI | MO | Line - Huben - Lacygne 345 kV | Huben 345 kV Terminal Equipment | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 2428753 |  | Identified |  |  |  |  | Install 345 kV terminal equipment at Huben to support new line from Lacygne 345 kV
| 93113 | 158521 | EM | KS | Line - Huben - Lacygne 345 kV | Lacygne 345 kV Terminal Equipment | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 2428753 |  | Identified |  |  |  |  | Install 345 kV terminal equipment at Lacygne to support new line from Huben 345 kV
| 93114 | 158522 | OGE | OK | Line - Matthewson - Riverside Station 345 kV | Matthewson 345 kV Terminal Equipment | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 2428753 |  | Identified |  |  |  |  | Install 345 kV terminal equipment at Matthewson to support new line from Riverside Station 345 kV
| 93114 | 158523 | AEP | OK | Line - Matthewson - Riverside Station 345 kV | Riverside Station 345 kV Terminal Equipment | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 2428753 |  | Identified |  |  |  |  | Install 345 kV terminal equipment at Riverside Station to support new line from Matthewson 345 kV
| 30823 | 158524 | SPS | TX | INACTIVES | Potter County Interchange 345 kV Terminal Equipment | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 2428753 |  | Identified |  |  |  |  | Install 345 kV terminal equipment at Potter Co. to support new line from Tolk 345 kV
| 30823 | 158525 | SPS | TX | INACTIVES | Tolk Station 345 kV Terminal Equipment | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 2428753 |  | Identified |  |  |  |  | Install 345 kV terminal equipment at Tolk to support new line from Potter Co. 345 kV
| 93117 | 158526 | EM | MO | Line - Nashua - Sibley 345 kV | Nashua 345 kV terminal Equipment | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 2428753 |  | Identified |  |  |  |  | Install 345 kV terminal equipment at Nashua to support new line from Sibley 345 kV
| 93117 | 158527 | EM | MO | Line - Nashua - Sibley 345 kV | Sibley 345 kV Terminal Equipment | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 2428753 |  | Identified |  |  |  |  | Install 345 kV terminal equipment at Sibley to support new line from Nashua 345 kV
| 93120 | 158530 | AEP | OK | Line - Hawthorne - Sibley 345 kV | Hawthorn 345 kV Terminal Equipment #2 | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 2428753 |  | Identified |  |  |  |  | Install 345 kV terminal equipment at Hawthorn to support new line from Sibley 345 kV
| 93120 | 158531 | EM | MO | Line - Hawthorne - Sibley 345 kV | Sibley 345 kV Terminal Equipment #2 | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 2428753 |  | Identified |  |  |  |  | Install 345 kV terminal equipment at Sibley to support new line from Hawthorn 345 kV
| 93122 | 158532 | OGE | OK | Line - Cimarron - Norman Hill 345 kV Ckt 2 | Cimarron 345 kV Terminal Equipment | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 2428753 |  | Identified |  |  |  |  | Install 345 kV terminal equipment at Cimarron to support new line from Norman Hill 345 kV
| 93122 | 158533 | OGE | OK | Line - Cimarron - Norman Hill 345 kV Ckt 2 | Norman Hill 345 kV Terminal Equipment | Economic |  | 2042-01-01 |  | 2022 20 Year Assessment |  |  | 0 | 2428753 |  | Identified |  |  |  |  | Install 345 kV terminal equipment at Norman Hill to support new line from Cimarron 345 kV
220772 | 94010 | 158573 | OGE | OK | Line - Mathewson 345 kV - Redbud 345 kV | Redbud 345 kV Terminal Upgrade | Economic | 2026-08-28 | 2025-01-01 | 2024-03-25 | 2023 ITP | 3579283 | 2024 | 3760484.2019 | 4648981 |  | Delay - Mitigation | 514908 | ARCADIA 345 |  |  | Install any necessary terminal equipment at Redbud 345 kV substation to support a new line from Redbud 345 kV substation to Matthewson 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220772 | 94010 | 158574 | OGE | OK | Line - Mathewson 345 kV - Redbud 345 kV | Matthewson 345 kV Terminal Equipment #2 | Economic | 2027-12-01 | 2025-01-01 | 2024-03-25 | 2023 ITP | 3952014 | 2024 | 4152084.7088 | 3952014 |  | Delay - Mitigation | 515497 | MATHEWSON 345 |  |  | Install any necessary terminal equipment at Matthewson 345 kV substation to support a new line from Matthewson 345 kV substation to Redbud 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220780 | 94067 | 158629 | SPS | TX | XFR-Potter County 345/230 kV Ckt1 & Ckt2 | Potter County 345/230 kV Transformer Ckt 2 (345 kV) | Economic | 2028-12-15 | 2023-11-14 | 2024-05-24 | 2023 ITP | 9642000 | 2024 | 10130126.25 | 11014456 |  | Delay - Mitigation | 523961 | Potter County Interchange 345 kV | 523959 | Potter County Interchange 230 kV | Install new 345/230 transformer at Potter County 345 kV substation CKt2 | 345
220780 | 94067 | 158630 | SPS | TX | XFR-Potter County 345/230 kV Ckt1 & Ckt2 | Potter County 345/230 kV Transformer Ckt 1 (230 kV) | Economic | 2028-12-15 | 2023-11-14 | 2024-05-24 | 2023 ITP | 5577000 | 2024 | 5859335.625 | 5577000 |  | Delay - Mitigation | 523961 | Potter County Interchange 345 kV | 523959 | Potter County Interchange 230 kV | Expand and replace 230 kV terminal equipment at Potter County substation to support the replacement of the 345/230 kV transformer ckt 1 and the new 345/230 kV transformer ckt 2 | 230
220780 | 94067 | 158631 | SPS | TX | XFR-Potter County 345/230 kV Ckt1 & Ckt2 | Potter County 345/230 kV Transformer Ckt 1 | Economic | 2028-12-15 | 2023-11-14 | 2024-05-24 | 2023 ITP | 10187000 | 2024 | 10702716.875 | 11709865 |  | Delay - Mitigation | 523961 | Potter County Interchange 345 kV | 523959 | Potter County Interchange 230 kV | Replace existing 345/230 kV transformer at Potter County substation ckt 1 | 230
220780 | 94067 | 158632 | SPS | TX | XFR-Potter County 345/230 kV Ckt1 & Ckt2 | Potter County 345 kV Substation Expansion | Economic | 2028-12-15 | 2023-11-14 | 2024-05-24 | 2023 ITP | 10545000 | 2024 | 11078840.625 | 10545000 |  | Delay - Mitigation | 523961 | Potter County Interchange 345 kV | 523959 | Potter County Interchange 230 kV | Expand and replace 345 kV terminal equipment at Potter County substation to support the replacement of the 345/230 kV transformer ckt 1 and the new 345/230 kV transformer ckt 2 | 345
220774 | 81701 | 158637 | OGE | OK | Line - Anadarko - Gracemont 138 kV double Ckt 2 & 3 | Gracemont 138 kV Ckt 3 Terminal Equipment | Economic | 2027-12-31 | 2023-11-14 | 2024-04-11 | 2023 ITP | 2177750 | 2024 | 2287998.5938 | 2177750 |  | Delay - Mitigation | 515802 | Gracemont 138 kV |  |  | Install any necessary terminal equipment at Gracemont 138 kV substation to support a third 138 kV line from Anadarko to Gracemont to achieve a summer emergency rating of 478 MVA | 138/138
220773 | 81701 | 158638 | WFEC | OK | Line - Anadarko - Gracemont 138 kV double Ckt 2 & 3 | Anadarko SPA 138 kV Ckt 2 Terminal Equipment | Economic | 2028-05-31 | 2023-11-14 | 2024-04-11 | 2023 ITP | 2500000 | 2023 | 2692226.55 | 2500000 |  | Delay - Mitigation | 520814 | ANADARKO |  |  | Install any necessary terminal equipment at Anadarko SPA 138 kV to support a second 138 kV line from Anadarko to Gracemont. | 138/138
220791 | 94134 | 158640 | EKC | KS | Multi - Atlantic- Craig - West Gardener 345/115 kV | Atlantic Substation 115 kV | Regional Reliability | 2025-04-02 | 2027-06-01 | 2024-11-04 | 2023 ITP | 18118475 | 2024 | 18571436.875 | 16068122 |  | Complete | 533279 |  |  |  | Build a new 115 kV substation at the new intersection of West Gardner-Craig and Atlantic-Eudora Township. | 115
220791 | 94134 | 158641 | EKC | KS | Multi - Atlantic- Craig - West Gardener 345/115 kV | Atlantic Substation 345 kV | Regional Reliability | 2025-04-02 | 2027-06-01 | 2024-11-04 | 2023 ITP | 28916015 | 2024 | 29638915.375 | 25407790 |  | Complete | 542940 |  |  |  | Build a new 345 kV substation at the new intersection of West Gardner-Craig and Atlantic -Eudora Township. | 345
220791 | 94134 | 158645 | EKC | KS | Multi - Atlantic- Craig - West Gardener 345/115 kV | Eudora Township – Atlantic 115 kV Tap | Regional Reliability | 2025-05-16 | 2027-06-01 | 2024-11-04 | 2023 ITP | 7584713 | 2024 | 7774330.825 | 6903534 |  | Complete |  |  |  |  | Tap the existing Eudora Township - Atlantic 115 kV near Atlantic | 115/115
220792 | 94134 | 158646 | EM | KS | Multi - Atlantic- Craig - West Gardener 345/115 kV | West Gardner - Craig 345 kV | Regional Reliability | 2025-04-02 | 2027-06-01 | 2024-11-04 | 2023 ITP | 30685881 | 2024 | 31453028.025 | 30189542 |  | Complete |  |  |  |  | Extend the existing West Gardner - Craig 345 kV line 10.3 miles to intersect with the Atlantic – Eudora Township 115 kV line. | 345
220791 | 94134 | 158648 | EKC | KS | Multi - Atlantic- Craig - West Gardener 345/115 kV | Atlantic 345/115 kV Transformer (115 kV) | Regional Reliability | 2025-08-14 | 2027-06-01 | 2024-11-04 | 2023 ITP | 15434743 | 2024 | 15820611.575 | 18659127 |  | Complete |  |  |  |  | Install two new 345/115 transformer at Atlantic 115 kV substation | 345/115
220749 | 94153 | 158654 | EKC | KS | XFR - 87th St. 345/115 kV. Ckt 2 | 87th St. 345/115 kV Transformer | Regional Reliability | 2024-05-30 | 2025-01-01 | 2023-12-15 | 2023 ITP | 10200000 | 2024 | 10200000 | 11084701 |  | Complete |  |  |  |  | Transformer ratings 400/440/400/440 MVA (SN/SE/WN/WE) must be met. Terminal equipment must support new 345/115 kV transformer with 675 MVA summer emergency rating. | 345/115
220777 | 92986 | 159052 | SPS | NM | XFR - Phantom 345/115 kV Transformer & Capacitor Banks | XFR - Phantom 345/115 kV Transformer (115 kV) | Regional Reliability | 2026-06-30 | 2026-06-01 | 2024-05-06 | DPA-2022-March-1564 | 12078558 | 2024 | 12690034.9987 | 15797807 |  | Delay - Mitigation Window |  |  |  |  | Add new Phantom 345/115 kV transformer
220791 | 94134 | 159064 | EKC | KS | Multi - Atlantic- Craig - West Gardener 345/115 kV | Atlantic Terminal Equipment 345 kV Transformer(345 kV) | Regional Reliability | 2025-04-02 | 2027-06-01 | 2024-11-04 | 2023 ITP | 750498 | 2024 | 769260.45 | 724630 |  | Complete |  |  | 533279 |  | Install 345 kV terminal equipment to support 345/115 transformer at Atlantic 345 kV substation | 115
220904 | 94567 | 159073 | EREC | SD | Multi - Marion Area 115 kV Voltage Conversion Reconfig | North Marion - Montrose Manual 115 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-07-01 | 2027-11-12 | 2025-06-19 | 2024 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 655014 |  | 655020 |  | Convert 2.5-mile 69kV Ckt 1 line from North Marion to Montrose Manual to 115 kV | 115
220904 | 94567 | 159118 | EREC | SD | Multi - Marion Area 115 kV Voltage Conversion Reconfig | Dolton Manual 115 kV New Switch | Regional Reliability | 2026-07-15 | 2027-11-12 | 2025-06-19 | 2024 ITP | 152000 | 2025 | 155800 | 152000 | 152000 | NTC - Commitment Window | 655025 |  |  |  | Install 115 kV Switch at Dolton Manual | 115
220904 | 94567 | 159121 | EREC | SD | Multi - Marion Area 115 kV Voltage Conversion Reconfig | Marion Industrial 115 kV New Substation | Regional Reliability | 2027-11-12 | 2027-11-12 | 2025-06-19 | 2024 ITP | 4025000 | 2025 | 4125625 | 4025000 |  | NTC - Commitment Window | 655165 |  |  |  | Install 115 kV new substation at Marion Industrial | 115
220904 | 94567 | 159123 | EREC | SD | Multi - Marion Area 115 kV Voltage Conversion Reconfig | Parker City 115 kV New Substation | Regional Reliability | 2027-11-12 | 2027-11-12 | 2025-06-19 | 2024 ITP | 3525000 | 2025 | 3613125 | 3525000 |  | NTC - Commitment Window | 655188 |  |  |  | Install 115 kV new substation at Parker City | 115
220904 | 94567 | 159144 | EREC | SD | Multi - Marion Area 115 kV Voltage Conversion Reconfig | Canistota 69-kV Substation Voltage Conversion | Regional Reliability | 2026-08-14 | 2027-11-12 | 2025-06-19 | 2024 ITP | 275000 | 2025 | 281875 | 275000 |  | NTC - Commitment Window | 655532 |  |  |  | Convert 69 kV Substation at Canistota to 115 kV | 115
220904 | 94567 | 159162 | EREC | SD | Multi - Marion Area 115 kV Voltage Conversion Reconfig | Canistota 115 kV Capacitor | Regional Reliability | 2026-08-14 | 2027-11-12 | 2025-06-19 | 2024 ITP | 400000 | 2025 | 410000 | 400000 |  | NTC - Commitment Window | 655532 |  |  |  | Install 2.4 MVAR capacitor at Canistota 115 kV substation | 115
220904 | 94567 | 159166 | EREC | SD | Multi - Marion Area 115 kV Voltage Conversion Reconfig | Dolton Manual - Canistota 115 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-07-01 | 2027-11-12 | 2025-06-19 | 2024 ITP |  |  | 0 | 0 |  | Complete | 655025 |  | 655532 |  | Convert 4-mile 69 kV Ckt 1 line from Dolton Manual to Canistota to 115 kV | 115
220904 | 94567 | 159176 | EREC | SD | Multi - Marion Area 115 kV Voltage Conversion Reconfig | VT Hanlon 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2025-11-14 | 2027-11-12 | 2025-06-19 | 2024 ITP | 1235000 | 2025 | 1235000 | 1235000 |  | NTC - Commitment Window | 655493 |  |  |  | Install any necessary terminal equipment at VT Hanlon 115 kV substation to support the voltage conversion from VT Hanlon 115 kV substation to Montrose Manual 115 kV switch with a summer emergency rating of 139 MVA. | 115
220904 | 94567 | 159181 | EREC | SD | Multi - Marion Area 115 kV Voltage Conversion Reconfig | Marion - Parker City 115 kV Ckt 1 Rebuild | Regional Reliability | 2026-02-27 | 2027-11-12 | 2025-06-19 | 2024 ITP | 2480000 | 2025 | 2542000 | 2480000 |  | NTC - Commitment Window | 655187 |  | 655188 |  | Rebuild 6.3-mile 69 kV Ckt 1 line from Marion 115 kV substation to Parker City and upgrade any necessary terminal equipment to achieve a summer emergency rating of 139 MVA. | 115
220904 | 94567 | 159183 | EREC | SD | Multi - Marion Area 115 kV Voltage Conversion Reconfig | Marion Industrial - Marion 115 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-07-01 | 2027-11-12 | 2025-06-19 | 2024 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 655165 |  | 655187 |  | Convert 2.5-mile 69 kV Ckt 1 line from Marion Industrial to Marion to 115 kV | 115
220904 | 94567 | 159185 | EREC | SD | Multi - Marion Area 115 kV Voltage Conversion Reconfig | Marion Industrial 115 kV Capacitor Bank | Regional Reliability | 2026-05-18 | 2027-11-12 | 2025-06-19 | 2024 ITP | 565000 | 2025 | 579125 | 565000 |  | NTC - Commitment Window | 655346 |  |  |  | Install 7.2 MVAR switched shunt at Marion Industrial 115 kV substation | 115
220904 | 94567 | 159192 | EREC | SD | Multi - Marion Area 115 kV Voltage Conversion Reconfig | Montrose Manual – VT Hanlon 115 kV Ckt 1 | Regional Reliability | 2024-07-01 | 2027-11-12 | 2025-06-19 | 2024 ITP |  |  | 0 | 0 |  | Complete | 655020 |  | 655493 |  | Convert 3.5-mile 69 kV Ckt 1 line from Montrose Manual to VT Hanlon to 115 kV Voltage Conversion | 115
220904 | 94567 | 159195 | EREC | SD | Multi - Marion Area 115 kV Voltage Conversion Reconfig | North Marion - Canistota 115 kV Ckt 1 Voltage Conversion | Regional Reliability | 2024-07-01 | 2027-11-12 | 2025-06-19 | 2024 ITP |  |  | 0 | 0 |  | Complete | 655014 |  | 655532 |  | Convert 9-mile 69 kV Ckt 1 line from North Marion to Canistota to 115 kV | 115
220904 | 94567 | 159212 | EREC | SD | Multi - Marion Area 115 kV Voltage Conversion Reconfig | Turkey Ridge Manual 115 kV New Switch | Regional Reliability | 2025-11-28 | 2027-11-12 | 2025-06-19 | 2024 ITP | 152000 | 2025 | 152000 | 152000 |  | NTC - Commitment Window | 655106 |  |  |  | Install 115 kV new switch at Turkey Ridge Manual | 115
220904 | 94567 | 159214 | EREC | SD | Multi - Marion Area 115 kV Voltage Conversion Reconfig | Turkey Ridge Manual - Turner County 115 kV Ckt 1 New Line | Regional Reliability | 2026-11-13 | 2027-11-12 | 2025-06-19 | 2024 ITP | 5880000 | 2025 | 6027000 | 5880000 |  | NTC - Commitment Window | 655106 |  |  |  | Build a 14.5-mile 115 kV Ckt 1 line from Turkey Ridge Manual 115 kV switch to Turner County 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 112 MVA. | 115
220904 | 94567 | 159216 | EREC | SD | Multi - Marion Area 115 kV Voltage Conversion Reconfig | Turkey Ridge Manual – Hutchinson County 115 kV Ckt 1 New Line | Regional Reliability | 2026-11-13 | 2027-11-12 | 2025-06-19 | 2024 ITP | 3280000 | 2025 | 3362000 | 3280000 |  | NTC - Commitment Window | 655106 |  |  |  | Build 8.2-mile 115 kV Ckt 1 line from Turkey Ridge Manual 115 kV switch to Hutchinson County 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 112 MVA. | 115
220904 | 94567 | 159220 | EREC | SD | Multi - Marion Area 115 kV Voltage Conversion Reconfig | Parker City - Turner County 115 kV Ckt 1 New Line | Regional Reliability | 2026-11-13 | 2027-11-12 | 2025-06-19 | 2024 ITP | 4675000 | 2025 | 4791875 | 4675000 |  | NTC - Commitment Window | 655188 |  |  |  | Build a 12- mile 115 kV Ckt 1 line from Parker City 115 kV substation to Turner County 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 139 MVA. | 115
220904 | 94567 | 159229 | EREC | SD | Multi - Marion Area 115 kV Voltage Conversion Reconfig | Turner County 115 kV New Substation | Regional Reliability | 2026-11-13 | 2027-11-12 | 2025-06-19 | 2024 ITP | 5575000 | 2025 | 5714375 | 5575000 |  | On Schedule < 4 |  |  |  |  | Install 115 kV new substation at Turner County | 115
220904 | 94567 | 159230 | EREC | SD | Multi - Marion Area 115 kV Voltage Conversion Reconfig | Hutchinson County 115 kV New Substation | Regional Reliability | 2025-11-21 | 2027-11-12 | 2025-06-19 | 2024 ITP | 4825000 | 2025 | 4825000 | 4825000 |  | NTC - Commitment Window |  |  |  |  | Install 115 kV new substation at Hutchinson County | 115
220923 | 94571 | 159234 | WAPA | SD | Multi - Sioux Falls 115 kV System Reconfig | Sioux Falls 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2028-06-30 | 2025-06-01 | 2025-07-21 | 2024 ITP | 145000 | 2025 | 148625 | 145000 |  | NTC - Commitment Window | 652524 | SIOUX FALLS |  |  | Install any necessary terminal equipment at Sioux Falls 115 kV substation to support tapping the existing line from Sioux Falls 115 kV substation to Beresford 115 kV substation for the new tap station Lincoln County 115 kV (owned by EREPC) with a summer emergency rating of 120 MVA. | 115
220923 | 94571 | 159235 | WAPA | SD | Multi - Sioux Falls 115 kV System Reconfig | Beresford 115 kV - Sioux Falls 115 kV Line Tap | Regional Reliability | 2028-06-30 | 2025-06-01 | 2025-07-21 | 2024 ITP | 2904148 | 2025 | 2976751.7 | 2904148 |  | NTC - Commitment Window | 652502 | BERSFORD | 652524 | SIOUX FALLS | Support the transmission line tap work to reroute the existing Beresford 115 kV - Sioux Falls 115 kV line into and out of (approximately 1 mile) to Lincoln County 115 kV substation (owned by EREPC). | 115
220846 | 94571 | 159237 | EREC | SD | Multi - Sioux Falls 115 kV System Reconfig | Lincoln County 115 kV New Substation | Regional Reliability | 2026-12-01 | 2025-06-01 | 2024-12-13 | 2024 ITP | 8651000 | 2025 | 8867275 | 8651000 |  | Delay - Mitigation Window | 655362 |  |  |  | Install 115 kV new substation at Lincoln County | 115
220846 | 94571 | 159240 | EREC | SD | Multi - Sioux Falls 115 kV System Reconfig | 4 Mile Creek 115 kV New Substation | Regional Reliability | 2026-12-01 | 2025-06-01 | 2024-12-13 | 2024 ITP | 6500000 | 2025 | 6662500 | 6500000 |  | Delay - Mitigation Window | 655349 |  |  |  | Install 115 kV new substation at 4 Mile Creek. | 115
220809 | 94576 | 159250 | MWE | ND | Line - Crane Creek 115 kV - Satterthwaite 115 kV New Line | Crane Creek - Satterthwaite115 kV Ckt 1 New Line | Regional Reliability | 2027-12-31 | 2028-01-01 | 2024-12-13 | 2024 ITP | 11454000 | 2025 | 11740350 | 14500000 |  | On Schedule < 4 | 655906 |  | 655967 |  | Build 12.6 mile 115 kV Ckt 1 line from Crane Creek 115 kV substation to Satterthwaite 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA. | 115
220827 | 94576 | 159251 | BEPC | ND | Line - Crane Creek 115 kV - Satterthwaite 115 kV New Line | Finstad 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2027-12-31 | 2028-01-01 | 2024-12-13 | 2024 ITP | 3309335 | 2025 | 3392068.375 | 3309335 |  | On Schedule < 4 | 655906 |  |  |  | Install any necessary terminal equipment at Finstad 115 kV substation to support a new line from Finstad 115 kV substation to Satterwaite 115 kV substation with a summer emergency rating of 239 MVA. | 115
220809 | 94576 | 159252 | MWE | ND | Line - Crane Creek 115 kV - Satterthwaite 115 kV New Line | Satterthwaite 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2027-12-31 | 2028-01-01 | 2024-12-13 | 2024 ITP | 899922 | 2025 | 922420.05 | 1303988 |  | On Schedule < 4 | 655967 |  |  |  | Install any necessary terminal equipment at Satterthwaite 115 kV substation to support a new line from Satterthwaite 115 kV substation to Crane Creek 115 kV substation with a summer emergency rating of 239 MVA. | 115
220817 | 94584 | 159258 | SPS | NM | XFR - Road Runner 345/115 kV Ckt 2 | Roadrunner 345/115 kV Transformer Ckt 2 (115 kV) | Regional Reliability | 2025-05-15 | 2025-01-01 | 2024-12-13 | 2024 ITP | 1831097 | 2025 | 1831097 | 1901723 |  | Closed Out | 528027 | Road Runner 345 kV |  |  | Install a new 345/115 kV transformer at Roadrunner 115 kV substation and expand the 115 kV bus. | 345/115
220817 | 94584 | 159259 | SPS | NM | XFR - Road Runner 345/115 kV Ckt 2 | Roadrunner 345/115 kV Transformer Ckt 2 (345 kV) | Regional Reliability | 2025-05-15 | 2025-01-01 | 2024-12-13 | 2024 ITP | 1066419 | 2025 | 1066419 | 446984 |  | Closed Out | 528025 | Road Runner 115 kV |  |  | Install 345 kV terminal equipment to support 345/115 kV transformer at Roadrunner 345 kV substation with a summer emergency rating of 435 MVA. | 345/115
220778 | 94587 | 159263 | BEPC | ND | XFR - BEPC-Judson 345 kV 345/230 kV | XFR - Judson 345/230 kV second (230 kV) | Transmission Service | 2025-06-12 | 2024-06-01 | 2024-05-08 | SPP-2023-AG2 | 8300000 | 2024 | 8300000 | 8300000 |  | In Service | 659333 | JUDSON | 659334 |  | Install a second 345/230 kV transformer at the Judson 345/230 kV substation | 345/230
220808 | 94596 | 159285 | EKC | KS | Line - Lawrence Energy Center Unit 3 115 kV - Lawrence Hill 115 kV Rebuild | Lawrence Energy Center Unit 3 - Lawrence Hill 115 kV Ckt 1 Rebuild | Regional Reliability | 2027-06-01 | 2025-01-01 | 2024-12-13 | 2024 ITP | 2631541 | 2025 | 2697329.525 | 2902757 |  | Delay - Mitigation | 533248 | LAWRENCE ENERGY CENTER UNIT 3 115 KV | 533250 | LAWRENCE HILL 115 KV | Rebuild 0.5-mile 115 kV Ckt 1 line from Lawrence Energy Center Unit 3 115 kV substation to Lawrence Hill 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA. | 115
220808 | 94596 | 159286 | EKC | KS | Line - Lawrence Energy Center Unit 3 115 kV - Lawrence Hill 115 kV Rebuild | Lawrence Hill 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2027-06-01 | 2025-01-01 | 2024-12-13 | 2024 ITP | 88010 | 2025 | 90210.25 | 88010 |  | Delay - Mitigation | 533250 | LAWRENCE HILL 115 KV |  |  | Install any necessary terminal equipment at Lawrence Hill 115 kV substation for the line from Lawrence Hill 115 kV substation to Lawrence Energy Center Unit 3 115 kV substation with a summer emergency rating of 239 MVA. | 115
220808 | 94596 | 159289 | EKC | KS | Line - Lawrence Energy Center Unit 3 115 kV - Lawrence Hill 115 kV Rebuild | Lawrence Energy Center Unit 3 115 kV Ckt 1 Terminal Upgrade #2 | Regional Reliability | 2027-06-01 | 2025-01-01 | 2024-12-13 | 2024 ITP | 98186 | 2025 | 100640.65 | 98186 |  | Delay - Mitigation | 533248 | LAWRENCE ENERGY CENTER UNIT 3 115 KV |  |  | Install any necessary terminal equipment at Lawrence Energy Center Unit 3 115 kV substation for the line from Lawrence Energy Center Unit 3 115 kV substation to Lawrence Hill 115 kV substation with a summer emergency rating of 239 MVA. | 115
220808 | 94604 | 159305 | EKC | KS | Line - Butler 138 kV - Midian 138 kV Rebuild | Butler - Midian 138 kV Ckt 1 Rebuild | Economic | 2028-12-31 | 2028-01-01 | 2024-12-13 | 2024 ITP | 9164661 | 2025 | 9393777.525 | 9164661 |  | Delay - Mitigation | 532987 | BUTLER 138 KV | 532990 | MIDIAN 138 KV | Rebuild 3-mile Ckt 1 line from Butler 138 kV substation to Midian 138 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 286 MVA | 138
220810 | 94606 | 159308 | NPPD | NE | Line - Hoskins 115 kV - Stanton North 115 kV Rebuild | Hoskins - Stanton North 115 kV Ckt 1 Rebuild | Economic | 2027-06-01 | 2026-01-01 | 2024-12-13 | 2024 ITP | 4331860 | 2025 | 4440156.5 | 4331860 |  | Delay - Mitigation | 640228 | Hoskins | 640363 | Stanton North | Rebuild 9.9-mile 115 kV Ckt 1 line from Hoskins 115 kV substation to Stanton North 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of at least 239 MVA. | 115 |  | 9.9
220810 | 94606 | 159309 | NPPD | NE | Line - Hoskins 115 kV - Stanton North 115 kV Rebuild | Hoskins 115 kV Ckt 1 Terminal Upgrade | Economic | 2027-06-01 | 2026-01-01 | 2024-12-13 | 2024 ITP | 152252 | 2025 | 156058.3 | 152252 |  | Delay - Mitigation | 640228 | Hoskins |  |  | Install any necessary terminal equipment at Hoskins 115 kV substation for the line from Hoskins 115 kV substation to Stanton North 115 kV substation with a summer emergency rating of at least 239 MVA. | 115
220810 | 94606 | 159310 | NPPD | NE | Line - Hoskins 115 kV - Stanton North 115 kV Rebuild | Stanton North 115 kV Ckt 1 Terminal Upgrade | Economic | 2027-06-01 | 2026-01-01 | 2024-12-13 | 2024 ITP | 155752 | 2025 | 159645.8 | 155752 |  | Delay - Mitigation | 640363 | Stanton North |  |  | Install any necessary terminal equipment at Stanton North 115 kV substation for the line from Stanton North 115 kV substation to Hoskins 115 kV substation with a summer emergency rating of at least 239 MVA. | 115
220937 | 94615 | 159336 | AEP | OK | Line - Buffalo Flats 345 kV - Delaware 345 kV New Line | Buffalo Flats - Delaware 345 kV Ckt 1 New Line | Regional Reliability | 2029-05-01 | 2025-12-01 | 2025-09-18 | 2024 ITP | 113332569 | 2025 | 116165883.225 | 113332569 |  | Delay - Mitigation | 510380 | DELAWARE 345KV | 532782 |  | Build a 154.6 mile 345 kV Ckt 1 new line from Delaware 345 kV substation to Buffalo Flats 345 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA. | 345
220937 | 94615 | 159337 | AEP | OK | Line - Buffalo Flats 345 kV - Delaware 345 kV New Line | Delaware 345 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2029-05-01 | 2025-12-01 | 2025-09-18 | 2024 ITP | 11201155 | 2025 | 11481183.875 | 11201155 |  | Delay - Mitigation | 510380 | DELAWARE 345KV |  |  | Install any necessary terminal equipment at Delaware 345 kV substation to support a new line from Delaware 345 kV substation to Buffalo Flats 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220938 | 94615 | 159338 | EKC | KS | Line - Buffalo Flats 345 kV - Delaware 345 kV New Line | Buffalo 345 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2029-12-31 | 2025-12-01 | 2025-09-18 | 2024 ITP | 5698178 | 2025 | 5840632.45 | 3654198 |  | Delay - Mitigation | 532782 |  |  |  | Install any necessary terminal equipment at Buffalo Flats 345 kV substation to support a new line from Buffalo Flats 345 kV substation to Delaware 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220901 | 94618 | 159345 | EKC | KS | Line - Farber 138 kV - Sumner County No. 10 Belle Plain 138 kV Rebuild | Farber - Sumner County No. 10 Belle Plain 138 kV Ckt 1 Rebuild | Economic | 2029-06-01 | 2025-01-01 | 2025-04-24 | 2024 ITP | 19222238 | 2025 | 19702793.95 | 19222237 |  | NTC - Commitment Window | 533042 | FARBER 138 KV | 533063 | SUMNER COUNTY NO. 10 BELLE PLAIN 138 KV | Rebuild 10.3-mile 138 kV Ckt 1 line from Farber 138 kV substation to Sumner County No. 10 Belle Plain 138 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 286 MVA. | 138
220808 | 94625 | 159362 | EKC | KS | Line - Butler South 138 kV - Tallgrass 138 kV Rebuild #2 | Butler South - Tallgrass 138 kV Ckt 1 Rebuild #1 | Economic | 2029-06-01 | 2025-01-01 | 2024-12-13 | 2024 ITP | 13985366 | 2025 | 14335000.15 | 13985366 |  | Delay - Mitigation | 532989 | Butler 138kV | 532993 |  | Rebuild 9.9-mile Ckt 1 line from Butler South 138 kV substation to Tallgrass 138 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 286 MVA. | 138
220808 | 94625 | 159363 | EKC | KS | Line - Butler South 138 kV - Tallgrass 138 kV Rebuild #2 | Butler South 138 kV Ckt 1 Terminal Upgrade #2 | Economic | 2029-06-01 | 2025-01-01 | 2024-12-13 | 2024 ITP | 201595 | 2025 | 206634.875 | 201595 |  | Delay - Mitigation | 532989 | Butler 138kV |  |  | Install any necessary terminal equipment at Butler South 138 kV substation to support the line from Butler South 138 kV substation to Tallgrass 138 kV substation with a summer emergency rating of 286 MVA. | 138
220808 | 94625 | 159364 | EKC | KS | Line - Butler South 138 kV - Tallgrass 138 kV Rebuild #2 | Tallgrass 138 kV Ckt 1 Terminal Upgrade #2 | Economic | 2029-06-01 | 2025-01-01 | 2024-12-13 | 2024 ITP |  |  | 0 | 0 |  | Delay - Mitigation | 532993 |  |  |  | Install any necessary terminal equipment at Tallgrass 138 kV substation to support the line from Tallgrass 138 kV substation to Butler South 138 kV substation with a summer emergency rating of 286 MVA. | 138
220902 | 94626 | 159365 | OPPD | NE | Line - Sub 1209 161 kV - Sub 1250 161 kV Rebuild | Sub 1209 - Sub 1250 161 kV Ckt 2 Rebuild | Regional Reliability | 2027-08-20 | 2028-06-01 | 2025-04-24 | 2024 ITP | 28933550 | 2025 | 29656888.75 | 28933550 |  | On Schedule < 4 | 646209 | Sub 1209 | 646250 | Sub 1250 | Rebuild approximately 8-mile 161 kV Ckt 2 line from Sub 1209 161 kV substation to Sub 1250 161 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 558 MVA. | 161 |  | 8
220902 | 94626 | 159366 | OPPD | NE | Line - Sub 1209 161 kV - Sub 1250 161 kV Rebuild | Sub 1209 161 kV Ckt 2 Terminal Upgrade | Regional Reliability | 2027-08-20 | 2028-06-01 | 2025-04-24 | 2024 ITP | 373879 | 2025 | 383225.975 | 373879 |  | On Schedule < 4 | 646209 | Sub 1209 |  |  | Install any necessary terminal equipment at Sub 1209 161 kV substation for the line from Sub 1209 161 kV substation to Sub 1250 161 kV substation with a summer emergency rating of 558 MVA | 161
220902 | 94626 | 159367 | OPPD | NE | Line - Sub 1209 161 kV - Sub 1250 161 kV Rebuild | Sub 1250 161 kV Ckt 2 Terminal Upgrade | Regional Reliability | 2027-08-20 | 2028-06-01 | 2025-04-24 | 2024 ITP | 141570 | 2025 | 145109.25 | 141570 |  | On Schedule < 4 | 646250 | Sub 1250 |  |  | Install any necessary terminal equipment at Sub 1250 161 kV substation for the line from Sub 1250 161 kV substation to Sub 1209 161 kV substation with a summer emergency rating of 558 MVA. | 161
220813 | 94635 | 159373 | OPPD | NE | Line - Sub 1250 161 kV - Sub 1358 161 kV Rebuild | Sub 1250 - Sub 1358 161 kV Ckt 1 Rebuild | Regional Reliability | 2027-08-20 | 2028-06-01 | 2024-12-13 | 2024 ITP | 4065338 | 2025 | 4166971.45 | 4065338 |  | On Schedule < 4 | 646250 | Sub 1250 | 646358 |  | Rebuild approximately 5-mile 161 kV Ckt 1 line from Sub 1250 161 kV substation to Sub 1358 161 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 558 MVA. | 161 |  | 5
220813 | 94635 | 159374 | OPPD | NE | Line - Sub 1250 161 kV - Sub 1358 161 kV Rebuild | Sub 1250 161 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2027-08-20 | 2028-06-01 | 2024-12-13 | 2024 ITP | 141570 | 2025 | 145109.25 | 141570 |  | On Schedule < 4 | 646250 | Sub 1250 |  |  | Install any necessary terminal equipment at Sub 1250 161 kV substation for the line from Sub 1250 161 kV substation to Sub 1358 161 kV substation with a summer emergency rating of 558 MVA. | 161
220813 | 94635 | 159375 | OPPD | NE | Line - Sub 1250 161 kV - Sub 1358 161 kV Rebuild | Sub 1358 161 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2027-08-20 | 2028-06-01 | 2024-12-13 | 2024 ITP |  |  | 0 | 0 |  | On Schedule < 4 | 646358 |  |  |  | Install any necessary terminal equipment at Sub 1358 161 kV substation for the line from Sub 1358 161 kV substation to Sub 1250 161 kV substation with a summer emergency rating of 558 MVA. | 161
220813 | 94634 | 159379 | OPPD | NE | Line - Sub 1209 161 kV - Sub 1358 161 kV Rebuild | Sub 1209 - Sub 1358 161 kV Ckt 1 Rebuild | Regional Reliability | 2027-03-16 | 2028-06-01 | 2024-12-13 | 2024 ITP | 3664337 | 2025 | 3755945.425 | 3664337 |  | On Schedule < 4 | 646209 | Sub 1209 | 646358 |  | Rebuild approximately 5-mile 161 kV Ckt 1 line from Sub 1209 161 kV substation to Sub 1358 161 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 558 MVA. | 161 |  | 5
220813 | 94634 | 159380 | OPPD | NE | Line - Sub 1209 161 kV - Sub 1358 161 kV Rebuild | Sub 1209 161 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2027-03-16 | 2028-06-01 | 2024-12-13 | 2024 ITP |  |  | 0 | 0 |  | On Schedule < 4 | 646209 | Sub 1209 |  |  | : Install any necessary terminal equipment at Sub 1209 161 kV substation for the line from Sub 1209 161 kV substation to Sub 1358 161 kV substation with a summer emergency rating of 558 MVA. | 161
220813 | 94634 | 159381 | OPPD | NE | Line - Sub 1209 161 kV - Sub 1358 161 kV Rebuild | Sub 1358 161 kV Ckt 1 Terminal Upgrade #1 | Regional Reliability | 2027-03-16 | 2028-06-01 | 2024-12-13 | 2024 ITP |  |  | 0 |  |  | On Schedule < 4 | 646358 |  |  |  | Install any necessary terminal equipment at Sub 1358 161 kV substation for the line from Sub 1358 161 kV substation to Sub 1209 161 kV substation with a summer emergency rating of 558 MVA. | 161
220880 | 94630 | 159382 | EDE | AR | Line - N Reed Spring 161 kV - S Reed Spring 161 kV Rebuild | N Reed Spring - S Reed Spring 161 kV Ckt 1 Rebuild | Economic | 2029-11-01 | 2025-12-01 | 2025-01-23 | 2024 ITP | 2543371 | 2025 | 2606955.275 | 2543371 |  | Delay - Mitigation |  |  |  |  | Rebuild 1.5 mile Ckt 1 line from N Reed Spring 161 kV substation to S Reed Spring 161 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 557 MVA. | 161 |  | 1.5
220880 | 94630 | 159383 | EDE | MO | Line - N Reed Spring 161 kV - S Reed Spring 161 kV Rebuild | N Reed Spring 161 kV Ckt 1 Terminal Upgrade | Economic | 2029-11-01 | 2025-12-01 | 2025-01-23 | 2024 ITP | 843321 | 2025 | 864404.025 | 843321 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at N Reeds Spring 161 kV Ckt 1 substation for the line from N Reeds Spring 161 kV Ckt 1 substation to S Reeds Spring 161 kV Ckt 1 substation with a summer emergency rating of 557 MVA. | 161
220880 | 94630 | 159384 | EDE | MO | Line - N Reed Spring 161 kV - S Reed Spring 161 kV Rebuild | S Reed Spring 161 kV Ckt 1 Terminal Upgrade | Economic | 2028-11-01 | 2025-12-01 | 2025-01-23 | 2024 ITP | 136473 | 2025 | 139884.825 | 136473 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at S Reeds Spring 161 kV Ckt 1 substation for the line from S Reeds Spring 161 kV Ckt substation to N Reeds Spring 161 kV Ckt 1 substation with a summer emergency rating of 557 MVA. | 161
220880 | 94910 | 159385 | EDE | MO | Line - Branson Northwest 161 kV - Branson North 161 kV - Reed Spring Rebuild | Reed Spring - Branson Northwest 161 kV Ckt 1 Rebuild | Economic | 2030-03-01 | 2024-11-12 | 2025-01-23 | 2024 ITP | 13974975 | 2025 | 14324349.375 | 13974975 |  | Delay - Mitigation |  |  |  |  | Rebuild 8.3 mile Ckt 1 line from Reed Spring 161 kV substation to Branson Northwest 161 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 557 MVA. | 161 | 8.3 | 8.3
220880 | 94910 | 159387 | EDE | MO | Line - Branson Northwest 161 kV - Branson North 161 kV - Reed Spring Rebuild | Branson Northwest 161 kV Ckt 1 Terminal Upgrade | Economic | 2030-03-01 | 2024-11-12 | 2025-01-23 | 2024 ITP | 386943 | 2025 | 396616.575 | 386943 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at Branson Northwest 161 kV Ckt1 substation to support the line from Branson Northwest 161 kV Ckt1 substation to Reed Spring 161 kV Ckt1 substation with a summer emergency rating of 557 MVA. | 161
220817 | 94640 | 159391 | SPS | TX | Line - Frankford 115 kV - Quaker 115 kV Rebuild | Frankford - Quaker 115 kV Ckt 1 Rebuild | Regional Reliability | 2025-03-03 | 2025-06-01 | 2024-12-13 | 2024 ITP | 6100000 | 2025 | 6100000 | 5464908 |  | Complete | 526199 | South Plains REC-Frankford Sub 115 kV | 526243 | South Plains REC-Quaker 115 kV | Rebuild 2-mile Ckt 1 line from Frankford 115 kV substation to Quaker 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA | 115
220817 | 94640 | 159392 | SPS | TX | Line - Frankford 115 kV - Quaker 115 kV Rebuild | Frankford 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2025-06-23 | 2025-06-01 | 2024-12-13 | 2024 ITP |  |  | 0 | 55612 |  | Complete | 526199 | South Plains REC-Frankford Sub 115 kV |  |  | Install any necessary terminal equipment at Frankford 115 kV substation for the line from Frankford 115 kV substation to Quaker 115 kV substation to meet a summer emergency rating of 239 MVA. | 115
220817 | 94640 | 159393 | SPS | TX | Line - Frankford 115 kV - Quaker 115 kV Rebuild | Quaker 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2025-05-05 | 2025-06-01 | 2024-12-13 | 2024 ITP |  |  | 0 | 65549 |  | Closed Out | 526243 | South Plains REC-Quaker 115 kV |  |  | Install any necessary terminal equipment at Quaker 115 kV substation for the line from Quaker 115 kV substation to Frankford 115 kV substation to meet a summer emergency rating of 239 MVA. | 115
220808 | 94643 | 159412 | EKC | KS | Line - Weaver 138 kV - Tallgrass 138 kV Rebuild #1 | Weaver - Tallgrass 138 kV Ckt 1 Rebuild #1 | Economic | 2029-12-31 | 2025-01-01 | 2024-12-13 | 2024 ITP | 13006327 | 2025 | 13331485.175 | 13006327 |  | Delay - Mitigation | 532991 | WEAVER 138 KV | 532993 |  | Rebuild 9.8 mile Ckt 1 line from Weaver 138 kV substation to Tallgrass 138 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 286 MVA. | 138
220808 | 94643 | 159413 | EKC | KS | Line - Weaver 138 kV - Tallgrass 138 kV Rebuild #1 | Weaver 138 kV Ckt 1 Terminal Upgrade #2 | Economic | 2029-12-31 | 2025-06-01 | 2024-12-13 | 2024 ITP | 203046 | 2025 | 208122.15 | 203046 |  | Delay - Mitigation | 532991 | WEAVER 138 KV |  |  | Install any necessary terminal equipment at Weaver 138 kV substation for the line from Weaver 138 kV substation to Tallgrass 138 kV substation with a summer emergency rating of 239 MVA. | 138
220808 | 94643 | 159414 | EKC | KS | Line - Weaver 138 kV - Tallgrass 138 kV Rebuild #1 | Weaver - Tallgrass 138 kV Ckt 1 Rebuild #2 | Economic | 2029-12-31 | 2025-01-01 | 2024-12-13 | 2024 ITP |  |  | 0 | 0 |  | Delay - Mitigation | 532991 | WEAVER 138 KV | 532993 |  | Install any necessary terminal equipment at Tallgrass 138 kV substation for the line from Tallgrass 138 kV substation to Weaver 138 kV substation with a summer emergency rating of 239 MVA. | 138
220903 | 94647 | 159430 | EDE | MO | Line - Aurora 161 kV - Reeds Spring 161 kV Rebuild | Aurora - Reeds Spring 161 kV Ckt 1 Rebuild | Economic | 2029-09-01 | 2024-11-12 | 2025-05-01 | 2024 ITP | 40112705 | 2025 | 41115522.625 |  | 40112705 | Delay - Mitigation | 547468 | SUB 124 - AURORA H.T. | 547473 | SUB 295 - REEDS SPRING | Rebuild 23.7 mile Ckt 1 line from Aurora 161 kV substation to Reeds Spring 161 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 557 MVA. | 161
220903 | 94647 | 159431 | EDE | MO | Line - Aurora 161 kV - Reeds Spring 161 kV Rebuild | Aurora 161 kV Ckt 1 Terminal Upgrade | Economic | 2029-09-01 | 2024-11-12 | 2025-05-01 | 2024 ITP | 421046 | 2025 | 431572.15 | 421046 |  | Delay - Mitigation | 547468 | SUB 124 - AURORA H.T. | 547468 | SUB 124 - AURORA H.T. | Install any necessary terminal equipment at Aurora 161 kV Ckt1 substation to support the line from Aurora 161 kV Ck1 substation to Reeds Spring 161 kV Ckt1 substation with a summer emergency rating of 557 MVA. | 161
220903 | 94647 | 159432 | EDE | MO | Line - Aurora 161 kV - Reeds Spring 161 kV Rebuild | Reeds Spring 161 kV Ckt 1 Terminal Upgrade #1 | Economic | 2029-09-01 | 2025-12-01 | 2025-05-01 | 2024 ITP | 135466 | 2025 | 138852.65 | 135466 |  | Delay - Mitigation | 547473 | SUB 295 - REEDS SPRING | 547473 | SUB 295 - REEDS SPRING | Install any necessary terminal equipment at Reeds Spring 161 kV Ckt1 substation to support the line from Reeds Spring 161 kV Ckt1 substation to Aurora 161 kV Ckt1 substation with a summer emergency rating of 557 MVA. | 161
220880 | 94648 | 159438 | EDE | MO | Line - Ozark Dam 161 kV - Branson North 161 kV Rebuild | Branson North - Ozark Dam 161 kV Ckt 1 Rebuild | Economic | 2030-09-01 | 2024-11-12 | 2025-01-23 | 2024 ITP | 12421543 | 2025 | 12732081.575 | 12421543 |  | Delay - Mitigation | 547474 | SUB 312 - POWERSITE | 547475 | SUB 331 - BRANSON NORTH | Rebuild 7.1 mile Ckt 1 line from Ozark Dam 161 kV Ckt1 substation to Branson North 161 kV Ckt1 substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 557 MVA. | 161 |  | 7.1
220880 | 94648 | 159439 | EDE | MO | Line - Ozark Dam 161 kV - Branson North 161 kV Rebuild | Ozark Dam 161 kV Ckt 1 Terminal Upgrade | Economic | 2028-03-01 | 2024-11-12 | 2025-01-23 | 2024 ITP | 267221 | 2025 | 273901.525 | 267221 |  | Delay - Mitigation | 547474 | SUB 312 - POWERSITE | 547475 | SUB 331 - BRANSON NORTH | Install any necessary terminal equipment at Ozark Dam 161 kV Ckt1 substation to support the line from Ozark Dam 161 kV Ckt1 substation to Branson North 161 kV Ckt1 substation with a summer emergency rating of 557 MVA. | 161
220880 | 94648 | 159440 | EDE | MO | Line - Ozark Dam 161 kV - Branson North 161 kV Rebuild | Branson North 161 kV Ckt 1 Terminal Upgrade | Economic | 2030-09-01 | 2024-11-12 | 2025-01-23 | 2024 ITP | 683669 | 2025 | 700760.725 | 683669 |  | Delay - Mitigation | 547475 | SUB 331 - BRANSON NORTH | 547474 | SUB 312 - POWERSITE | Install any necessary terminal equipment at Branson North 161 kV Ckt1 substation to support the line from Branson North 161 kV Ckt1 substation to Ozark Dam 161 kV Ckt1 substation with a summer emergency rating of 557 MVA. | 161
220808 | 94816 | 159449 | EKC | KS | Line - Chisholm 138 kV - Maize 138 kV - Evan Energy Center North 138 KV Ct1 Rebuild | Evans Energy Center North - Maize 138 kV Ckt 1 Rebuild | Economic | 2028-12-31 | 2032-01-01 | 2024-12-13 | 2024 ITP | 4140875 | 2025 | 4244396.875 | 3907935 |  | On Schedule < 4 | 533040 | EVANS ENERGY CENTER NORTH 138 KV | 533054 | MAIZE | Rebuild 4.9-mile Ckt 1 line from Evans Energy Center North 138 kV substation to Maize 138 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 478 MVA. | 138
220811 | 94667 | 159464 | MRES | SD | Line - 15th Ave - Watertown 115 kV Rebuild | Watertown - 15th Ave 115 kV Ckt 1 Rebuild | Regional Reliability | 2031-06-01 | 2031-06-01 | 2024-12-13 | 2024 ITP | 1779000 | 2025 | 1823475 | 1779000 |  | On Schedule > 4 | 652531 | WATERTOWN | 658089 |  | Rebuild 1.4-mile Ckt 1 line from 15th Ave 115 kV substation to Watertown 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA. | 115 |  | 1.4
220811 | 94667 | 159465 | MRES | SD | Line - 15th Ave - Watertown 115 kV Rebuild | Watertown 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2031-06-01 | 2031-06-01 | 2024-12-13 | 2024 ITP |  |  | 0 | 0 |  | On Schedule > 4 | 652531 | WATERTOWN |  |  | Install any necessary terminal equipment at Watertown 115 kV substation to support the line from Watertown 115 kV substation to 15th Ave 115 kV substation with a summer emergency rating of 239 MVA. | 115
220811 | 94667 | 159466 | MRES | SD | Line - 15th Ave - Watertown 115 kV Rebuild | 15th Ave 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2031-06-01 | 2031-06-01 | 2024-12-13 | 2024 ITP |  |  | 0 | 0 |  | On Schedule > 4 | 658089 |  |  |  | Install any necessary terminal equipment at 15th Ave 115 kV substation to support the line from 15th Ave 115 kV substation to Watertown 115 kV substation with a summer emergency rating of 239 MVA. | 115
220817 | 94662 | 159467 | SPS | TX | Sub - Lubbock South 115 kV - Lubbock East 115 kV Terminal Upgrades | Lubbock South 115 kV Terminal Upgrade #1 | Economic | 2027-05-15 | 2025-06-01 | 2024-12-13 | 2024 ITP | 621000 | 2025 | 636525 | 622325 |  | Delay - Mitigation | 525480 | Plant X Station 115 kV | 526268 | Lubbock South Interchange 115 kV | Install any necessary terminal equipment at Lubbock South 115 kV substation for the line from Lubbock South 115 kV substation to Lubbock East 115 kV substation to meet a summer emergency rating of 239 MVA. | 115
220817 | 94662 | 159468 | SPS | TX | Sub - Lubbock South 115 kV - Lubbock East 115 kV Terminal Upgrades | Lubbock East 115 kV Terminal Upgrade | Economic | 2027-05-15 | 2025-06-01 | 2024-12-13 | 2024 ITP | 621000 | 2025 | 636525 | 610329 |  | Delay - Mitigation | 526298 | Lubbock East Interchange 115 kV | 526268 | Lubbock South Interchange 115 kV | Install any necessary terminal equipment at Lubbock East 115 kV substation for the line from Lubbock East 115 kV substation to Lubbock South 115 kV substation to meet a summer emergency rating of 239 MVA. | 115
220926 | 94673 | 159471 | BEPC | ND | Multi - Springbrook - Twelve Mile 345 New Line | Twelve Mile 345/115 kV Transformer Ckt 1 (115 kV) | Regional Reliability | 2032-03-31 | 2032-04-01 | 2025-08-08 | 2024 ITP | 12233925 | 2025 | 12539773.125 | 12233925 |  | On Schedule > 4 |  |  |  |  | Install new 345/115 kV transformer at Twelve Mile 345 kV substation | 345/115
220926 | 94673 | 159472 | BEPC | ND | Multi - Springbrook - Twelve Mile 345 New Line | Twelve Mile 345 kV Terminal Upgrade (345 kV) | Regional Reliability | 2032-03-31 | 2032-04-01 | 2025-08-08 | 2024 ITP | 2394416 | 2025 | 2454276.4 | 2394416 |  | On Schedule > 4 |  |  |  |  | Install 345 kV terminal equipment to support 345/115 kV transformer at Twelve Mile 345 kV substation | 345/115
220926 | 94673 | 159473 | BEPC | ND | Multi - Springbrook - Twelve Mile 345 New Line | Twelve Mile 345 kV New Substation | Regional Reliability | 2032-03-31 | 2032-04-01 | 2025-08-08 | 2024 ITP | 16533147 | 2025 | 16946475.675 | 16533147 |  | On Schedule > 4 |  |  |  |  | Install a new 345 kV Substation at or near the existing Twelve Mile 115 kV substation | 345
220926 | 94673 | 159474 | BEPC | ND | Multi - Springbrook - Twelve Mile 345 New Line | Springbrook - Twelve Mile 345 kV Ckt 1 New Line | Regional Reliability | 2032-03-31 | 2032-04-01 | 2025-08-08 | 2024 ITP | 40000000 | 2025 | 41000000 | 40000000 |  | On Schedule > 4 |  |  |  |  | Build 8.4-mile 345 kV Ckt 1 line from Springbrook 345 kV substation to a new Twelve Mile 345 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA. | 345 | 8.4
220926 | 94673 | 159475 | BEPC | ND | Multi - Springbrook - Twelve Mile 345 New Line | Springbrook 345 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2032-03-31 | 2032-04-01 | 2025-08-08 | 2024 ITP | 4780649 | 2025 | 4900165.225 | 4780649 |  | On Schedule > 4 |  |  |  |  | Install any necessary terminal equipment at Springbrook 345 kV substation to support a new line from the new Twelve Mile 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220926 | 94673 | 159476 | BEPC | ND | Multi - Springbrook - Twelve Mile 345 New Line | Twelve Mile 345 kV Ckt 1 Terminal Additon | Regional Reliability | 2032-03-31 | 2032-04-01 | 2025-08-08 | 2024 ITP | 3550253 | 2025 | 3639009.325 | 3550253 |  | On Schedule > 4 |  |  |  |  | Install any necessary terminal equipment at Twelve Mile 345 kV substation to support a new line from the Spring Brook 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220863 | 94669 | 159497 | BEPC | ND | Multi - Robinson Lake 115 kV - Crane Creek 115 kV New Line | Crane Creek 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2031-06-01 | 2028-01-01 | 2024-12-13 | 2024 ITP |  |  | 0 | 488934 |  | Delay - Mitigation Window |  |  |  |  | Install any necessary terminal equipment at Crane Creek 115 kV substation to support a new line to from Crane Creek 115 kV substation to Robinson Lake 115 kV substation with a summer emergency rating of 239 MVA. | 115
220863 | 94669 | 159499 | BEPC | ND | Multi - Robinson Lake 115 kV - Crane Creek 115 kV New Line | Crane Creek 345/115 kV Transformer Ckt 3 (115 kV) | Regional Reliability | 2031-06-01 | 2028-01-01 | 2024-12-13 | 2024 ITP |  |  | 0 | 11041626 |  | Delay - Mitigation Window |  |  |  |  | Install new 345/115 transformer at Crane Creek 115 kV substation | 345/115
220863 | 94669 | 159500 | BEPC | ND | Multi - Robinson Lake 115 kV - Crane Creek 115 kV New Line | Crane Creek 345 kV Terminal Equipment r Ckt 3 (345 kV) | Regional Reliability | 2031-06-01 | 2028-01-01 | 2024-12-13 | 2024 ITP |  |  | 0 | 8795633 |  | Delay - Mitigation Window |  |  |  |  | Install 345 kV terminal equipment to support 345/115 transformer at Crane Creek 345 kV substation | 345/115
220890 | 94711 | 159565 | SPS | TX | Line - Kingsmill 115 kV - Grapevine 115 kV New Line | Kingsmill - Grapevine 115 kV Ckt 1 New Line | Regional Reliability | 2027-12-15 | 2025-06-01 | 2025-02-12 | 2024 ITP | 10602558 | 2025 | 10867621.95 | 10925685 |  | Delay - Mitigation | 523712 | Kingsmill Interchange 115 kV | 523770 | Grapevine Interchange 115 kV | Build 10.7-mile 115 kV Ckt 1 line from Kingsmill 115 kV substation to Grapevine 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 303 MVA. | 115
220890 | 94711 | 159566 | SPS | TX | Line - Kingsmill 115 kV - Grapevine 115 kV New Line | Kingsmill 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2027-12-15 | 2025-06-01 | 2025-02-12 | 2024 ITP | 3425298 | 2025 | 3510930.45 | 3021056 |  | Delay - Mitigation | 523712 | Kingsmill Interchange 115 kV |  |  | Install any necessary terminal equipment at Kingsmill 115 kV substation to support a new line from Kingsmill 115 kV substation to Grapevine 115 kV substation with a summer emergency rating of 303 MVA. | 115
220890 | 94711 | 159567 | SPS | TX | Line - Kingsmill 115 kV - Grapevine 115 kV New Line | Grapevine 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2027-12-15 | 2025-06-01 | 2025-02-12 | 2024 ITP | 13695573 | 2025 | 14037962.325 | 14348531 |  | Delay - Mitigation | 523770 | Grapevine Interchange 115 kV |  |  | Install any necessary terminal equipment at Grapevine 115 kV substation to support a new line from Grapevine 115 kV substation to Kingsmill 115 kV substation with a summer emergency rating of 303 MVA. | 115
220805 | 94716 | 159583 | CBPC | IA | Line - Spencer 69 kV - Wisdom 69 kV Rebuild | Spencer - Wisdom 69 kV Ckt 1 Rebuild (CBPC) | Regional Reliability | 2025-12-01 | 2025-12-01 | 2024-12-13 | 2024 ITP | 171500 | 2024 | 175787.5 | 1200000 |  | On Schedule < 4 | 652581 | Spencer | 656573 | 6 Mile Road 115 kV Bus (Sioux Falls area) | Rebuild 0.5-mile 69 kV Ckt 1 line from Spencer 69 kV substation to Wisdom 69 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 114 MVA. | 69 |  | 0.5
220815 | 94716 | 159584 | WAPA | IA | Line - Spencer 69 kV - Wisdom 69 kV Rebuild | Spencer 69 kV Ckt 2 Terminal Upgrade | Regional Reliability | 2026-07-31 | 2025-12-01 | 2024-12-13 | 2024 ITP | 89039 | 2025 | 91264.975 | 89039 |  | Delay - Mitigation | 652581 | Spencer |  |  | Install any necessary terminal equipment at Spencer 69 kV substation to support the line from Spencer 69 kV substation to Wisdom 69 kV substation with a summer emergency rating of 114 MVA. | 69
220815 | 94719 | 159593 | WAPA | ND | Line - Ren 115 kV - Williston 115 kV Rebuild | Williston 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2027-09-30 | 2028-05-12 | 2024-12-13 | 2024 ITP | 416683 | 2025 | 427100.075 | 450928 |  | On Schedule < 4 | 652421 | WILISTON |  |  | Install any necessary terminal equipment at Williston 115 kV substation for the line from Williston 115 kV substation to Ren 115 kV substation with a summer emergency rating of 239 MVA. | 115
220905 | 94723 | 169628 | BEPC | ND | Multi - Logan 345 kV - Leland Olds 345 kV Voltage Conv and Logan 345 kV - Finstad 345 kV New Line | Logan - Leland Olds 345 kV Ckt 1 Voltage Conversion | Regional Reliability | 2032-11-30 | 2032-12-01 | 2025-05-06 | 2024 ITP | 106781208 | 2025 | 109450738.2 | 106781208 |  | NTC - Commitment Window |  |  |  |  | Convert 65-mile 230 kV Ckt 1 line from Logan 345 kV substation to Leland Olds 345 kV substation to 345 kV and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA.
220905 | 94723 | 169632 | BEPC | ND | Multi - Logan 345 kV - Leland Olds 345 kV Voltage Conv and Logan 345 kV - Finstad 345 kV New Line | Logan 345 kV Ckt 1 Terminal Addition | Regional Reliability | 2032-11-30 | 2032-12-01 | 2025-05-06 | 2024 ITP | 3829372 | 2025 | 3925106.3 | 3829372 |  | NTC - Commitment Window |  |  |  |  | Install any necessary terminal equipment at the new Logan 345 kV substation for the addition of the line from Leland Olds 345 kV substation for the voltage conversion from 230 kV with a summer emergency rating of 1792 MVA. | 345
220905 | 94723 | 169633 | BEPC | ND | Multi - Logan 345 kV - Leland Olds 345 kV Voltage Conv and Logan 345 kV - Finstad 345 kV New Line | Leland Olds 345 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2032-11-30 | 2032-12-01 | 2025-05-06 | 2024 ITP | 7973419 | 2025 | 8172754.475 | 7973419 |  | NTC - Commitment Window | 659105 | LELAND OLDS |  |  | Install any necessary terminal equipment at Leland Olds 345 kV substation for the line from Leland Olds 345 kV substation to Logan 345 kV substation for the voltage conversion from 230 kV with a summer emergency rating of 1792 MVA. | 345
220905 | 94723 | 169634 | BEPC | ND | Multi - Logan 345 kV - Leland Olds 345 kV Voltage Conv and Logan 345 kV - Finstad 345 kV New Line | Logan - Crane Creek 345 kV Ckt 1 New Line | Regional Reliability | 2032-11-30 | 2032-12-01 | 2025-05-06 | 2024 ITP | 145299619 | 2025 | 148932109.475 | 145299619 |  | NTC - Commitment Window |  |  | 659355 | Keystone Pump Site 18 - Philip | Build a new 53-mile 345 kV Ckt 1 line from Logan 345 kV substation to Finstad 345 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA. | 345 | 53
220905 | 94723 | 169635 | BEPC | ND | Multi - Logan 345 kV - Leland Olds 345 kV Voltage Conv and Logan 345 kV - Finstad 345 kV New Line | Logan 345 kV Ckt 1 Terminal Upgrade #1 | Regional Reliability | 2032-11-30 | 2032-12-01 | 2025-05-06 | 2024 ITP | 3846328 | 2025 | 3942486.2 | 3846328 |  | NTC - Commitment Window |  |  |  |  | Install any necessary terminal equipment at Logan 345 kV substation for the line from Logan 345 kV substation to Crane Creek 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220905 | 94723 | 169636 | BEPC | ND | Multi - Logan 345 kV - Leland Olds 345 kV Voltage Conv and Logan 345 kV - Finstad 345 kV New Line | Crane Creek 345 kV Terminal Addition | Regional Reliability | 2032-11-30 | 2032-12-01 | 2025-05-06 | 2024 ITP | 9235041 | 2025 | 9465917.025 | 9235041 |  | NTC - Commitment Window | 659355 | Keystone Pump Site 18 - Philip |  |  | Install any necessary terminal equipment at the Crane Creek 345 kV substation for the addition of the line from the Logan 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220905 | 94723 | 169637 | BEPC | ND | Multi - Logan 345 kV - Leland Olds 345 kV Voltage Conv and Logan 345 kV - Finstad 345 kV New Line | Logan 345 kV New Substation | Regional Reliability | 2032-11-30 | 2032-12-01 | 2025-05-06 | 2024 ITP | 15293911 | 2025 | 15676258.775 | 15293911 |  | NTC - Commitment Window |  |  |  |  | : Install a new 345 kV substation at or near Logan. | 345
220905 | 94723 | 169638 | BEPC | ND | Multi - Logan 345 kV - Leland Olds 345 kV Voltage Conv and Logan 345 kV - Finstad 345 kV New Line | Logan 345/230 kV Transformer Ckt 1 (230 kV) | Regional Reliability | 2032-11-30 | 2032-12-01 | 2025-05-06 | 2024 ITP | 16427065 | 2025 | 16837741.625 | 16427065 |  | NTC - Commitment Window |  |  |  |  | Install new 345/230 transformer Ckt 1 at the new Logan 345 kV substation | 345/230
220905 | 94723 | 169639 | BEPC | ND | Multi - Logan 345 kV - Leland Olds 345 kV Voltage Conv and Logan 345 kV - Finstad 345 kV New Line | Logan 345 kV Terminal Equipment Ckt 1 (345 kV) | Regional Reliability | 2032-11-30 | 2032-12-01 | 2025-05-06 | 2024 ITP | 2419081 | 2025 | 2479558.025 | 2419081 |  | NTC - Commitment Window | 659108 | LOGAN |  |  | Install 345 kV terminal equipment to support 345/230 Ckt 1 transformer at the new Logan 345 kV substation | 345/230
220905 | 94723 | 169640 | BEPC | ND | Multi - Logan 345 kV - Leland Olds 345 kV Voltage Conv and Logan 345 kV - Finstad 345 kV New Line | Logan 345/230 kV Transformer Ckt 2 (230 kV) #1 | Regional Reliability | 2032-11-30 | 2032-12-01 | 2025-05-06 | 2024 ITP | 16632004 | 2025 | 17047804.1 | 16632004 |  | NTC - Commitment Window |  |  |  |  | Install new 345/230 Ckt 2 transformer at the new Logan 345 kV substation | 345/230
220905 | 94723 | 169641 | BEPC | ND | Multi - Logan 345 kV - Leland Olds 345 kV Voltage Conv and Logan 345 kV - Finstad 345 kV New Line | Logan 345 kV Terminal Equipment Ckt 2 (345 kV) #1 | Regional Reliability | 2032-11-30 | 2032-12-01 | 2025-05-06 | 2024 ITP | 2419081 | 2025 | 2479558.025 | 2419081 |  | NTC - Commitment Window | 659108 | LOGAN |  |  | Install 345 kV terminal equipment to support 345/230 Ckt 2 transformer at the new Logan 345 kV substation | 345/230
220948 | 94721 | 169649 | EDE | MO | Multi - North Branson 345 kV - Monett 345 kV New Line | North Branson - Monett 345 kV Ckt 1 New Line | Regional Reliability |  | 2025-12-01 | 2025-11-04 | 2024 ITP | 213682884 | 2025 | 219024956.1 | 213682884 |  | NTC - Commitment Window |  |  |  |  | Build a new 50.4 mile 345 kV Ckt 1 line from Branson NW 345 kV substation to Monett 345 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA. | 345 | 50.4
220948 | 94721 | 169650 | EDE | MO | Multi - North Branson 345 kV - Monett 345 kV New Line | North Branson 345 kV Ckt 1 Terminal Upgrade #1 | Regional Reliability |  | 2025-12-01 | 2025-11-04 | 2024 ITP | 2354102 | 2025 | 2412954.55 | 2354102 |  | NTC - Commitment Window |  |  |  |  | Install any necessary equipment at North Branson 345 kV substation for the line from North Branson 345 kV substation to Monett 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220948 | 94721 | 169651 | EDE | MO | Multi - North Branson 345 kV - Monett 345 kV New Line | Monett Tap 345 kV Ckt 1 Terminal Upgrade | Regional Reliability |  | 2025-12-01 | 2025-11-04 | 2024 ITP | 3615480 | 2025 | 3705867 | 3615480 |  | NTC - Commitment Window |  |  |  |  | Install any necessary terminal equipment at Monett 345 kV substation for the line from Monett 345 kV substation to North Branson 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220812 | 94729 | 169664 | OGE | OK | Sub - Tinker 138 kV Breaker 121 & 122 | Tinker 138kV Breaker 121 Replacement | Regional Reliability | 2025-10-31 | 2025-06-01 | 2024-12-13 | 2024 ITP | 165000 | 2025 | 165000 | 225000 |  | Complete |  |  |  |  | Replace Breaker at TINKER - 121 138 kV with 40kA Breaker
220812 | 94729 | 169665 | OGE | OK | Sub - Tinker 138 kV Breaker 121 & 122 | Tinker 138kV Breaker 122 Replacement | Regional Reliability | 2025-10-31 | 2025-06-01 | 2024-12-13 | 2024 ITP | 165000 | 2025 | 165000 | 225000 |  | Complete |  |  |  |  | Replace Breaker at TINKER - 122 138 kV with 40kA Breaker
220904 | 94737 | 169675 | EREC | SD | Multi - Hanson County 115 kV System Reconfig | Mount Vernon - Mitchell 69 kV Ckt 1 New Line | Regional Reliability | 2025-05-15 | 2025-06-01 | 2025-06-19 | 2024 ITP | 2472000 | 2025 | 2472000 | 2472000 |  | NTC - Commitment Window |  |  |  |  | Build a new 18.4-mile 69 kV Ckt 1 line from Mount Vernon to Mitchell and upgrade any necessary terminal equipment to achieve a summer emergency rating of 84 MVA. | 69
220904 | 94737 | 169676 | EREC | SD | Multi - Hanson County 115 kV System Reconfig | Mitchell 69 kV New Substation | Regional Reliability | 2025-07-01 | 2025-06-01 | 2025-06-19 | 2024 ITP | 3947000 | 2025 | 3947000 | 3947000 |  | NTC - Commitment Window |  |  |  |  | Install 69 kV new substation at Mitchell
220904 | 94737 | 169677 | EREC | SD | Multi - Hanson County 115 kV System Reconfig | Letcher - Plano 115 kV Ckt 1 New Line | Regional Reliability | 2026-03-06 | 2025-06-01 | 2025-06-19 | 2024 ITP | 2795000 | 2025 | 2864875 | 2795000 |  | NTC - Commitment Window |  |  |  |  | Build a new 6.2-mile 115 kV Ckt 1 line from Letcher 115 kV substation to Plano 115 kV motor-operated switch and upgrade any necessary terminal equipment to achieve a summer emergency rating of 193 MVA. | 115
220904 | 94737 | 169678 | EREC | SD | Multi - Hanson County 115 kV System Reconfig | Letcher 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2025-12-12 | 2025-06-01 | 2025-06-19 | 2024 ITP | 1936000 | 2025 | 1936000 | 1936000 |  | NTC - Commitment Window |  |  |  |  | Install any necessary terminal equipment at Letcher 115 kV substation for the line from Letcher 115 kV substation to Plano 115 kV substation with a summer emergency rating of 193 MVA.
220904 | 94737 | 169686 | EREC | SD | Multi - Hanson County 115 kV System Reconfig | Mitchell - Hanson County 69 kV Ckt 1 New Line | Regional Reliability | 2025-11-03 | 2025-06-01 | 2025-06-19 | 2024 ITP | 4993000 | 2025 | 4993000 | 4993000 |  | NTC - Commitment Window |  |  |  |  | Build a new 18.3-mile 69 kV Ckt 1 line from Mitchell 69 kV substation to Hanson County 69 kV substation with a summer emergency rating of 84 MVA. | 69
220904 | 94737 | 169692 | EREC | SD | Multi - Hanson County 115 kV System Reconfig | Plano - Hanson County 115 kV Ckt 1 New Line | Regional Reliability | 2025-11-03 | 2025-06-01 | 2025-06-19 | 2024 ITP | 8017000 | 2025 | 8017000 | 8017000 |  | NTC - Commitment Window |  |  |  |  | Build a new 18.6-mile 115 kV Ckt 1 line from Plano 115 kV substation to Hanson County 115 kV substation with a summer emergency rating of 139 MVA. | 115
220904 | 94737 | 169694 | EREC | SD | Multi - Hanson County 115 kV System Reconfig | Plano 115 kV New Motor Operated Switch (MOS) | Regional Reliability | 2025-08-01 | 2025-06-01 | 2025-06-19 | 2024 ITP | 170000 | 2025 | 170000 | 170000 |  | NTC - Commitment Window |  |  |  |  | Install new three-way motor-operated switch and any necessary terminal equipment at Plano 115 kV MOS for the lines from Plano 115 kV MOS to Letcher 115 kV substation and from Plano 115 kV MOS to Hanson County 115 kV substation with a summer emergency rating of 193 MVA.
220904 | 94737 | 169695 | EREC | SD | Multi - Hanson County 115 kV System Reconfig | Letcher-Miner County 115 kV line extension | Regional Reliability | 2025-12-12 | 2025-06-01 | 2025-06-19 | 2024 ITP | 1527000 | 2025 | 1527000 | 1527000 |  | NTC - Commitment Window |  |  |  |  | Extend the 115 kV line from Letcher to Miner County 3.25 miles to reroute around the new lines to Letcher.
220904 | 94737 | 169696 | EREC | SD | Multi - Hanson County 115 kV System Reconfig | Hanson County 115 kV New Substation | Regional Reliability | 2025-11-07 | 2025-06-01 | 2025-06-19 | 2024 ITP | 2046000 | 2025 | 2046000 | 2046000 |  | NTC - Commitment Window |  |  |  |  | Install 115 kV new substation at Hanson County
220904 | 94737 | 169697 | EREC | SD | Multi - Hanson County 115 kV System Reconfig | Hanson County 69 kV New Substation | Regional Reliability | 2025-11-07 | 2025-06-01 | 2025-06-19 | 2024 ITP | 5441000 | 2025 | 5441000 | 5441000 |  | NTC - Commitment Window |  |  |  |  | Install 69 kV new Substation at Hanson County.
220904 | 94737 | 169698 | EREC | SD | Multi - Hanson County 115 kV System Reconfig | Hanson County 69 kV Capacitor | Regional Reliability | 2025-11-07 | 2025-06-01 | 2025-06-19 | 2024 ITP | 963000 | 2025 | 963000 | 963000 |  | NTC - Commitment Window |  |  |  |  | Install 9.6 MVAR Capacitor at Hanson County 69 kV substation
220904 | 94737 | 169699 | EREC | SD | Multi - Hanson County 115 kV System Reconfig | Hanson County 115/69 kV Transformer Ckt 1 (69 kV) | Regional Reliability | 2025-11-07 | 2025-06-01 | 2025-06-19 | 2024 ITP | 3075000 | 2025 | 3075000 | 3075000 |  | NTC - Commitment Window |  |  |  |  | Install new 115/69 transformer at Hanson County 69 kV substation
220904 | 94737 | 169701 | EREC | SD | Multi - Hanson County 115 kV System Reconfig | Mount Vernon 69 kV Ckt 1 Terminal Upgrade 3 | Regional Reliability | 2025-09-03 | 2025-06-01 | 2025-06-19 | 2024 ITP | 800000 | 2025 | 800000 | 800000 |  | NTC - Commitment Window |  |  |  |  | Install any necessary terminal equipment at Mount Vernon 69 kV substation for the line from Mount Vernon 69 kV substation to Mitchell 69 kV substation with a summer emergency rating of 84 MVA.
220919 | 94758 | 169762 | WAPA | ND | Line - Dawson County 230 kV - Williston 230 kV New Line | Dawson County - Williston 230 kV Ckt 1 New Line | Economic | 2032-12-31 | 2028-01-01 | 2025-07-08 | 2024 ITP | 237958276 | 2025 | 243907232.9 | 237958276 |  | NTC - Commitment Window | 652400 | WILLISTON | 652403 | DAWSON CREEK | Build 103.7-mile 230 kV Ckt 1 line from Dawson County 230 kV substation to Williston 230 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 796 MVA. | 230
220919 | 94758 | 169763 | WAPA | ND | Line - Dawson County 230 kV - Williston 230 kV New Line | Dawson County 230 kV Ckt 1 Terminal Upgrade | Economic | 2032-12-31 | 2028-01-01 | 2025-07-08 | 2024 ITP | 4592583 | 2025 | 4707397.575 | 4592583 |  | NTC - Commitment Window | 652400 | WILLISTON |  |  | Install any necessary terminal equipment at Dawson County 230 kV substation to support a new line from Dawson County 230 kV substation to Williston 230 kV substation with a summer emergency rating of 796 MVA. | 230
220919 | 94758 | 169764 | WAPA | MT | Line - Dawson County 230 kV - Williston 230 kV New Line | Williston 230 kV Ckt 1 Terminal Upgrade | Economic | 2032-12-31 | 2028-01-01 | 2025-07-08 | 2024 ITP | 3999147 | 2025 | 4099125.675 | 3999147 |  | NTC - Commitment Window | 652403 | DAWSON CREEK |  |  | Install any necessary terminal equipment at Williston 230 kV substation to support a new line from Williston 230 kV substation to Dawson County 230 kV substation with a summer emergency rating of 796 MVA. | 230
220973 | 94763 | 169835 | BEPC | ND | Line - Logan 230 kV - Magic City 230 kV New Line | Logan 230 kV Ckt 1 Terminal Upgrade | Regional Reliability |  | 2032-12-01 | 2025-11-20 | 2024 ITP |  |  | 0 | 4100000 |  | Identified | 659108 | LOGAN |  |  | Install any necessary terminal equipment at Logan 230 kV Ckt 1 substation to support a new line from Logan 230 kV Ckt 1 substation to Magic City 230 kV Ckt 1 substation with a summer emergency rating of 577 MVA. | 230
220903 | 94787 | 169886 | EDE | MO | Multi - Delaware - Monett - North Branson - Shipe Road - Brookline new 345 kV system | Reeds Spring - Branson Northwest 161 kV Line Tap | Economic | 2030-12-31 | 2024-11-12 | 2025-05-01 | 2024 ITP | 2515240 | 2025 | 2578121 | 2515240 |  | Delay - Mitigation |  |  |  |  | Tap the existing Reeds Spring - Branson Northwest 161 kV line where it intersects Compton Ridge - Roark Creek161 kV line | 161
220903 | 94787 | 169887 | EDE | MO | Multi - Delaware - Monett - North Branson - Shipe Road - Brookline new 345 kV system | North Branson 161 kV New Substation | Economic | 2030-12-31 | 2024-11-12 | 2025-05-01 | 2024 ITP | 36908272 | 2025 | 37830978.8 | 36908272 |  | Delay - Mitigation |  |  |  |  | Build 161 kV Substation at North Branson at intersection of Reeds Spring - Branson Northwest and Compton Ridge - Roark Creek 161 kV lines | 161
220903 | 94787 | 169888 | EDE | MO | Multi - Delaware - Monett - North Branson - Shipe Road - Brookline new 345 kV system | North Branson 345 kV New Substation | Economic | 2030-12-31 | 2024-11-12 | 2025-05-01 | 2024 ITP | 42714199 | 2025 | 43782053.975 | 42714199 |  | Delay - Mitigation |  |  |  |  | Build 345 kV Substation at North Branson at intersection of Reeds Spring - Branson Northwest and Compton Ridge - Roark Creek 161 kV lines | 345
220903 | 94787 | 169890 | EDE | MO | Multi - Delaware - Monett - North Branson - Shipe Road - Brookline new 345 kV system | North Branson 345/161 kV Transformer Ckt 1 (161 kV) | Economic | 2030-12-31 | 2024-11-12 | 2025-05-01 | 2024 ITP | 24081943 | 2025 | 24683991.575 | 24081943 |  | Delay - Mitigation |  |  |  |  | Install new 345/161 transformer at North Branson 161 kV substation | 345/161
220903 | 94787 | 169891 | EDE | MO | Multi - Delaware - Monett - North Branson - Shipe Road - Brookline new 345 kV system | North Branson 345/161 kV Transformer Ckt 1 (345 kV) | Economic | 2030-12-31 | 2024-11-12 | 2025-05-01 | 2024 ITP | 2512405 | 2025 | 2575215.125 | 2512405 |  | Delay - Mitigation |  |  |  |  | Install 345 kV terminal equipment to support 345/161 transformer at North Branson 345 kV substation | 345/161
220948 | 94721 | 169892 | EDE | MO | Multi - North Branson 345 kV - Monett 345 kV New Line | Flint Creek - Brookline 345 kV Line Tap #2 | Regional Reliability |  | 2025-12-01 | 2025-11-04 | 2024 ITP | 4625515 | 2025 | 4741152.875 | 4625515 |  | NTC - Commitment Window |  |  |  |  | Tap the existing Flint Creek - Brookline345 kV line at Monett | 345
220948 | 94721 | 169893 | EDE | MO | Multi - North Branson 345 kV - Monett 345 kV New Line | Monett 345 kV New Substation | Regional Reliability |  | 2025-12-01 | 2025-11-04 | 2024 ITP | 28286872 | 2025 | 28994043.8 | 28286872 |  | NTC - Commitment Window |  |  |  |  | Install 345 kV Substation at Monett | 345
220904 | 94782 | 169933 | EREC | SD | Multi - Madison, SD Area 115 kV System Voltage Conversion | Madison - Lake County115 kV Ckt 1 New Line | Regional Reliability | 2026-06-01 | 2025-12-31 | 2025-06-19 | 2024 ITP | 882000 | 2025 | 904050 | 882000 |  | NTC - Commitment Window | 655052 |  | 655119 |  | Build a 3-mile 115 kV Ckt 1 line from Madison SE 115 kV substation to Lake County 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 139 MVA. | 115 | 3
220904 | 94782 | 169935 | EREC | SD | Multi - Madison, SD Area 115 kV System Voltage Conversion | Madison SE - Lakeview 115 kV Ckt 1 Voltage Conversion | Regional Reliability | 2026-06-01 | 2025-12-31 | 2025-06-19 | 2024 ITP | 360000 | 2025 | 369000 | 360000 |  | NTC - Commitment Window | 655052 |  | 655226 |  | Convert the 0.9 mile Ckt 1 69kV line from Madison SE to Lakeview to 115 kV | 115
220904 | 94782 | 169937 | EREC | SD | Multi - Madison, SD Area 115 kV System Voltage Conversion | Lake County - Howard 115 kV Ckt 1 New Line | Regional Reliability | 2025-09-19 | 2025-12-31 | 2025-06-19 | 2024 ITP | 8762000 | 2025 | 8762000 | 8762000 |  | NTC - Commitment Window | 655119 |  | 655196 |  | Build a 22.2-mile 115 kV Ckt 1 line from Lake County 115 kV substation to Howard 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 139 MVA. | 115
220904 | 94782 | 169940 | EREC | SD | Multi - Madison, SD Area 115 kV System Voltage Conversion | Howard - Howard City 115 kV Ckt 1 New Line | Regional Reliability | 2025-11-14 | 2025-12-31 | 2025-06-19 | 2024 ITP | 1962000 | 2025 | 1962000 | 1962000 |  | NTC - Commitment Window | 655196 |  | 655197 |  | Build a 6.0-mile 115 kV Ckt 1 line from Howard 115kV substation to Howard City 115kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 139 MVA. | 115
220904 | 94782 | 169951 | EREC | SD | Multi - Madison, SD Area 115 kV System Voltage Conversion | Howard City - Miner County 115 kV Ckt 1 New Line | Regional Reliability | 2025-11-14 | 2025-12-31 | 2025-06-19 | 2024 ITP | 4742000 | 2025 | 4742000 | 4742000 |  | NTC - Commitment Window |  |  |  |  | Build a 12.4-mile 115 kV Ckt 1 line from Howard City 115 kV MOS to Miner County 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 139 MVA. | 115
220904 | 94782 | 169953 | EREC | SD | Multi - Madison, SD Area 115 kV System Voltage Conversion | Miner County 115 kV Ckt 1 Terminal Upgrade #2 | Regional Reliability | 2025-11-07 | 2025-12-31 | 2025-06-19 | 2024 ITP | 760000 | 2025 | 760000 | 760000 |  | NTC - Commitment Window |  |  |  |  | : Install any necessary terminal equipment at Miner County 115 kV substation to support the new line from Miner County 115 kV substation to Howard City 115 kV MOS to achieve a summer emergency rating of 139 MVA. | 115
220887 | 94811 | 169968 | BEPC | KS | Line - Holcomb - Sidney 345 kV Ckt 1 New Line | Holcomb - Sidney 345 kV Ckt 1 New Line | Economic |  | 2025-03-21 | 2025-03-21 | 2024 ITP |  |  | 0 | 0 |  | NTC-C Project Estimate Window |  |  |  |  | Build a new 300 mile 345 kV Ckt 1 line from Holcomb 345 kV Ckt 1 substation to Sidney 345 Ckt 1 substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA. | 345
220904 | 94782 | 169969 | EREC | SD | Multi - Madison, SD Area 115 kV System Voltage Conversion | VT Hanlon - Lakeview 115 kV Ckt 1 Voltage Conversion | Regional Reliability | 2010-05-12 | 2025-12-31 | 2025-06-19 | 2024 ITP |  |  | 0 | 0 |  | Complete | 655493 |  |  |  | Convert the 24-mile Ckt 1 69 kV line from Hanlon to Lakeview to 115 kV | 115
220904 | 94782 | 169970 | EREC | SD | Multi - Madison, SD Area 115 kV System Voltage Conversion | VT Hanlon 115 kV Ckt 1 Terminal Upgrade #1 | Regional Reliability | 2025-12-31 | 2025-12-31 | 2025-06-19 | 2024 ITP | 1235000 | 2025 | 1235000 | 1235000 |  | NTC - Commitment Window | 655493 |  |  |  | Install any necessary terminal equipment at Hanlon 115 kV substation to support the voltage conversion from VT Hanlon 115 kV substation to Lakeview 115 kV MOS to achieve a summer emergency rating of 139 MVA. | 115
220904 | 94782 | 169972 | EREC | SD | Multi - Madison, SD Area 115 kV System Voltage Conversion | Lake County 115 kV New Substation | Regional Reliability | 2025-08-01 | 2025-12-31 | 2025-06-19 | 2024 ITP | 3342000 | 2025 | 3342000 | 3342000 |  | NTC - Commitment Window |  |  |  |  | Install 115 kV new substation at Lake County | 115
220904 | 94782 | 169973 | EREC | SD | Multi - Madison, SD Area 115 kV System Voltage Conversion | Madison SE 115 kV New Substation | Regional Reliability | 2027-11-05 | 2025-12-31 | 2025-06-19 | 2024 ITP | 4570000 | 2025 | 4684250 | 4570000 |  | NTC - Commitment Window |  |  |  |  | Install 115 kV new substation at Madison SE | 115
220904 | 94782 | 169974 | EREC | SD | Multi - Madison, SD Area 115 kV System Voltage Conversion | Howard 115 kV New Substation | Regional Reliability | 2027-11-05 | 2025-12-31 | 2025-06-19 | 2024 ITP | 3795000 | 2025 | 3889875 | 3795000 |  | NTC - Commitment Window |  |  |  |  | Install 115 kV new substation at Howard | 115
220904 | 94782 | 169975 | EREC | SD | Multi - Madison, SD Area 115 kV System Voltage Conversion | Howard City 115 kV New Motor Operated Switch (MOS) | Regional Reliability | 2025-11-06 | 2025-12-31 | 2025-06-19 | 2024 ITP | 165000 | 2025 | 165000 | 165000 |  | NTC - Commitment Window |  |  |  |  | Install new three-way motor-operated switch and any necessary terminal equipment at Howard City MOS for the lines from Howard City MOS to Miner County substation and from the Howard City MOS to the Howard substation with a summer emergency rating of 139 MVA. | 115
220904 | 94782 | 169977 | EREC | SD | Multi - Madison, SD Area 115 kV System Voltage Conversion | Lakeview 115 kV New Motor Operated Switch (MOS) | Regional Reliability | 2026-06-12 | 2025-12-31 | 2025-06-19 | 2024 ITP | 165000 | 2025 | 169125 | 165000 |  | NTC - Commitment Window |  |  |  |  | Install new three-way motor-operated switch and any necessary terminal equipment at Lakeview 115 kV MOS for the lines from Lakeview 115 kV MOS to Madison SE substation and from Lakeview 115 kV MOS to VT Hanlon substation with a summer emergency rating of 139 MVA. | 115
220904 | 94782 | 169978 | EREC | SD | Multi - Madison, SD Area 115 kV System Voltage Conversion | Miner County 115 kV Ckt 1 Terminal Upgrade #1 | Regional Reliability | 2025-05-01 | 2025-12-31 | 2025-06-19 | 2024 ITP | 760000 | 2025 | 760000 | 760000 |  | NTC - Commitment Window | 655548 |  |  |  | Install any necessary terminal equipment at Miner County 115 kV substation to support the new line from Miner County 115 kV substation to Fedora 115 kV substation to achieve a summer emergency rating of 139 MVA. | 115
220904 | 94782 | 169979 | EREC | SD | Multi - Madison, SD Area 115 kV System Voltage Conversion | Lake County 115/69 kV Transformer Ckt 1 (69 kV) | Regional Reliability | 2025-10-01 | 2025-12-31 | 2025-06-19 | 2024 ITP | 3344000 | 2025 | 3344000 | 3344000 |  | NTC - Commitment Window |  |  |  |  | Install new 115/69 transformer at Lake County 69 kV substation | 115/69
220906 | 94795 | 169993 | BEPC | ND | Line - Patent Gate 345 kV - Pioneer 345 kV New Line | Patent Gate - Pioneer 345 kV Ckt 1 New Line | Regional Reliability | 2030-11-30 | 2025-04-01 | 2025-05-06 | 2024 ITP | 128061208 | 2025 | 131262738.2 | 131262739 |  | NTC - Commitment Window | 659390 |  | 659575 |  | Build approximately 50 mile 345 kV Ckt 1 line from Patent Gate 345 kV substation to Pioneer 345 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA | 345
220906 | 94795 | 169994 | BEPC | ND | Line - Patent Gate 345 kV - Pioneer 345 kV New Line | Patent Gate 345 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2030-11-30 | 2025-04-01 | 2025-05-06 | 2024 ITP | 589680 | 2025 | 604422 | 589680 |  | NTC - Commitment Window | 659390 |  |  |  | : Install any necessary terminal equipment at Patent Gate 345 kV substation to support a new line from Patent Gate 345 kV substation to Pioneer 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220906 | 94795 | 169995 | BEPC | ND | Line - Patent Gate 345 kV - Pioneer 345 kV New Line | Pioneer 345 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2030-11-30 | 2025-04-01 | 2025-05-06 | 2024 ITP | 3949983 | 2025 | 4048732.575 | 3949983 |  | Pending NTC/NTC-C | 659575 |  |  |  | Install any necessary terminal equipment at Pioneer 345 kV substation to support a new line from Pioneer 345 kV substation to Patent Gate 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220932 | 94800 | 170000 | WAPA | ND | Multi - Belfield 345 kV - Maurine 345 kV | Belfield 2 - Maurine 2 345 kV Ckt 1 New Line | Economic | 2034-10-01 | 2025-01-01 | 2025-08-19 | 2024 ITP | 402593167 | 2025 | 412657996.175 | 402593167 |  | Delay - Mitigation |  |  |  |  | Build a 154.2-mile 345 kV Ckt 1 new line from Belfield 2 345 kV substation to Maurine 2 345 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA. This upgrade shall include 40 MVAR line reactor compensation at the Belfield 2 and Maurine 2 terminals. | 345
220932 | 94800 | 170001 | WAPA | ND | Multi - Belfield 345 kV - Maurine 345 kV | Belfield 2 345 kV Ckt 1 Terminal Upgrade | Economic | 2034-11-01 | 2025-01-01 | 2025-08-19 | 2024 ITP | 10400000 | 2025 | 10660000 | 10400000 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at Belfield 2 345 kV substation to support a new line from Belfield 2 345 kV substation to Maurine 2 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220932 | 94800 | 170002 | WAPA | SD | Multi - Belfield 345 kV - Maurine 345 kV | Maurine 2 345 kV Ckt 1 Terminal Upgrade | Economic | 2034-10-01 | 2025-01-01 | 2025-08-19 | 2024 ITP | 11443047 | 2025 | 11729123.175 | 11443047 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at Maurine 2 345 kV substation to support a new line from Maurine 2 345 kV substation to Belfield 2 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220928 | 94986 | 170003 | BEPC | WY | Multi - New Underwood 345 kV - Laramie River 345 kV | Laramie River - New Underwood 345 kV Ckt 1 New Line (BEPC) | Economic | 2034-10-01 | 2025-01-01 | 2025-08-13 | 2024 ITP | 582799370 | 2025 | 597369354.25 | 582799370 |  | On Schedule < 4 |  |  |  |  | Build a 161.4-mile 345 kV Ckt1 new line from Laramie River 345 kV Ckt1 substation to new New Underwood 345 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA. | 345 | 161.4
220928 | 94986 | 170004 | BEPC | SD | Multi - New Underwood 345 kV - Laramie River 345 kV | Laramie River 345 kV Ckt 1 Terminal Upgrade (BEPC) | Economic | 2034-10-01 | 2025-01-01 | 2025-08-13 | 2024 ITP | 11334906 | 2025 | 11618278.65 | 11334906 |  | On Schedule < 4 |  |  |  |  | Install any necessary terminal equipment at Laramie River 345 kV substation to support a new line from Laramie River 345 kV substation to new New Underwood 345 kV substation with a summer emergency rating of 1792 MVA. This also includes at least a 40 MVAR line reactor on this line terminal at Laramie River. | 345
220929 | 94986 | 170005 | WAPA | SD | Multi - New Underwood 345 kV - Laramie River 345 kV | New Underwood 2 345 kV Ckt 1 Terminal Upgrade | Economic | 2034-10-01 | 2025-01-01 | 2025-08-13 | 2024 ITP | 9747839 | 2025 | 9991534.975 | 9747839 |  | NTC - Commitment Window |  |  |  |  | Install any necessary terminal equipment at New Underwood 2 345 kV substation to support a new line from New Underwood 2 345 kV substation to Laramie River 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220929 | 94986 | 170006 | WAPA | SD | Multi - New Underwood 345 kV - Laramie River 345 kV | New Underwood 2 - Maurine 2 345 kV Ckt 1 New Line | Economic | 2034-10-01 | 2025-01-01 | 2025-08-13 | 2024 ITP | 211621167 | 2025 | 216911696.175 | 211621167 |  | NTC - Commitment Window |  |  |  |  | Build a 78-mile 345 kV Ckt1 new line from New Underwood 2 345 kV substation to Maurine 2 345 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA. This upgrade shall include 40 MVAR line reactor compensation at the New Underwood 2 and Maurine 2 terminals. | 345
220940 | 94811 | 170008 | SEPC | KS// | Line - Holcomb - Sidney 345 kV Ckt 1 New Line | Holcomb 345 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2030-10-01 | 2025-03-21 | 2025-09-23 | 2024 ITP | 14343048 |  | 0 | 20172702 |  | NTC - Commitment Window | 531449 | HOLCOMB |  |  | Install any necessary equipment at Holcomb 345 kV substation for the line from Holcomb 345 kV substation to Sidney 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220939 | 94811 | 170009 | BEPC | KS | Line - Holcomb - Sidney 345 kV Ckt 1 New Line | Sidney 345 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2030-12-31 | 2025-03-21 | 2025-09-23 | 2024 ITP | 21138823 |  | 0 | 21138823 |  | NTC-C Project Estimate Window | 659133 | SIDNEY |  |  | Install any necessary terminal equipment at Sidney 345 kV substation for the line from Sidney 345 kV substation to Holcomb 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220929 | 94986 | 170012 | WAPA | SD | Multi - New Underwood 345 kV - Laramie River 345 kV | New Underwood 2 345 kV Ckt 1 Terminal Upgrade #1 | Economic | 2034-10-01 | 2025-01-01 | 2025-08-13 | 2024 ITP | 10327789 | 2025 | 10585983.725 | 10327789 |  | NTC - Commitment Window |  |  |  |  | : Install any necessary terminal equipment at New Underwood 2 345 kV substation to support a new line from New Underwood 2 345 kV substation to Maurine 2 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220932 | 94800 | 170013 | WAPA | SD | Multi - Belfield 345 kV - Maurine 345 kV | Maurine 2 345 kV Ckt 1 Terminal Upgrade #1 | Economic | 2034-10-01 | 2025-01-01 | 2025-08-19 | 2024 ITP | 9816800 | 2025 | 10062220 | 9816800 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at Maurine 2 345 kV substation to support a new line from Maurine 2 345 kV substation to New Underwood 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220929 | 94986 | 170014 | WAPA | SD | Multi - New Underwood 345 kV - Laramie River 345 kV | New Underwood 2 345 kV New Substation | Economic | 2034-10-01 | 2025-01-01 | 2025-08-13 | 2024 ITP | 15827515 | 2025 | 16223202.875 | 15827515 |  | NTC - Commitment Window |  |  |  |  | Build a new 345 kV substation at New Underwood 2 | 345
220932 | 94800 | 170015 | WAPA | SD | Multi - Belfield 345 kV - Maurine 345 kV | Maurine 2 345 kV New Substation | Economic | 2034-10-01 | 2025-01-01 | 2025-08-19 | 2024 ITP | 14987986 | 2025 | 15362685.65 | 14987986 |  | Delay - Mitigation |  |  |  |  | Build a 345 kV new substation at Maurine 2 | 345
220929 | 94986 | 170016 | WAPA | SD | Multi - New Underwood 345 kV - Laramie River 345 kV | New Underwood 2 345/230 kV Transformer Ckt 1 (230 kV) | Economic | 2034-10-01 | 2025-01-01 | 2025-08-13 | 2024 ITP | 15975365 | 2025 | 16374749.125 | 15975365 |  | NTC - Commitment Window |  |  |  |  | Install a new 345/230 kV transformer at the new New Underwood 2 230 kV substation. | 345/230
220929 | 94986 | 170017 | WAPA | SD | Multi - New Underwood 345 kV - Laramie River 345 kV | New Underwood 2 345/230 kV Transformer Ckt 1 (345 kV) | Economic | 2034-10-01 | 2025-01-01 | 2025-08-13 | 2024 ITP | 2964870 | 2025 | 3038991.75 | 2964870 |  | NTC - Commitment Window |  |  |  |  | Install 345 kV terminal equipment to support 345/230 kV transformer at the new New Underwood 2 345 kV substation | 345/230
220932 | 94800 | 170018 | WAPA | SD | Multi - Belfield 345 kV - Maurine 345 kV | Maurine 2 345/230 kV Transformer Ckt 1 (230 kV) | Economic | 2034-10-01 | 2025-01-01 | 2025-08-19 | 2024 ITP | 15681376 | 2025 | 16073410.4 | 15681376 |  | Delay - Mitigation |  |  |  |  | Install a new 345/230 kV transformer at the new Maurine 2 345 kV substation | 345/230
220932 | 94800 | 170019 | WAPA | SD | Multi - Belfield 345 kV - Maurine 345 kV | Maurine 2 345/230 kV Terminal Equipment | Economic | 2034-10-01 | 2025-01-01 | 2025-08-19 | 2024 ITP | 2703604 | 2025 | 2771194.1 | 2703604 |  | Delay - Mitigation |  |  |  |  | Install 345 kV and 230 kV terminal equipment to support 345/230 kV transformer at the new Maurine 2 345 kV substation tied to the 230 kV terminal equipment at the existing Maurine substation. | 345/230
220902 | 94788 | 170036 | OPPD | NE | Line - S3458 345 kV - S3740 345 kV Ckt 2 New Line | S3458 - S3740 345 kV Ckt 2 New Line | Economic | 2030-12-31 | 2025-01-01 | 2025-04-24 | 2024 ITP | 97406244 | 2025 | 99841400.1 | 97406244 |  | Delay - Mitigation |  |  |  |  | Build second 33-mile 345 kV Ckt 2 line from S3458 345 kV substation to S3740 345 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA | 345 | 33
220902 | 94788 | 170037 | OPPD | NE | Line - S3458 345 kV - S3740 345 kV Ckt 2 New Line | S3458 345 kV Ckt 2 Terminal Upgrade | Economic | 2030-12-31 | 2025-01-01 | 2025-04-24 | 2024 ITP | 5206856 | 2025 | 5337027.4 | 5206856 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at S3458 345 kV substation to support a second line from S3458 345 kV substation to S3740 345 kV substation with a summer emergency rating of 1792 MVA | 345
220902 | 94788 | 170038 | OPPD | NE | Line - S3458 345 kV - S3740 345 kV Ckt 2 New Line | S3740 345 kV Ckt 2 Terminal Upgrade | Economic | 2030-12-31 | 2025-01-01 | 2025-04-24 | 2024 ITP | 3386900 | 2025 | 3471572.5 | 3386900 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at S3740 345 kV substation to support a second line from S3740 345 kV substation to S3458 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220936 | 94805 | 170051 | SPS | NM | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Potter County - Crossroads 765 kV Ckt 1 New Line | Regional Reliability | 2031-05-15 | 2025-01-01 | 2025-09-09 | 2024 ITP | 936807351 |  | 0 | 936807351 |  | NTC - Commitment Window |  |  |  |  | Build a new 123.7 mile 765 kV Ckt 1 line from Potter County 765 kV substation to Crossroads 765 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 5300 MVA. | 765
220936 | 94805 | 170054 | SPS | NM | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Crossroads - Phantom 765 kV Ckt 1 New Line | Regional Reliability | 2031-05-15 | 2025-01-01 | 2025-09-09 | 2024 ITP | 1158308441 |  | 0 | 1158308441 |  | NTC - Commitment Window |  |  |  |  | Build 120.5 mile 765 kV Ckt 1 line from Crossroads substation to Phantom substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 5300 MVA. | 765
220979 | 94807 | 170065 | SPS | OK | Line - Beckham County - Potter -345 kV New Line | Beckham County - Potter 345 kV Ckt 1 New Line (SPS) | Economic | 2029-11-12 | 2029-11-12 | 2025-12-03 | 2024 ITP |  |  | 0 | 222551930 |  | Identified |  |  |  |  | Build a 149.6 mile 345 kV Ckt1 new line from Beckham County 345 kV substation to Potter 345 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA. | 345 | 149.6
220812 | 94807 | 170066 | OGE | OK | Line - Beckham County - Potter -345 kV New Line | Beckham County 345 kV Ckt 1 Terminal Upgrade | Economic | 2029-11-12 | 2029-11-12 | 2024-12-13 | 2024 ITP | 4500000 | 2025 | 4612500 | 4500000 |  | On Schedule < 4 |  |  |  |  | Install any necessary terminal equipment at Beckham County 345 kV substation to support the line from Beckham County 345 kV substation to Potter 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220936 | 94805 | 170067 | SPS | NM | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Crossroads 765 kV Reactor 2 | Regional Reliability | 2031-05-15 | 2025-01-01 | 2025-09-09 | 2024 ITP | 69919661 |  | 0 | 69919661 |  | NTC - Commitment Window |  |  |  |  | Install at least -150 MVAR reactor at Crossroads 765 kV substation looking to Phantom 765 kV substation | 765
220936 | 94805 | 170068 | SPS | NM | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Crossroads 765/345 kV Transformer Ckt 1 (345 kV) | Regional Reliability | 2031-05-15 | 2025-01-01 | 2025-09-09 | 2024 ITP | 74330994 |  | 0 | 74330994 |  | NTC - Commitment Window |  |  |  |  | Install new 765/345 transformer at Crossroads 345 kV substation | 765/345
220936 | 94805 | 170078 | SPS | NM | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | New 765 kV Substation at Crossroads | Regional Reliability | 2031-05-15 | 2025-01-01 | 2025-09-09 | 2024 ITP | 163882248 |  | 0 | 163882248 |  | NTC - Commitment Window |  |  |  |  | Install 765 kV Substation at Crossroads and install any necessary terminal equipment at Crossroads 765 kV substation to support a new line from Crossroads 765 kV substation to Phantom 765 kV substation with a summer emergency rating of 5300 MVA and any necessary terminal equipment at Crossroads 765 kV substation to support a new line from Crossroads 765 kV substation to Potter County 765 kV substation with a summer emergency rating of 5300 MVA. | 765
220936 | 94805 | 170079 | SPS | NM | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | New 765 kV Substation at Phantom | Regional Reliability | 2031-05-15 | 2025-01-01 | 2025-09-09 | 2024 ITP | 156031580 |  | 0 | 156031580 |  | NTC - Commitment Window |  |  |  |  | Install 765 kV Substation at Phantom and install any necessary terminal equipment at Phantom 765 kV substation to support a new line from Phantom 765 kV substation to Crossroads 765 kV substation with a summer emergency rating of 5300 MVA. | 765
220936 | 94805 | 170080 | SPS | TX | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | New 765 kV Substation at Potter | Regional Reliability | 2031-05-15 | 2025-01-01 | 2025-09-09 | 2024 ITP | 156339028 |  | 0 | 156339028 |  | NTC - Commitment Window |  |  |  |  | Install 765 kV Substation at Potter County and install any necessary terminal equipment at Potter County 765 kV substation to support a new line from Potter County 765 kV substation to Crossroads 765 kV substation with a summer emergency rating of 5300 MVA. | 765
220936 | 94805 | 170091 | SPS | NM | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Phantom 765/345 kV Transformer Ckt 1 (345 kV) | Regional Reliability | 2031-05-15 | 2025-01-01 | 2025-09-09 | 2024 ITP | 73665801 |  | 0 | 73665801 |  | NTC - Commitment Window |  |  |  |  | Install new 765/345 transformer at Phantom 345 kV substation | 765/345
220817 | 94807 | 170093 | SPS | OK | Line - Beckham County - Potter -345 kV New Line | Potter 345 kV Ckt 1 Terminal Upgrade | Economic | 2029-11-12 | 2029-11-12 | 2024-12-13 | 2024 ITP | 20423945 | 2025 | 20934543.625 | 23950000 |  | On Schedule < 4 |  |  |  |  | Install any necessary terminal equipment at Potter 345 kV substation to support the line from Potter 345 kV substation to Beckham County 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220936 | 94805 | 170096 | SPS | TX | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Potter 765/345 kV Transformer Ckt 1 (345 kV) | Regional Reliability | 2031-05-15 | 2025-01-01 | 2025-09-09 | 2024 ITP | 73665801 |  | 0 | 73665801 |  | NTC - Commitment Window |  |  |  |  | Install new 765/345 transformer at Potter County 345 kV substation | 765/345
220946 | 94929 | 170106 | AEP | OK | Line - Delaware 345 kV - Monett 345 kV Ckt 1 New Line | Delaware - Monett 345 kV Ckt 1 New Line | Regional Reliability | 2029-11-01 | 2024-11-12 | 2025-11-04 | 2024 ITP | 250258040 | 2025 | 256514491 | 250258040 |  | Delay - Mitigation |  |  |  |  | Build 114.5 mile 345 kV Ckt 1 line from Delaware 345 kV Ckt 1 substation to Monett 345 kV Ckt 1 substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA. | 345
220947 | 94929 | 170107 | EDE | MO | Line - Delaware 345 kV - Monett 345 kV Ckt 1 New Line | Monett 345 kV Ckt 1 Terminal Upgrade #6 | Regional Reliability |  | 2025-12-01 | 2025-11-04 | 2024 ITP | 3610024 | 2025 | 3700274.6 | 3610024 |  | NTC-C Project Estimate Window |  |  |  |  | Install any necessary terminal equipment at Monett 345 kV substation to support a new line from Monett 345 kV substation to Delaware 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220946 | 94929 | 170110 | AEP | OK | Line - Delaware 345 kV - Monett 345 kV Ckt 1 New Line | Delaware 345 kV Ckt 1 Terminal Upgrade #2 | Regional Reliability | 2029-11-01 | 2024-11-12 | 2025-11-04 | 2024 ITP | 15031457 | 2025 | 15407243.425 | 15031457 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at Delaware 345 kV Ckt1 substation to support a new line from Delaware 345 kV Ckt1 substation to Monett 345 kV Ckt1 substation with a summer emergency rating of 1792 MVA. | 345
220808 | 94816 | 170123 | EKC | KS | Line - Chisholm 138 kV - Maize 138 kV - Evan Energy Center North 138 KV Ct1 Rebuild | Chisholm - Maize 138 kV Ckt 1 Rebuild | Economic | 2031-12-31 | 2032-01-01 | 2024-12-13 | 2024 ITP | 10780770 | 2025 | 11050289.25 | 5760359 |  | On Schedule > 4 | 533035 | CHISHOLM 138 KV | 533054 | MAIZE | Rebuild 7.3-mile Ckt 1 line from Chisholm 138 kV substation to Maize 138 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 478 MVA | 138
220808 | 94816 | 170124 | EKC | KS | Line - Chisholm 138 kV - Maize 138 kV - Evan Energy Center North 138 KV Ct1 Rebuild | Chisholm 138 kV Ckt 1 Terminal Upgrade | Economic | 2031-12-31 | 2032-01-01 | 2024-12-13 | 2024 ITP | 168527 | 2025 | 172740.175 | 168528 |  | On Schedule > 4 | 533035 | CHISHOLM 138 KV |  |  | Install any necessary terminal equipment at Chisholm 138 kV substation to support the line from Chisholm 138 kV substation to Maize 138 kV substation with a summer emergency rating of 478 MVA. | 138
220808 | 94816 | 170127 | EKC | KS | Line - Chisholm 138 kV - Maize 138 kV - Evan Energy Center North 138 KV Ct1 Rebuild | Maize 138 kV Ckt 1 Terminal Upgrade #2 | Economic | 2031-12-31 | 2032-01-01 | 2024-12-13 | 2024 ITP | 59116 | 2025 | 60593.9 | 59116 |  | On Schedule > 4 | 533054 | MAIZE |  |  | Install any necessary terminal equipment at Maize 138 kV substation to support a line from Maize 138 kV substation to Chisholm 138 kV substation with a summer emergency rating of 478 MVA. | 138
220907 | 94819 | 170131 | NPPD | TX | Line - Gering 115 kV - Scottsbluff 115 kV Rebuild | Scottsbluff 115 kV Ckt 1 Terminal Upgrade | Economic |  | 2025-01-01 | 2025-05-06 | 2024 ITP |  |  | 0 | 385333 |  | Identified | 653313 |  |  |  | Install any necessary terminal equipment at Scottsbluff 115 kV substation for the line from Scottsbluff 115 kV substation to Gering 115 kV substation with a summer emergency rating of 239 MVA. | 115
220903 | 94832 | 170133 | EDE | MO | Line - Aurora H.T. 161 kV - Monett 161 kV Rebuild | Aurora H.T. - Monett 161 kV Ckt 1 Rebuild | Economic | 2028-08-31 | 2024-11-12 | 2025-05-01 | 2024 ITP | 23159596 | 2025 | 23738585.9 | 23159596 |  | Delay - Mitigation | 547468 | SUB 124 - AURORA H.T. | 547480 | SUB 383 - MONETT | Rebuild 11.5 mile Ckt1 line from Aurora H.T. 161 kV Ckt1 substation to Monett 161 kV Ckt1 substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 557 MVA. | 161
220903 | 94832 | 170134 | EDE | MO | Line - Aurora H.T. 161 kV - Monett 161 kV Rebuild | Aurora H.T. 161 kV Ckt 1 Terminal Upgrade | Economic | 2028-08-31 | 2024-11-12 | 2025-05-01 | 2024 ITP | 582032 | 2025 | 596582.8 | 582032 |  | Delay - Mitigation | 547468 | SUB 124 - AURORA H.T. |  |  | Install any necessary terminal equipment at Aurora H.T. 161 kV Ckt1 substation to support the line from Aurora H.T. 161 kV Ckt1 substation to Monett 161 kV Ckt1 substation with a summer emergency rating of 557 MVA. | 161
220903 | 94832 | 170141 | EDE | MO | Line - Aurora H.T. 161 kV - Monett 161 kV Rebuild | Monett 161 kV Ckt 1 Terminal Upgrade #1 | Economic | 2028-08-31 | 2024-11-12 | 2025-05-01 | 2024 ITP | 803766 | 2025 | 823860.15 | 803766 |  | Delay - Mitigation | 547480 | SUB 383 - MONETT |  |  | Install any necessary terminal equipment at Monett 161 kV Ckt1 substation to support the line from Monett 161 kV Ckt1 substation to Aurora H.T. 161 kV Ckt1 substation with a summer emergency rating of 557 MVA. | 161
220810 | 94814 | 170147 | NPPD | NE | Line - Aurora 115 kV - Central City 115 kV New Line | Aurora - Central City 115 kV Ckt 1 New Line | Regional Reliability | 2028-12-31 | 2026-06-01 | 2024-12-13 | 2024 ITP | 22366000 | 2025 | 22925150 | 22366000 |  | Delay - Mitigation | 640063 | Aurora | 640107 | Central City | Build a 13.2-mile 115 kV Ckt 1 new line from Aurora 115 kV substation to Central City 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of at least 228 MVA. | 115 | 13.2
220810 | 94814 | 170148 | NPPD | NE | Line - Aurora 115 kV - Central City 115 kV New Line | Aurora 115 kV Ckt 1 Terminal Upgrade #1 | Regional Reliability | 2028-12-31 | 2026-06-01 | 2024-12-13 | 2024 ITP | 1743770 | 2025 | 1787364.25 | 1743770 |  | Delay - Mitigation | 640063 | Aurora |  |  | Install any necessary terminal equipment at Aurora 115 kV substation to support a new line from Aurora 115 kV substation to Central City 115 kV substation with a summer emergency rating of at least 228 MVA. | 115
220810 | 94814 | 170149 | NPPD | NE | Line - Aurora 115 kV - Central City 115 kV New Line | Central City 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2028-12-31 | 2026-06-01 | 2024-12-13 | 2024 ITP | 1828162 | 2025 | 1873866.05 | 1828162 |  | Delay - Mitigation | 640107 | Central City |  |  | Install any necessary terminal equipment at Central City 115 kV substation to support a new line from Central City 115 kV substation to Aurora 115 kV substation with a summer emergency rating of at least 228 MVA. | 115
220949 | 94867 | 170151 | SPS | NM | Multi - San Andreas - Seminole Mid America - Denver Tap 115/69 kV Intersection | San Andreas - Seminole 115 kV Line Tap | Regional Reliability |  | 2025-06-01 | 2025-11-07 | 2024 ITP | 7746098 | 2025 | 7939750.45 | 7746098 |  | NTC-C Project Estimate Window |  |  |  |  | Tap the existing San Andreas - Seminole 115 kV line where it intersects Mid America - Denver 69 kV line and upgrade any necessary terminal equipment to achieve a summer emergency rating of 194 MVA. | 115
220949 | 94867 | 170152 | SPS | NM | Multi - San Andreas - Seminole Mid America - Denver Tap 115/69 kV Intersection | San Sem Tap 115/69 kV Transformer Ckt 1 (69 kV) | Regional Reliability |  | 2025-06-01 | 2025-11-07 | 2024 ITP | 5441435 | 2025 | 5577470.875 | 5441435 |  | NTC-C Project Estimate Window |  |  |  |  | Install new 115/69 transformer at San Sem Tap 69 kV substation | 115/69
220949 | 94867 | 170153 | SPS | NM | Multi - San Andreas - Seminole Mid America - Denver Tap 115/69 kV Intersection | San Sem Tap 115/69 kV Transformer Ckt 1 (115 kV) | Regional Reliability |  | 2025-06-01 | 2025-11-07 | 2024 ITP | 2186308 | 2025 | 2240965.7 | 2186308 |  | NTC-C Project Estimate Window |  |  |  |  | Install 115 kV terminal equipment to support 115/69 transformer at San Sem Tap 115 kV substation. | 115/69
220925 | 94830 | 170157 | SPS | NM | Line - Medanos 115 kV - Lynch 115 kV New Line | Medanos - Lynch 115 kV Ckt 1 New Line | Regional Reliability | 2028-10-13 | 2028-12-01 | 2025-08-07 | 2024 ITP | 21171782 | 2025 | 21701076.55 | 21717782 |  | In Service | 527954 |  | 528390 |  | Build a 17 mile 115 kV Ckt 1 line from Medanos to Lynch | 115 | 17
220817 | 94830 | 170158 | SPS | NM | Line - Medanos 115 kV - Lynch 115 kV New Line | Medanos 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2028-10-13 | 2028-12-01 | 2024-12-13 | 2024 ITP | 4846641 | 2025 | 4967807.025 | 5489000 |  | On Schedule < 4 | 527954 |  |  |  | Install any necessary terminal equipment at Medanos 115 kV substation to support a new line from Medanos 115 kV substation to Lynch 115 kV substation with a summer emergency rating of 298 MVA. | 115
220817 | 94830 | 170159 | SPS | NM | Line - Medanos 115 kV - Lynch 115 kV New Line | Lynch 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2028-10-13 | 2028-12-01 | 2024-12-13 | 2024 ITP | 11617504 | 2025 | 11907941.6 | 11266000 |  | On Schedule < 4 | 528390 |  |  |  | Install any necessary terminal equipment at Lynch 115 kV substation to support a new line from Lynch 115 kV substation to Medanos 115 kV substation with a summer emergency rating of 298 MVA. | 115
220817 | 94952 | 170160 | SPS | NM | Sub - Lynch 115 kV -Pearle 115 kV Terminal Upgrades | Lynch 115 kV Terminal Upgrade | Regional Reliability | 2028-05-31 | 2028-12-01 | 2024-12-13 | 2024 ITP |  |  | 0 |  |  | On Schedule < 4 | 528390 |  |  |  | Install any necessary terminal equipment at Lynch 115 kV substation to support the line from Lynch 115 kV substation to Pearle 115 kV substation with a summer emergency rating of 152 MVA. | 115
220817 | 94952 | 170161 | SPS | NM | Sub - Lynch 115 kV -Pearle 115 kV Terminal Upgrades | Pearl 115 kV Terminal Upgrade | Regional Reliability |  | 2028-12-01 | 2024-12-13 | 2024 ITP | 274950 | 2025 | 281823.75 | 0 |  | In Service | 528392 | Pearl Sub 115 kV |  |  | Install any necessary terminal equipment at Pearl 115 kV substation to support the line from Pearl 115 kV substation to Lynch 115 kV substation with a summer emergency rating of 298.1 MVA. | 115
220812 | 94835 | 170168 | OGE | OK | Device - Maud Tap 138 kV Terminal Equipment | Maud Tap 138 kV Ckt 1 Terminal Upgrade | Economic | 2026-05-31 | 2025-01-01 | 2024-12-13 | 2024 ITP | 736625 | 2025 | 755040.625 | 736625 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at Maud Tap 138 kV substation for the line from Maud Tap 138 kV substation to Earlsboro 138 kV substation with a summer emergency rating of 286 MVA. | 138
220949 | 94867 | 170169 | SPS | NM | Multi - San Andreas - Seminole Mid America - Denver Tap 115/69 kV Intersection | San Sem Tap 115 kV New Substation | Regional Reliability |  | 2025-06-01 | 2025-11-07 | 2024 ITP | 9321219 | 2025 | 9554249.475 | 9321219 |  | NTC-C Project Estimate Window |  |  |  |  | Install 115 kV new substation at San Sem Tap | 115
220895 | 94868 | 170170 | LEA | NM | Line - Iron House 115 kV - Texaco 115 kV New Line | Iron House - Texaco 115 kV Ckt 1 New Line | Regional Reliability | 2029-12-15 | 2025-06-01 | 2025-03-21 | 2024 ITP |  |  | 0 | 19900000 |  | NTC - Commitment Window | 528385 | Buckeye Sub 115 kV | 528627 |  | Build a 2.3 mile 115 kV Ckt 1 new line from Iron House 115 kV Ckt1 substation to Texaco 15 kV Ckt1 substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA. | 115
220890 | 94868 | 170171 | SPS | NM | Line - Iron House 115 kV - Texaco 115 kV New Line | Iron House 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2029-10-15 | 2025-06-01 | 2025-02-12 | 2024 ITP | 3700485 | 2025 | 3792997.125 | 3700485 |  | NTC - Commitment Window | 528385 | Buckeye Sub 115 kV |  |  | Install any necessary terminal equipment at Iron House 115 kV Ckt1 substation to support a new line from Iron House 115 kV Ckt1 substation to Texaco 115 kV Ckt1 substation with a summer emergency rating of 289 MVA. | 115
220945 | 94869 | 170172 | SPS | NM | Line - Moore County 230 kV - Xit 230 kV New Line | Moore County - Xit 230 kV Ckt 1 New Line | Regional Reliability | 2028-12-15 | 2025-06-01 | 2025-11-04 | 2024 ITP | 54563546 | 2025 | 55927634.65 | 54563546 |  | NTC - Commitment Window | 523221 |  | 523309 | Moore County Interchange 230 kV | Build 46.2-mile 230 kV Ckt1 line from Moore County 230 kV substation to Xit 230 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 796 MVA. | 230
220945 | 94869 | 170173 | SPS | NM | Line - Moore County 230 kV - Xit 230 kV New Line | Moore County 230 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2028-12-15 | 2025-06-01 | 2025-11-04 | 2024 ITP | 10632427 | 2025 | 10898237.675 | 10632427 |  | NTC - Commitment Window | 523221 |  |  |  | Install any necessary terminal equipment at Moore County 230 kV substation to support a new line from Moore County 230 kV substation to Xit 230 kV substation with a summer emergency rating of 796 MVA. | 230
220945 | 94869 | 170174 | SPS | TX | Line - Moore County 230 kV - Xit 230 kV New Line | Xit 230 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2028-12-15 | 2025-06-01 | 2025-11-04 | 2024 ITP | 6641650 | 2025 | 6807691.25 | 6641650 |  | NTC - Commitment Window | 523309 | Moore County Interchange 230 kV |  |  | Install any necessary terminal equipment at Xit 230 kV substation to support a new line from Xit 230 kV substation to Moore County 230 kV substation with a summer emergency rating of 796 MVA. | 230
220817 | 94870 | 170190 | SPS | TX | Device - Channing 230 kV Capacitor | Channing 230 kV Capacitor | Regional Reliability | 2027-12-15 | 2025-06-01 | 2024-12-13 | 2024 ITP | 6498526 | 2025 | 6660989.15 | 6775647 |  | Delay - Mitigation |  |  |  |  | Install a 14.4 MVAR Capacitor at Channing 230 kV substation | 230
220871 | 94815 | 170191 | GRDA | OK | XFR - Catoosa 161/138 kV | Catoosa 161/138 kV Transformer (GRDA) | Economic | 2027-04-01 | 2025-01-01 | 2024-12-13 | 2024 ITP | 7641150 | 2025 | 7832178.75 | 7641150 |  | Delay - Mitigation |  |  |  |  | Switch in the 161/138 transformer at Catoosa 161 kV substation with a summer emergency rating of 96 MVA. | 161/138
220931 | 94818 | 170192 | NPPD | NE | Line - Ainsworth Wind 115 kV - Bassett 115 kV New Line | Ainsworth Wind - Bassett 115 kV Ckt 1 New Line | Regional Reliability | 2029-06-01 | 2029-06-01 | 2025-08-19 | 2024 ITP | 31006000 | 2025 | 31781150 | 31006000 |  | On Schedule < 4 | 640050 | Ainsworth | 640580 |  | Build a 25-mile 115 kV Ckt 1 new line from Ainsworth Wind 115 kV substation to Bassett 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of at least 228 MVA. | 115 | 25
220931 | 94818 | 170193 | NPPD | NE | Line - Ainsworth Wind 115 kV - Bassett 115 kV New Line | Ainsworth Wind 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2029-06-01 | 2029-06-01 | 2025-08-19 | 2024 ITP | 1562842 | 2025 | 1601913.05 | 1562842 |  | On Schedule < 4 |  |  | 640050 | Ainsworth | Install any necessary terminal equipment at Ainsworth Wind 115 kV substation to support a new line from Ainsworth Wind 115 kV substation to Bassett 115 kV substation with a summer emergency rating of at least 228 MVA. | 115
220931 | 94818 | 170194 | NPPD | NE | Line - Ainsworth Wind 115 kV - Bassett 115 kV New Line | Bassett 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2029-06-01 | 2029-06-01 | 2025-08-19 | 2024 ITP | 1313940 | 2025 | 1346788.5 | 1313940 |  | On Schedule < 4 |  |  | 640580 |  | : Install any necessary terminal equipment at Bassett 115 kV substation to support a new line from Bassett 115 kV substation to Ainsworth Wind 115 kV substation with a summer emergency rating of at least 228 MVA. | 115
220930 | 94842 | 170229 | NPPD | NE | Line - Holt County 345 kV - Antelope 345 kV New Line | Antelope - Holt County 345 kV Ckt 1 New Line | Economic | 2029-12-31 | 2025-01-01 | 2025-08-19 | 2024 ITP | 69160208 | 2025 | 70889213.2 | 69160208 |  | On Schedule < 4 |  |  |  |  | Build a 24 mile 345 kV Ckt1 new line from Holt County 345 kV Ck1 substation to Antelope 345 kV Ck1 substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA. | 345 | 24
220930 | 94842 | 170230 | NPPD | NE | Line - Holt County 345 kV - Antelope 345 kV New Line | Holt County 345 kV Ckt 1 Terminal Upgrade | Economic | 2029-12-31 | 2025-01-01 | 2025-08-19 | 2024 ITP | 5350202 | 2025 | 5483957.05 | 5350202 |  | NTC-C Project Estimate Window |  |  |  |  | Install any necessary terminal equipment at Holt County 345 kV Ck1 substation to support a new line from Holt County 345 kV Ck1 substation to Antelope 345 kV Ckt1 substation with a summer emergency rating of 1792 MVA. | 345
220930 | 94842 | 170231 | NPPD | NE | Line - Holt County 345 kV - Antelope 345 kV New Line | Antelope 345 kV Ckt 1 Terminal Upgrade | Economic | 2029-12-31 | 2025-01-01 | 2025-08-19 | 2024 ITP | 3934947 | 2025 | 4033320.675 | 3934947 |  | NTC-C Project Estimate Window |  |  |  |  | Install any necessary terminal equipment at Antelope 345 kV Ck1 substation to support a new line from Antelope 345 kV Ck1 substation to Holt County 345 kV Ck1 substation with a summer emergency rating of 1792 MVA. | 345
220817 | 94874 | 170296 | SPS | TX | Sub - Conway 115 kV - Kirby 115 kV Terminal Upgrades | Conway 115 kV Terminal Upgrade | Regional Reliability | 2027-12-31 | 2024-11-12 | 2024-12-13 | 2024 ITP |  |  | 0 |  |  | Delay - Mitigation | 524079 | Conway Sub 115 kV |  |  | Install any necessary terminal equipment at Conway 115 kV substation to support a line from Conway 115 kV substation to Kirby 115 kV substation with a summer emergency rating of 197 MVA. | 115
220817 | 94874 | 170297 | SPS | TX | Sub - Conway 115 kV - Kirby 115 kV Terminal Upgrades | Kirby 115 kV Terminal Upgrade | Regional Reliability | 2027-12-31 | 2024-11-12 | 2024-12-13 | 2024 ITP |  |  | 0 | 0 |  | Delay - Mitigation | 524088 | Kirby Switching Station 115 kV |  |  | Install any necessary terminal equipment at Kirby 115 kV substation to support a line from Kirby 115 kV substation to Conway 115 kV substation with a summer emergency rating of 197 MVA. | 115
220809 | 94875 | 170298 | MWE | ND | Line - Sanderson 115 kV - Pioneer 115 kV New Line | Sanderson - Pioneer 115 kV Ckt 1 New Line | Regional Reliability | 2029-12-31 | 2028-01-01 | 2024-12-13 | 2024 ITP | 15173613 | 2025 | 15552953.325 | 10941451.2 |  | Delay - Mitigation | 655794 |  | 659430 |  | Build 10.1-mile 115 kV Ckt 1 line from Sanderson 115 kV substation to Pioneer 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 203 MVA. | 115
220862 | 94875 | 170299 | BEPC | ND | Line - Sanderson 115 kV - Pioneer 115 kV New Line | Sanderson 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2029-12-31 | 2028-01-01 | 2024-12-13 | 2024 ITP | 2457506 | 2025 | 2518943.65 | 2457506 |  | Delay - Mitigation | 655794 |  |  |  | Install any necessary terminal equipment at Sanderson 115 kV substation to support a new line from Sanderson 115 kV substation to Pioneer 115 kV substation with a summer emergency rating of 203 MVA. | 115
220862 | 94875 | 170300 | BEPC | ND | Line - Sanderson 115 kV - Pioneer 115 kV New Line | Pioneer 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2029-12-31 | 2028-01-01 | 2024-12-13 | 2024 ITP | 3357965 | 2025 | 3441914.125 | 3357965 |  | Delay - Mitigation | 659430 |  |  |  | Install any necessary terminal equipment at Pioneer 115 kV substation to support a new line from Pioneer 115 kV substation to Sanderson 115 kV substation with a summer emergency rating of 203 MVA. | 115
220817 | 94880 | 170354 | SPS | NM/ | XFR - Road Runner 345/115 kV #3 | XFR - Roadrunner 345/115 kV #3 | Regional Reliability | 2029-03-15 | 2025-01-01 | 2024-12-13 | 2024 ITP | 23180282 | 2025 | 23759789.05 | 23528000 |  | Delay - Mitigation |  |  |  |  | Install new Ckt 3 345/115 kV transformer at Roadrunner 115 kV substation and expand the 115 kV bus. | 345/115
220817 | 94880 | 170355 | SPS | NM | XFR - Road Runner 345/115 kV #3 | Roadrunner 345/115 kV Transformer Ckt 3 (345 kV) | Regional Reliability | 2029-03-15 | 2025-06-01 | 2024-12-13 | 2024 ITP | 3128845 | 2025 | 3207066.125 | 3180000 |  | Delay - Mitigation |  |  |  |  | Install 345 kV terminal equipment to support a Ckt 3 345/115 kV transformer at Roadrunner 345 kV substation with a summer emergency rating of 435 MVA. | 345/115
220903 | 94881 | 170356 | EDE | MO | Multi - Ozark Dam 161 kV - Forsythe North 161 kV - Ozark South 161 kV Voltage Conversion | Ozark Dam - Forsythe North 161 kV Ckt 1 Voltage Conversion | Regional Reliability | 2028-03-01 | 2024-11-12 | 2025-05-01 | 2024 ITP | 6062305 | 2025 | 6213862.625 | 6062305 |  | Delay - Mitigation | 547474 | SUB 312 - POWERSITE | 547603 | SUB 410 - FORSYTH NORTH | Convert the 69 kV 3.8 mile Ckt 1 line from Ozark Dam 161 kV Ckt 1 substation to Forsythe North 161 kV Ckt 1 and upgrade any necessary terminal equipment to achieve a summer emergency rating of 446 MVA.V 3.8 mile Ckt 1 line from Ozark Dam substation to Forsythe North substation to 161 kV | 161
220903 | 94881 | 170357 | EDE | MO | Multi - Ozark Dam 161 kV - Forsythe North 161 kV - Ozark South 161 kV Voltage Conversion | Forsythe North 161 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2027-07-28 | 2024-11-12 | 2025-05-01 | 2024 ITP | 17072776 | 2025 | 17499595.4 | 17072776 |  | Delay - Mitigation | 547603 | SUB 410 - FORSYTH NORTH |  |  | Install any necessary terminal equipment at Forsythe North 69 kV Ckt 1 substation to convert to 161 kV for the line from Forsythe North 161 kV Ckt 1 substation to Ozark Dam substation Ckt 1 substation to 161 kV with a summer emergency rating of 446 MVA. | 161
220903 | 94881 | 170358 | EDE | MO | Multi - Ozark Dam 161 kV - Forsythe North 161 kV - Ozark South 161 kV Voltage Conversion | Forsythe North - Ozark South 161 kV Ckt 1 Voltage Conversion | Regional Reliability |  | 2024-11-12 | 2025-05-01 | 2024 ITP | 39033209 | 2025 | 40009039.225 | 39033209 |  | In Service | 547603 | SUB 410 - FORSYTH NORTH | 547621 | OZARKS | Convert the 69 kV 24.4 mile Ckt 1 line from Forsythe North substation to Ozark South substation to 161 kV and upgrade any necessary terminal equipment to achieve a summer emergency rating of 446 MVA. | 161
220903 | 94881 | 170359 | EDE | MO | Multi - Ozark Dam 161 kV - Forsythe North 161 kV - Ozark South 161 kV Voltage Conversion | Ozark Dam 161 kV Ckt 1 Terminal Upgrade #1 | Regional Reliability | 2028-03-01 | 2024-11-12 | 2025-05-01 | 2024 ITP | 1048264 | 2025 | 1074470.6 | 1048264 |  | Delay - Mitigation | 547474 | SUB 312 - POWERSITE |  |  | Install any necessary terminal equipment at Ozark Dam 69 kV Ckt 1 substation to convert to 161 kV for the line from Ozark Dam 161 kV Ckt 1 substation to Forsythe North 161 kV Ckt 1 substation with a summer emergency rating of 446 MVA. | 161
220903 | 94881 | 170360 | EDE | MO | Multi - Ozark Dam 161 kV - Forsythe North 161 kV - Ozark South 161 kV Voltage Conversion | Ozark South 161 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2027-07-30 | 2024-11-12 | 2025-05-01 | 2024 ITP | 1994954 | 2025 | 2044827.85 | 1994954 |  | Delay - Mitigation | 547621 | OZARKS |  |  | Install any necessary terminal equipment at Ozark South 69 kV Ckt 1 substation to convert to 161 kV for the line from Ozark South 161 kV Ckt 1 substation to Forsythe North 161 kV Ckt 1 substation with a summer emergency rating of 446 MVA. | 161
220935 | 94911 | 170380 | NPPD | NE | Line - Elm Creek 345 kV - Tobias 345 kV New Line | Tobias 345 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2030-12-01 | 2028-12-01 | 2025-09-09 | 2024 ITP | 11410404 | 2025 | 11695664.1 | 11410404 |  | Delay - Mitigation | 640525 |  |  |  | Install any necessary terminal equipment at Tobias 345 kV substation to support a new line from Tobias 345 kV substation to Elm Creek 345 kV substation with a summer emergency rating of at least 1792 MVA. | 345
220807 | 94908 | 170381 | WFEC | OK | Device - Colbert 138 kV Capacitor | Colbert 138 kV Capacitor | Regional Reliability | 2029-06-30 | 2029-06-01 | 2024-12-13 | 2024 ITP | 1400000 | 2024 | 1470875 | 1400000 |  | Delay - Mitigation Window | 520860 | COLBERT4 138 |  |  | Install 6 MVAR Capacitor at Colbert 138 kV substation | 138
220804 | 94916 | 170384 | AEP | OK | XFR - Tulsa North 345/138 kV | Tulsa North 345/138 kV Transformer Ckt 2 (138 kV) | Economic | 2029-03-01 | 2025-01-01 | 2024-12-13 | 2024 ITP | 11484217 | 2024 | 12065605.4856 | 24926242 |  | Delay - Mitigation | 509817 | TULSA NORTH |  |  | Install new 345/138 transformer at Tulsa North 138 kV substation | 345/138
220804 | 94916 | 170385 | AEP | OK | XFR - Tulsa North 345/138 kV | Tulsa North 345/138 kV Transformer Ckt 2 (345 kV) | Economic | 2029-03-01 | 2025-01-01 | 2024-12-13 | 2024 ITP | 1537869 | 2024 | 1615723.6181 | 6710342 |  | Delay - Mitigation | 509852 | TULSA NORTH 345KV |  |  | Install 345 kV terminal equipment to support 345/138 transformer at Tulsa North 345 kV substation with a summer emergency rating of 675 MVA. | 345/138
220809 | 94914 | 170386 | MWE | ND | Multi - Ellisville - Simpson 115 kV New Line and Zahl 115 kV Cap Bank | Simpson - Ellisville 115 kV Ckt 1 New Line | Regional Reliability | 2026-10-31 | 2025-06-01 | 2024-12-13 | 2024 ITP | 12485000 | 2025 | 12797125 | 12485000 |  | Delay - Mitigation | 655911 |  | 655954 |  | Build a new 15.6-mile 115 kV Ckt 1 line from Simpson substation to Ellisville substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA. | 115
220809 | 94914 | 170387 | MWE | ND | Multi - Ellisville - Simpson 115 kV New Line and Zahl 115 kV Cap Bank | Simpson 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2026-10-31 | 2025-06-01 | 2024-12-13 | 2024 ITP | 875922 | 2025 | 897820.05 | 875922 |  | Delay - Mitigation | 655911 |  |  |  | Install any necessary terminal equipment at Simpson 115 kV substation for the line from Simpson 115 kV substation to Ellisville 115 kV substation with a summer emergency rating of 239 MVA. | 115
220809 | 94914 | 170388 | MWE | ND | Multi - Ellisville - Simpson 115 kV New Line and Zahl 115 kV Cap Bank | Ellisville 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2026-10-31 | 2025-06-01 | 2024-12-13 | 2024 ITP | 875922 | 2025 | 897820.05 | 875922 |  | Delay - Mitigation | 655954 |  |  |  | Install any necessary terminal equipment at Ellisville 115 kV substation for the line from Ellisville 115 kV substation to Simpson 115 kV substation with a summer emergency rating of 239 MVA. | 115
220804 | 94913 | 170389 | AEP | OK | Line - Cherokee Data Center East 138 kV - Tulsa North 138 kV Rebuild | Cherokee Data Center East - Tulsa North 138 kV Ckt 1 Rebuild | Economic | 2027-10-01 | 2025-01-01 | 2024-12-13 | 2024 ITP | 5008393 | 2024 | 5261942.8956 | 5008392.6 |  | Delay - Mitigation | 509817 | TULSA NORTH | 509839 | CHEROKEE DATA CENTER EAST TAP | Rebuild 4.6-mile Ckt 1 line from Tulsa North 138 kV substation to Cherokee Data Center East 138 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 300 MVA. | 138 |  | 4.6
220804 | 94913 | 170390 | AEP | OK | Line - Cherokee Data Center East 138 kV - Tulsa North 138 kV Rebuild | Cherokee Data Center East 138 kV Ckt 1 Terminal Upgrade | Economic | 2027-10-01 | 2025-01-01 | 2024-12-13 | 2024 ITP | 425503 | 2024 | 447044.0894 | 425503 |  | Delay - Mitigation | 509839 | CHEROKEE DATA CENTER EAST TAP |  |  | Install any necessary terminal equipment at Cherokee Data Center East 138 kV substation to support the line from Cherokee Data Center East 138 kV substation to Tulsa North 138 kV substation with a summer emergency rating of 300 MVA. | 138
220903 | 94881 | 170391 | EDE | MO | Multi - Ozark Dam 161 kV - Forsythe North 161 kV - Ozark South 161 kV Voltage Conversion | Forsythe North 161 kV Ckt 1 Terminal Upgrade #1 | Regional Reliability | 2027-07-28 | 2024-11-12 | 2025-05-01 | 2024 ITP | 841998 | 2025 | 863047.95 | 841998 |  | Delay - Mitigation | 547603 | SUB 410 - FORSYTH NORTH |  |  | Install any necessary terminal equipment at Forsythe North 69 kV substation for the line to Ozark South substation Ckt 1 to 161 kV with a summer emergency rating of 446 MVA. | 161
220935 | 94911 | 170392 | NPPD | NE | Line - Elm Creek 345 kV - Tobias 345 kV New Line | Elm Creek - Tobias 345 kV Ckt 1 New Line (NPPD) | Regional Reliability | 2030-12-01 | 2028-12-01 | 2025-09-09 | 2024 ITP | 123647000 | 2025 | 126738175 | 123647000 |  | Delay - Mitigation | 539805 |  | 640525 |  | Build 42.7 miles of the 84-mile 345 kV Ckt 1 line from Elm Creek 345 kV substation to Tobias 345 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of at least 1792 MVA. The NPPD section of transmission line will be solely in the State of Nebraska from Tobias 345 kV substation to an acceptable location on the Nebraska / Kansas state line. | 345
220934 | 94911 | 170393 | ITCGP | KS | Line - Elm Creek 345 kV - Tobias 345 kV New Line | Elm Creek 345 kV Terminal Upgrade #3 | Regional Reliability | 2028-12-01 | 2028-12-01 | 2025-09-09 | 2024 ITP | 8466971 | 2025 | 8678645.275 | 8466971 |  | On Schedule < 4 | 539805 |  |  |  | Install any necessary terminal equipment at Elm Creek 345 kV substation to support a new line from Elm Creek 345 kV substation to Tobias 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220880 | 94910 | 170401 | EDE | MO | Line - Branson Northwest 161 kV - Branson North 161 kV - Reed Spring Rebuild | Branson Northwest - Branson North 161 kV Ckt 1 Rebuild | Economic | 2030-05-01 | 2024-11-12 | 2025-01-23 | 2024 ITP | 1453990 | 2025 | 1490339.75 | 1435990 |  | Delay - Mitigation | 547475 | SUB 331 - BRANSON NORTH | 547488 | SUB 412 - BRANSON NORTHWEST | Rebuild 0.9 mile Ckt 1 line from Branson 161 kV substation to Branson North 161 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 557 MVA. | 161 |  | 0.9
220880 | 94910 | 170402 | EDE | MO | Line - Branson Northwest 161 kV - Branson North 161 kV - Reed Spring Rebuild | Branson Northwest 161 kV Ckt 1 Terminal Upgrade #2 | Economic | 2030-05-01 | 2024-11-12 | 2025-01-23 | 2024 ITP | 513916 | 2025 | 526763.9 | 513916 |  | Delay - Mitigation | 547475 | SUB 331 - BRANSON NORTH |  |  | Install any necessary terminal equipment at Branson Northwest 161 kV Ckt1 substation to support the line from Branson Northwest 161 kV Ckt1 substation to Branson North 161 kV Ckt1 substation with a summer emergency rating of 557 MVA. | 161
220880 | 94910 | 170403 | EDE | MO | Line - Branson Northwest 161 kV - Branson North 161 kV - Reed Spring Rebuild | Branson North 161 kV Ckt 1 Terminal Upgrade #3 | Economic | 2030-05-01 | 2024-11-12 | 2025-01-23 | 2024 ITP | 322964 | 2025 | 331038.1 | 322964 |  | Delay - Mitigation | 547488 | SUB 412 - BRANSON NORTHWEST |  |  | Install any necessary terminal equipment at Branson North 161 kV Ckt1 substation to support the line from Branson North 161 kV Ckt1 substation to Branson Northwest 161 kV Ckt1 substation with a summer emergency rating of 557 MVA. | 161
220809 | 94914 | 170404 | MWE | ND | Multi - Ellisville - Simpson 115 kV New Line and Zahl 115 kV Cap Bank | Zahl 115 kV Capacitor | Regional Reliability | 2026-10-31 | 2025-06-01 | 2024-12-13 | 2024 ITP | 1353394 | 2025 | 1387228.85 | 1353395 |  | Delay - Mitigation | 655955 |  |  |  | Install 15 MVAR capacitor bank at Zahl 115 kV substation | 115
220804 | 94913 | 170405 | AEP | OK | Line - Cherokee Data Center East 138 kV - Tulsa North 138 kV Rebuild | Tulsa North 138 kV Ckt 1 Terminal Upgrade #3 | Economic | 2027-10-01 | 2025-01-01 | 2024-12-13 | 2024 ITP | 425503 | 2024 | 447044.0894 | 425503 |  | Delay - Mitigation | 509817 | TULSA NORTH |  |  | Install any necessary terminal equipment at Tulsa North 138 kV substation to support the line from Tulsa North 138 kV substation to Cherokee Data Center East 138 kV substation with a summer emergency rating of 300 MVA. | 138
220804 | 94815 | 170415 | AEP | OK | XFR - Catoosa 161/138 kV | Catoosa 161/138 kV Transformer (AEP) | Economic | 2027-10-01 | 2025-01-01 | 2024-12-13 | 2024 ITP | 4765714 | 2024 | 5006978.2713 | 4765714 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment to support connecting GRDA's third 161/138 kV transformer at Catoosa 138 kV substation with a summer emergency rating of 188 MVA. | 161/138
220871 | 94815 | 170416 | GRDA | OK | XFR - Catoosa 161/138 kV | Catoosa 161 kV Terminal Equipment | Economic | 2027-04-01 | 2025-01-01 | 2024-12-13 | 2024 ITP | 453000 | 2025 | 464325 | 453000 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment to support 161/138 transformer at Catoosa 161 kV substation with a summer emergency rating of 96 MVA. | 161/138
220914 | 94930 | 170417 | OGE | OK | Multi - Ft Smith - Muskogee 345 kV New Line Muskogee - Talequah 161 kV Rebuild | Muskogee 345 kV Ckt 1 Terminal Upgrade#1 | Economic | 2028-12-31 | 2024-11-12 | 2025-05-13 | 2024 ITP | 4186340 | 2025 | 4290998.5 | 4186340 |  | Delay - Mitigation |  |  |  |  | Install terminal equipment at Muskogee 345 kV substation to support a new line to Ft Smith 345 kV substation Ckt 1 | 345
220914 | 94930 | 170418 | OGE | AR/OK | Multi - Ft Smith - Muskogee 345 kV New Line Muskogee - Talequah 161 kV Rebuild | Ft Smith 345 kV Ckt 2 Terminal Upgrade | Economic | 2028-12-31 | 2024-11-12 | 2025-05-13 | 2024 ITP | 5468530 | 2025 | 5605243.25 | 5468530 |  | Delay - Mitigation |  |  |  |  | Install terminal equipment at Ft Smith 345 kV substation to support a new line from Ft Smith 345 kV substation to Muskogee 345 kV substation with a summer emergency rating of 1793 MVA. | 345
220914 | 94930 | 170419 | OGE | AR/OK | Multi - Ft Smith - Muskogee 345 kV New Line Muskogee - Talequah 161 kV Rebuild | Ft Smith 500/345 kV Transformer Ckt 2 (345 kV) | Economic | 2029-12-31 | 2024-11-12 | 2025-05-13 | 2024 ITP | 17480235 | 2025 | 17917240.875 | 17480235 |  | Delay - Mitigation |  |  |  |  | Install new 500/345 kV transformer at Ft Smith 345 kV substation with a summer emergency rating of 1481 MVA. | 500
220914 | 94930 | 170420 | OGE | AR/OK | Multi - Ft Smith - Muskogee 345 kV New Line Muskogee - Talequah 161 kV Rebuild | Highway 59 Tap - Talequah 345 kV Ckt 1 Voltage Conversion | Economic | 2029-12-31 | 2024-11-12 | 2025-05-13 | 2024 ITP | 109806850 | 2025 | 112552021.25 | 109806850 |  | Delay - Mitigation |  |  |  |  | Convert 42.5 miles of the 161 kV Ckt 1 line from Highway 59 Tap to Talequah to 345 kV with a summer emergency rating of 1793 MVA. | 161
220914 | 94930 | 170421 | OGE | OK | Multi - Ft Smith - Muskogee 345 kV New Line Muskogee - Talequah 161 kV Rebuild | Muskogee - Talequah 161 kV Ckt 1 Rebuild | Economic | 2029-12-31 | 2024-11-12 | 2025-05-13 | 2024 ITP | 9432689 | 2025 | 9668506.225 | 9432689 |  | Delay - Mitigation |  |  |  |  | Rebuild 23 mile 161 kV Ckt 1 line from Muskogee to Talequah as a double circuit and install/upgrade any necessary terminal equipment to achieve a summer emergency rating of 1793 MVA. | 161
220914 | 94930 | 170422 | OGE | OK | Multi - Ft Smith - Muskogee 345 kV New Line Muskogee - Talequah 161 kV Rebuild | Ft Smith - Muskogee 345 kV Ckt 2 New Line | Economic | 2029-12-31 | 2024-11-12 | 2025-05-13 | 2024 ITP | 24685329 | 2025 | 25302462.225 | 24685329 |  | Delay - Mitigation |  |  |  |  | Build a 17.5 mile 345 kV Ckt 2 line from Ft Smith to Highway 59 to connect to the line at Muskogee along the existing 161 kV route through Talequah with a summer emergency rating of 1793 MVA. This portion will be built to 500 kV specifications but operated at 345 kV. | 345
220912 | 94619 | 170428 | EM | MO | XFR - Nashua 345/161 kV Ckt2 | Nashua 345/161 kV Transformer Ckt 2 (161 kV) | Economic | 2026-12-31 | 2024-11-12 | 2025-05-12 | 2024 ITP | 9823936 | 2025 | 10069534.4 | 9823936 |  | Delay - Mitigation |  |  |  |  | Install new 345/161 transformer at Nashua 161 kV substation | 345/161
220912 | 94619 | 170429 | EM | MO | XFR - Nashua 345/161 kV Ckt2 | Nashua 345/161 kV Terminal Equipment (345 kV) | Economic | 2028-06-01 | 2024-11-12 | 2025-05-12 | 2024 ITP | 23991020 | 2025 | 24590795.5 | 21991020 |  | Delay - Mitigation |  |  |  |  | Rebuild Nashua 345 kV Station to a breaker-and-a-half configuration and install any 345 kV terminal equipment to support 345/161 transformer at Nashua 345 kV substation | 345/161
220846 | 94933 | 170432 | EREC | SD | Line - Harrisburg - Lincoln County 115 kV Rebuild | Lincoln County - Harrisburg 115 kV Ckt 1 Rebuild | Regional Reliability | 2026-12-01 | 2027-05-12 | 2024-12-13 | 2024 ITP | 1282500 | 2025 | 1314562.5 | 1282500 |  | On Schedule < 4 |  |  |  |  | Rebuild 3-mile Ckt 1 line from Lincoln County 115 kV substation to Harrisburg 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA. | 115/115 |  | 3
220817 | 94932 | 170433 | SPS | TX | Line -Gaines – Riley - Mid America - Mid-Denver Tap 69 kV Rebuild | Riley Tap - Gaines County 69 kV Ckt 1 Rebuild | Regional Reliability | 2028-05-31 | 2026-11-12 | 2024-12-13 | 2024 ITP | 1723516 | 2025 | 1766603.9 | 1723516 |  | Delay - Mitigation |  |  |  |  | Rebuild 0.4-mile 69 kV Ckt 1 line from Riley 69 kV Tap to Gaines County 69 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 71 MVA | 69/69
220817 | 94932 | 170435 | SPS | TX | Line -Gaines – Riley - Mid America - Mid-Denver Tap 69 kV Rebuild | Gaines County 69 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2028-05-31 | 2026-11-12 | 2024-12-13 | 2024 ITP | 223735 | 2025 | 229328.375 | 223735 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at Gaines County 69 kV substation for the line from Gaines County 69 kV substation to Riley 69 kV tap with a summer emergency rating of 71 MVA. | 69/69
220817 | 94932 | 170436 | SPS | TX | Line -Gaines – Riley - Mid America - Mid-Denver Tap 69 kV Rebuild | Riley - Mid America 69 kV Ckt 1 Rebuild | Regional Reliability | 2028-05-31 | 2026-11-12 | 2024-12-13 | 2024 ITP | 3574324 | 2025 | 3663682.1 | 3574324 |  | Delay - Mitigation |  |  |  |  | Rebuild 3.1-mile 69 kV line from Riley 69 kV substation to Mid America 69 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 71 MVA. | 69/69
220817 | 94932 | 170438 | SPS | TX | Line -Gaines – Riley - Mid America - Mid-Denver Tap 69 kV Rebuild | Mid America 69 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2028-05-31 | 2026-11-12 | 2024-12-13 | 2024 ITP | 1112615 | 2025 | 1140430.375 | 1112615 |  | Delay - Mitigation Window |  |  |  |  | Install any necessary terminal equipment at Mid America 69 kV substation for the line from Mid America 69 kV substation to Riley 69 kV substation with a summer emergency rating of 71 MVA. | 69/69
220817 | 94932 | 170439 | SPS | TX | Line -Gaines – Riley - Mid America - Mid-Denver Tap 69 kV Rebuild | Mid Denver - Mid America 69 kV Ckt 1 Rebuild | Regional Reliability | 2028-05-31 | 2026-11-12 | 2024-12-13 | 2024 ITP | 2137749 | 2025 | 2191192.725 | 2137749 |  | Delay - Mitigation |  |  |  |  | Rebuild 2.6-mile 69 kV Ckt 1 line from Mid Denver 69 kV substation to Mid America 69 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 71 MVA. | 69/69
220817 | 94932 | 170440 | SPS | TX | Line -Gaines – Riley - Mid America - Mid-Denver Tap 69 kV Rebuild | Mid Denver 69 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2028-05-31 | 2026-11-12 | 2024-12-13 | 2024 ITP | 565601 | 2025 | 579741.025 | 565601 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at Mid Denver 69 kV substation for the line from Mid Denver 69 kV substation to Mid American 69 kV substation with a summer emergency rating of 71 MVA. | 69/69
220817 | 94932 | 170441 | SPS | TX | Line -Gaines – Riley - Mid America - Mid-Denver Tap 69 kV Rebuild | Mid America 69 kV Ckt 1 Terminal Upgrade #1 | Regional Reliability | 2028-05-15 | 2026-11-12 | 2024-12-13 | 2024 ITP | 1112614 | 2025 | 1140429.35 | 1112614 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at Mid America 69 kV substation for the line from Mid America 69 kV substation to Mid Denver 69 kV substation with a summer emergency rating of 71 MVA. | 69/69
220846 | 94934 | 170442 | EREC | SD | Device - Hutchinson 115 kV Capacitor | Hutchinson 115 kV Capacitor Bank | Regional Reliability | 2027-02-11 | 2027-11-12 | 2024-12-13 | 2024 ITP | 1037000 | 2025 | 1062925 | 1037000 |  | On Schedule < 4 |  |  |  |  | Install 20 MVAR capacitor bank at Hutchinson 115 kV substation | 115
220817 | 94940 | 170445 | SPS | NM | Line - Maddox - Pearle 115 kV Rebuild | Maddox - Pearle 115 kV Ckt 1 Rebuild | Regional Reliability | 2028-12-15 | 2028-12-01 | 2024-12-13 | 2024 ITP | 11545505 | 2025 | 11834142.625 | 11998253 |  | Delay - Mitigation Window |  |  |  |  | Rebuild 15.3-mile 115 kV Ckt 1 line from Maddox 115 kV substation to Pearle 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA. | 115
220817 | 94940 | 170446 | SPS | NM | Line - Maddox - Pearle 115 kV Rebuild | Maddox 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2028-12-15 | 2028-12-01 | 2024-12-13 | 2024 ITP | 204901 | 2025 | 210023.525 | 220656 |  | Delay - Mitigation Window |  |  |  |  | Install any necessary terminal equipment at Maddox 115 kV substation for the line from Maddox 115 kV substation to Pearle 115 kV substation to meet a summer emergency rating of 239 MVA. | 115
220817 | 94940 | 170447 | SPS | NM | Line - Maddox - Pearle 115 kV Rebuild | Pearle 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2028-12-31 | 2028-12-01 | 2024-12-13 | 2024 ITP | 274950 | 2025 | 281823.75 | 296091 |  | Delay - Mitigation Window |  |  |  |  | Install any necessary terminal equipment at Pearle 115 kV substation for the line from Pearle 115 kV substation to Maddox 115 kV substation to meet a summer emergency rating of 239 MVA | 115
220817 | 94941 | 170448 | SPS | NM | XFR - Moore County 230/115 kV Ckt 2 Transformer | Moore County 230/115 kV Transformer Ckt 2 | Regional Reliability | 2029-05-15 | 2025-06-01 | 2024-12-13 | 2024 ITP |  |  | 0 | 30028000 |  | Delay - Mitigation |  |  |  |  | Install new 230/115 transformer at Moore County 115 kV substation | 115
220846 | 94942 | 170449 | EREC | SD | Device - Plankinton 115 kV Capacitor | Plankinton 69 kV Capacitor Bank | Regional Reliability | 2027-11-01 | 2027-11-12 | 2024-12-13 | 2024 ITP | 409000 | 2025 | 419225 | 409000 |  | On Schedule < 4 |  |  |  |  | Install 7.5 MVAR capacitor bank at Plankinton 69 kV substation. | 69
220973 | 94763 | 170454 | BEPC | NA | Line - Logan 230 kV - Magic City 230 kV New Line | Logan 115 kV Ckt 1 Terminal Upgrade | Regional Reliability |  | 2032-12-01 | 2025-11-20 | 2024 ITP |  |  | 0 | 2800000 |  | Identified |  |  |  |  | Install any necessary terminal equipment at Logan 115 kV substation to support in/out of Nelson to Mallard 115 kV line | 115
220904 | 94951 | 170455 | EREC | SD | Multi - Kingsbury County 115 Voltage Conversion | Oldham - Lake County 115 kV Ckt 1 New Line | Regional Reliability | 2027-05-07 | 2025-06-01 | 2025-06-19 | 2024 ITP | 9185000 | 2025 | 9414625 | 9185000 |  | NTC - Commitment Window |  |  |  |  | Build a 23-mile 115 kV Ckt 1 line from Oldham 115 kV MOS to Lake County 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 193 MVA. | 115
220904 | 94951 | 170457 | EREC | SD | Multi - Kingsbury County 115 Voltage Conversion | Lake County 115 kV Ckt 1 Terminal Upgrade #2 | Regional Reliability | 2025-09-14 | 2025-06-01 | 2025-06-19 | 2024 ITP | 750000 | 2025 | 750000 | 750000 |  | NTC - Commitment Window |  |  |  |  | Lake County 115 kV Ckt 1 Terminal Upgrade #2 Network Upgrade Description: Install any necessary terminal equipment at Lake County 115 kV substation to support the new line from Lake County 115 kV substation to Oldham 115 kV MOS to achieve a summer emergency rating of 193 MVA. | 115
220904 | 94951 | 170458 | EREC | SD | Multi - Kingsbury County 115 Voltage Conversion | Oldham 115 kV New Motor Operated Switch (MOS) Substation | Regional Reliability | 2026-10-16 | 2025-06-01 | 2025-06-19 | 2024 ITP | 165000 | 2025 | 169125 | 165000 |  | NTC - Commitment Window |  |  |  |  | Install new 115-kV three-way motor operated switch and any necessary terminal equipment at Oldham 115 kV MOS for the lines from Oldham 115 kV MOS to Lake County115 kV substation and from Oldham 115 kV MOS to Kingsbury County 115 kV substation with a summer emergency rating of 193 MVA. | 115
220904 | 94951 | 170459 | EREC | SD | Multi - Kingsbury County 115 Voltage Conversion | Oldham - Kingsbury County 115 kV Ckt 1 New Line | Regional Reliability | 2026-10-30 | 2025-06-01 | 2025-06-19 | 2024 ITP | 7321000 | 2025 | 7504025 | 7321000 |  | NTC - Commitment Window |  |  |  |  | Build a 18-mile 115 kV Ckt 1 line from Oldham 115 kV MOS to Kingsbury County 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 193 MVA. | 115
220904 | 94951 | 170467 | EREC | SD | Multi - Kingsbury County 115 Voltage Conversion | Kingsbury County 115 kV New Substation | Regional Reliability | 2026-03-20 | 2025-06-01 | 2025-06-19 | 2024 ITP | 7303000 | 2025 | 7485575 | 7303000 |  | NTC - Commitment Window |  |  |  |  | Install 115 kV new substation at Kingsbury County. | 115
220904 | 94951 | 170468 | EREC | SD | Multi - Kingsbury County 115 Voltage Conversion | Lake Preston - Kingsbury County 115 kV Ckt 1 New Line | Regional Reliability | 2026-04-17 | 2025-06-01 | 2025-06-19 | 2024 ITP | 3406000 | 2025 | 3491150 | 3406000 |  | NTC - Commitment Window |  |  |  |  | Build a 5-mile 115 kV Ckt 1 line from Lake Preston 115 kV Ckt 1 line from Lake Preston 115 kV MOS to Kingsbury County 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 193 MVA. | 115
220904 | 94951 | 170470 | EREC | SD | Multi - Kingsbury County 115 Voltage Conversion | Lake Preston 115 kV New Motor Operated Switch (MOS) | Regional Reliability | 2026-04-17 | 2025-06-01 | 2025-06-19 | 2024 ITP | 165000 | 2025 | 169125 | 165000 |  | NTC - Commitment Window |  |  |  |  | Install new 115 kV three-way motor-operated switch and necessary terminal equipment at Lake Preston 115 kV MOS for the lines from Lake Preston 115 kV MOS to Kingsbury County 115 kV substation and from Lake Preston 115 kV MOS to DeSmet 115 kV MOS with a summer emergency rating of at least 193 MVA. All line terminal elements and conductor to meet or exceed 193/193/193/193 (SN/SE/WN/WE) MVA rating | 115
220904 | 94951 | 170474 | EREC | SD | Multi - Kingsbury County 115 Voltage Conversion | Lake Preston - DeSmet 115 kV Ckt 1 New Line | Regional Reliability | 2026-10-16 | 2025-06-01 | 2025-06-19 | 2024 ITP | 6353000 | 2025 | 6511825 | 6353000 |  | NTC - Commitment Window |  |  |  |  | Build a 16-mile 115 kV Ckt 1 line from Lake Preston 115 kV MOS to DeSmet 115 kV MOS and upgrade any necessary terminal equipment to achieve a summer emergency rating of 193 MVA. | 115
220904 | 94951 | 170478 | EREC | SD | Multi - Kingsbury County 115 Voltage Conversion | DeSmet 115 kV New Motor Operated Switch (MOS) | Regional Reliability | 2026-10-16 | 2025-06-01 | 2025-06-19 | 2024 ITP | 165000 | 2025 | 169125 | 165000 |  | NTC - Commitment Window |  |  |  |  | Install new115 kV three-way motor-operated switch and necessary terminal equipment at DeSmet 115 kV MOS for the lines from DeSmet 115 kV MOS to Lake Preston 115 kV and from DeSmet 115 kV MOS to Manchester 115 kV substation with a summer emergency rating of at least 193 MVA. | 115
220904 | 94951 | 170479 | EREC | SD | Multi - Kingsbury County 115 Voltage Conversion | Manchester - DeSmet 115 kV Ckt 1 New Line | Regional Reliability | 2026-05-01 | 2025-06-01 | 2025-06-19 | 2024 ITP | 5718000 | 2025 | 5860950 | 5718000 |  | NTC - Commitment Window |  |  |  |  | Build a 12.5-mile 115 kV Ckt 1 line from Manchester 115 kV substation to DeSmet 115 kV MOS and upgrade any necessary terminal equipment to achieve a summer emergency rating of 239 MVA. | 115
220904 | 94951 | 170482 | EREC | SD | Multi - Kingsbury County 115 Voltage Conversion | Manchester 115 kV New Substation | Regional Reliability | 2026-04-03 | 2025-06-01 | 2025-06-19 | 2024 ITP | 5206000 | 2025 | 5336150 | 5206000 |  | NTC - Commitment Window |  |  |  |  | Install 115 kV new substation at Manchester | 115
220904 | 94951 | 170483 | EREC | SD | Multi - Kingsbury County 115 Voltage Conversion | Carpenter 115 kV New Substation | Regional Reliability | 2027-12-31 | 2025-06-01 | 2025-06-19 | 2024 ITP | 2588000 | 2025 | 2652700 | 2588000 |  | NTC - Commitment Window |  |  |  |  | Install 115 kV new substation at Carpenter | 115
220904 | 94951 | 170484 | EREC | SD | Multi - Kingsbury County 115 Voltage Conversion | Manchester - Carpenter 115 kV Ckt 1 New Line | Regional Reliability | 2026-04-03 | 2025-06-01 | 2025-06-19 | 2024 ITP | 13326000 | 2025 | 13659150 | 13326000 |  | NTC - Commitment Window |  |  |  |  | Build a 31.8-mile 115 kV Ckt 1 line from Manchester 115 kV substation to Carpenter 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 193 MVA. | 115
220904 | 94951 | 170487 | EREC | SD | Multi - Kingsbury County 115 Voltage Conversion | Arlington - Kingsbury County 115 kV Ckt 1 New Line | Regional Reliability | 2026-04-10 | 2025-06-01 | 2025-06-19 | 2024 ITP | 10003000 | 2025 | 10253075 | 10003000 |  | NTC - Commitment Window |  |  |  |  | Build a 25-mile 115 kV Ckt 1 line from Arlington 115 kV substation to Kingsbury County 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 193 MVA. | 115
220904 | 94951 | 170488 | EREC | SD | Multi - Kingsbury County 115 Voltage Conversion | Arlington 115 kV Breakers | Regional Reliability | 2025-10-31 | 2025-06-01 | 2025-06-19 | 2024 ITP | 3846000 | 2025 | 3846000 | 3846000 |  | NTC - Commitment Window |  |  |  |  | Install circuit breakers at the Arlington 115 kV substation and install any necessary terminal equipment at Arlington 115 kV substation to support the new line from Arlington 115 kV substation to Kingsbury County 115 kV substation to achieve a summer emergency rating of 193 MVA. | 115
220904 | 94951 | 170489 | EREC | SD | Multi - Kingsbury County 115 Voltage Conversion | Kingsbury County 115 kV Capacitor Bank | Regional Reliability | 2026-03-20 | 2025-06-01 | 2025-06-19 | 2024 ITP | 855000 | 2025 | 876375 | 855000 |  | NTC - Commitment Window |  |  |  |  | Install 15 MVAR capacitor bank at Kingsbury County 115 kV substation | 115
220904 | 94951 | 170490 | EREC | SD | Multi - Kingsbury County 115 Voltage Conversion | Carpenter 230/115 kV Transformer Ckt 1 (115 kV) | Regional Reliability | 2027-12-31 | 2025-06-01 | 2025-06-19 | 2024 ITP | 4317000 | 2025 | 4424925 | 4317000 |  | NTC - Commitment Window |  |  |  |  | Install new 230/115 transformer at Carpenter 115 kV substation | 115
220904 | 94951 | 170491 | EREC | SD | Multi - Kingsbury County 115 Voltage Conversion | Carpenter 230/115 kV Transformer Ckt 1 (230 kV) | Regional Reliability | 2027-12-31 | 2025-06-01 | 2025-06-19 | 2024 ITP | 3333000 | 2025 | 3416325 | 3333000 |  | NTC - Commitment Window |  |  |  |  | Install 230 kV terminal equipment to support 230/115 kV transformer at Carpenter 230 kV substation | 115
| 94955 | 170493 | MWE | na | Rebuild the MONT -MW7 to STRNDAHL-MW7 115kV Line 1 | Rebuild the MONT -MW7 to STRNDAHL-MW7 115kV Line 1 | Generation Interconnection | 2027-12-31 |  |  | GI STUDIES |  |  | 0 | 17281000 |  | In Service |  |  |  |  | Rebuild the existing MONT -MW7 to STRNDAHL-MW7 115 kV line 1 (11.97 miles) to a standard rating of 220 MVA | 115 |  | 11
| 94956 | 170494 | MWE | NA// | Build new STRNDAHL-MW7 to BLKTLTAP-MW7 115kV Line 1 | Build new STRNDAHL-MW7 to BLKTLTAP-MW7 115kV Line 1 | Generation Interconnection | 2027-12-31 |  |  | GI STUDIES |  |  | 0 | 16128750 |  | In Service |  |  |  |  | Build a new STRNDAHL-MW7 to BLKTLTAP-MW7 115 kV line 1 (15 miles) to a standard rating of 239 MVA | 115 | 15
| 94959 | 170499 | WAPA | NA | Rebuild the circuit from WAPA Denison to the new 69 kV tap station | Rebuild the circuit from WAPA Denison to the new 69 kV tap station (WAPA) | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 785000 |  | Identified |  |  |  |  | Build a new DENISON8 to NEWTAP 69 kV line 1 (0.82 miles) to a standard rating of 125 MVA
| 94960 | 170500 | SEPC |  | GBENDTP3 to SEWARD 3 115kV Line 1 Terminal Upgrade | GBENDTP3 to SEWARD 3 115kV Line 1 Terminal Upgrade | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 240000 |  | In Service |  |  |  |  | Rebuild the existing GBENDTP3 to SEWARD 3 115 kV line 1 (13.1 miles) to a standard rating of 109 MVA | 115 |  | 13.1
| 94961 | 170501 | SEPC |  | Rebuild the 24-FREY3 to N-GBEND3 115kV Line 1 | Rebuild the 24-FREY3 to N-GBEND3 115kV Line 1 | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 4282715 |  | In Service |  |  |  |  | Rebuild the existing 24-FREY3 to N-GBEND3 115 kV line 1 (5.1 miles) to a standard rating of 185 MVA
| 94962 | 170502 | SEPC |  | Rebuild the 24-FREY3 to 2ND-KS 3 115kV Line 1 | Rebuild the 24-FREY3 to 2ND-KS 3 115kV Line 1 | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 1528342 |  | In Service |  |  |  |  | Rebuild the existing 24-FREY3 to 2ND-KS 3 115 kV line 1 (1.82 miles) to a standard rating of 185 MVA | 115 |  | -1
| 94963 | 170503 | SEPC |  | Rebuild the GBENDTP3 to 2ND-KS 3 115kV Line 1 | Rebuild the GBENDTP3 to 2ND-KS 3 115kV Line 1 | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 2435269 |  | In Service |  |  |  |  | Rebuild the existing GBENDTP3 to 2ND-KS 3 115 kV line 1 (3.79 miles) to a standard rating of 175 MVA | 115 |  | 3.79
| 94964 | 170504 | SEPC |  | Rebuild the GRTBEND3 to N-GBEND3 115kV Line 1 | Rebuild the GRTBEND3 to N-GBEND3 115kV Line 1 | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 3006298 |  | In Service |  |  |  |  | Rebuild the existing GRTBEND3 to N-GBEND3 115 kV line 1 (3.58 miles) to a standard rating of 180 MVA | 115 |  | 3.58
| 94965 | 170505 | NPPD | na | Rebuild Columbus SE to G19-039-TAP 115 kV | Rebuild Columbus SE to G19-039-TAP 115 kV | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 4000000 |  | Identified |  |  |  |  | Rebuild the existing COL.SE 7 to G19-039-TAP 115 kV line 1 (6.76 miles) to a standard rating of 180 MVA
| 94968 | 170508 | NPPD | na/ | Build Second 345-115kV transformer at Antelope | Build Second 345-115kV transformer at Antelope | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 33500000 |  | Identified |  |  |  |  | Build a new ANTELOPE 3 to ANTELOPE 7 345-115 kV transformer 2 with a rating of 417 MVA
| 94969 | 170509 | AEP | na | Rebuild SWEETWT6 to CHISHOLM6 230 kV Line 1 | Rebuild SWEETWT6 to CHISHOLM6 230 kV Line 1 | Generation Interconnection |  |  |  | GI STUDIES |  |  | 0 | 25920000 |  | Identified |  |  |  |  | Rebuild the SWEETWT6 to CHISHOLM6 230kV line CKT1 (11.15 miles) to a minimum rating of 380 MVA
220905 | 94723 | 170516 | BEPC | ND | Multi - Logan 345 kV - Leland Olds 345 kV Voltage Conv and Logan 345 kV - Finstad 345 kV New Line | Logan 230 kV Terminal Upgrade | Regional Reliability | 2032-11-30 | 2032-12-01 | 2025-05-06 | 2024 ITP | 6588882 | 2025 | 6753604.05 | 6588882 |  | NTC - Commitment Window |  |  |  |  | Install 230 kV terminal equipment at the Logan 230 kV substation to accommodate the two terminals for the 345/230 kV transformers. This also includes the line or bus segments to connect the 345/230 kV transformers from the new Logan 345 to the existing Logan 230 kV substation
220904 | 94567 | 170517 | EREC | SD | Multi - Marion Area 115 kV Voltage Conversion Reconfig | Dolton Manual – Marion Industrial 115 kV Ckt 1 Voltage Conversion | Regional Reliability | 2026-10-01 | 2027-11-12 | 2025-06-19 | 2024 ITP |  |  | 0 | 0 |  | On Schedule < 4 |  |  |  |  | Convert 6.9-mile 69kV Ckt 1 line from Dolton Manual to Marion Industrial to 115 kV
220923 | 94571 | 170518 | WAPA | SD | Multi - Sioux Falls 115 kV System Reconfig | Beresford 115 kV Ckt 1 Terminal Upgrade | Regional Reliability | 2028-06-30 | 2025-06-01 | 2025-07-21 | 2024 ITP | 145000 | 2025 | 148625 | 145000 |  | NTC - Commitment Window |  |  |  |  | Install any necessary terminal equipment at the Beresford 115 kV substation to support tapping the existing line from Beresford 115 kV substation to Sioux Falls 115 kV substation for the new tap station Lincoln County 115 kV (owned by EREPC) with a summer emergency rating of 120 MVA. | 115
220932 | 94800 | 170519 | WAPA | SD | Multi - Belfield 345 kV - Maurine 345 kV | Belfield 2 345/230 kV Transformer Ckt 1 (230 kV) | Economic | 2034-11-01 | 2025-01-01 | 2025-08-19 | 2024 ITP | 10000000 | 2025 | 10250000 | 10000000 |  | Delay - Mitigation |  |  |  |  | Install a new 345/230 kV transformer at the new Belfield 2 345 kV substation or replace existing parallel transformers at existing Belfield substation. | 345
220932 | 94800 | 170520 | WAPA | SD | Multi - Belfield 345 kV - Maurine 345 kV | Belfield 230 kV Terminal Equipment | Economic | 2034-11-01 | 2025-01-01 | 2025-08-19 | 2024 ITP | 100000 | 2025 | 102500 | 100000 |  | Delay - Mitigation |  |  |  |  | Install 230 kV terminal equipment to support 345/230 kV transformers at the Belfield 345 kV substation tied to the 230 kV terminal equipment at the existing Belfield substation. | 345
220932 | 94800 | 170524 | WAPA | SD | Multi - Belfield 345 kV - Maurine 345 kV | Maurine 230 kV Terminal Upgrade | Economic | 2032-12-31 | 2025-01-01 | 2025-08-19 | 2024 ITP | 3709672 | 2025 | 3802413.8 | 3709672 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at Maurine substation to support a new line from Maurine 230 kV substation to Maurine 2 230 kV substation with a summer emergency rating of 1792 MVA. | 345
220932 | 94800 | 170525 | WAPA | SD | Multi - Belfield 345 kV - Maurine 345 kV | Maurine 2 230 kV Terminal Upgrade | Economic | 2034-10-01 | 2025-01-01 | 2025-08-19 | 2024 ITP | 2774719 | 2025 | 2844086.975 | 2774719 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at Maurine 2 230 kV substation to support a new line from Maurine 230 kV substation to Maurine 2 230 kV substation with a summer emergency rating of 1792 MVA. | 345
220932 | 94800 | 170526 | WAPA | SD | Multi - Belfield 345 kV - Maurine 345 kV | Maurine – Maurine 2 230 kV Ckt 1 New Line | Economic | 2034-10-01 | 2025-01-01 | 2025-08-19 | 2024 ITP | 6000000 | 2025 | 6150000 | 6000000 |  | Delay - Mitigation |  |  |  |  | Build a 1-mile 230 kV Ckt 1 new line from Maurine 230 kV substation to Maurine 2 230 kV substation and install any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA. | 345
220932 | 94800 | 170527 | WAPA | SD | Multi - Belfield 345 kV - Maurine 345 kV | Belfield 345 kV Terminal Equipment | Economic | 2034-11-01 | 2025-01-01 | 2025-08-19 | 2024 ITP | 400000 | 2025 | 410000 | 400000 |  | Delay - Mitigation |  |  |  |  | Install 345 kV terminal equipment to support 345/230 kV transformers at the Belfield 345 kV substation tied to the 230 kV terminal equipment at the existing Belfield substation. | 345
220929 | 94986 | 170529 | WAPA | SD | Multi - New Underwood 345 kV - Laramie River 345 kV | New Underwood 2 230 kV Ckt 1 Terminal Upgrade | Economic | 2034-10-01 | 2025-01-01 | 2025-08-13 | 2024 ITP | 7956029 | 2025 | 8154929.725 | 7956029 |  | NTC - Commitment Window |  |  |  |  | Install any necessary terminal equipment at New Underwood 2 substation to support a new line from New Underwood 2 substation to tie into an existing 230 kV substation in the vicinity with a summer emergency rating of 675 MVA. | 230
220872 | 30823 | 170530 | WAPA | SD | INACTIVES | Existing 230 kV substation Ckt 1 Terminal Upgrade | Economic |  | 2025-01-01 | 2024-12-13 | 2024 ITP |  |  | 0 | 0 |  | NTC-C Project Estimate Window |  |  |  |  | Install any necessary terminal equipment at an existing 230 kV substation to support a new line from New Underwood 2 substation to tie into an existing 230 kV substation in the vicinity with a summer emergency rating of 675 MVA. | 230
220872 | 30823 | 170531 | WAPA | SD | INACTIVES | New Underwood 2 to an existing substation 230 kV Ckt 1 New Line | Economic |  | 2025-01-01 | 2024-12-13 | 2024 ITP |  |  | 0 | 0 |  | NTC-C Project Estimate Window |  |  |  |  | Build a 1-mile 230 kV Ckt 1 new line from New Underwood 2 substation 230 kV substation to tie into an existing 230 kV substation in the vicinity with a summer emergency rating of 675 MVA. | 230
220873 | 94987 | 170533 | OPPD | KS | Line - Raun 345 kV - S3452 345 kV New Line (JTIQ) | Raun - S3452 345 kV Ckt 1 New Line | Regional Reliability | 2032-11-01 | 2026-06-01 | 2024-12-18 | 2024 JTIQ (DOE) | 305006506 | 2025 | 312631668.65 | 305006506 |  | Delay - Mitigation |  |  |  |  | Build approximately 72 mile 345 kV Ckt 1 line from S3452 345 kV substation to OPPD/MEC demarcation point and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA. | 345
220873 | 94987 | 170535 | OPPD | KS | Line - Raun 345 kV - S3452 345 kV New Line (JTIQ) | S3452 345 kV New Substation | Regional Reliability | 2032-11-01 | 2026-06-01 | 2024-12-18 | 2024 JTIQ (DOE) |  |  | 0 | 60718897 |  | Delay - Mitigation |  |  |  |  | Install 345 kV new substation at S3452 | 345
220874 | 94988 | 170536 | EKC | KS | Line - Auburn 345 kV - Hoyt 345 kV New Line (JTIQ) | S3771 - Hoyt 345 kV Ckt 1 New Line (EKC) | Regional Reliability | 2032-09-01 | 2026-06-01 | 2024-12-18 | 2024 JTIQ (DOE) | 162439000 | 2025 | 166499975 | 162439000 |  | Delay - Mitigation |  |  |  |  | Build approximately 55 mile 345 kV Ckt 1 line from S3771 345 kV substation to Hoyt 345 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA. | 345
220874 | 94988 | 170538 | EKC | KS | Line - Auburn 345 kV - Hoyt 345 kV New Line (JTIQ) | Hoyt 345 kV Terminal Upgrade | Regional Reliability | 2032-09-01 | 2026-06-01 | 2024-12-18 | 2024 JTIQ (DOE) | 3320000 | 2025 | 3403000 | 3320000 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at Hoyt 345 kV substation to support a new line from S3771 345 kV substation to Hoyt 345 kV substation with a summer emergency rating of 1792 MVA. | 345
220875 | 94989 | 170539 | EMW | KS | Bus - Sidley 345 kV Bus Reconfiguration (JTIQ) | Sibley 345 kV Bus Reconfiguration | Regional Reliability | 2032-09-01 | 2026-06-01 | 2024-12-18 | 2024 JTIQ (DOE) | 43686000 | 2025 | 44778150 | 43686000 |  | Delay - Mitigation |  |  |  |  | Sibley 345 kV Bus Reconfiguration | 345
220893 | 94988 | 170542 | NPPD | NE | Line - Auburn 345 kV - Hoyt 345 kV New Line (JTIQ) | Cooper - Moore 345 kV Line Tap | Regional Reliability | 2032-10-15 | 2026-06-01 | 2025-02-20 | 2024 JTIQ (DOE) | 13717595 | 2025 | 14060534.875 | 13717595 |  | Delay - Mitigation |  |  |  |  | Tap the existing Cooper - Moore 345 kV line at Auburn | 345
220885 | 94989 | 170543 | EM | KS | Bus - Sidley 345 kV Bus Reconfiguration (JTIQ) | Hawthorn 345kV Terminal Equipment | Regional Reliability | 2032-09-01 | 2026-06-01 | 2025-01-14 | 2024 JTIQ (DOE) | 1688000 | 2025 | 1730200 | 1688000 |  | NTC - Commitment Window |  |  |  |  | Install terminal equipment at Hawthorn and re-terminate Hawthorn - Sibley 345 kV line. | 345
220914 | 94930 | 170546 | OGE | OK | Multi - Ft Smith - Muskogee 345 kV New Line Muskogee - Talequah 161 kV Rebuild | Muskogee - Talequah 345 kV Ckt 1 Rebuild | Regional Reliability | 2028-12-31 | 2024-11-12 | 2025-05-13 | 2024 ITP | 80871234 | 2025 | 82893014.85 | 80871234 |  | Delay - Mitigation |  |  |  |  | Rebuild 23 miles 345 kV Ckt 1 line from Muskogee to Talequah as a double circuit and install/upgrade any necessary terminal equipment to achieve a summer emergency rating of 1793 MVA. | 345
220791 | 94134 | 170552 | EKC | KS | Multi - Atlantic- Craig - West Gardener 345/115 kV | Atlantic – Pacific #1 115 kV New Line | Regional Reliability | 2025-07-18 | 2027-06-01 | 2024-11-04 | 2023 ITP | 11216179 | 2024 | 11496583.475 | 13362585 |  | Complete |  |  |  |  | Build a 4.2-mile 115 kV new west line from Atlantic 115 kV substation to Pacific 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA. | 115
220791 | 94134 | 170553 | EKC | KS | Multi - Atlantic- Craig - West Gardener 345/115 kV | Atlantic – Pacific #2 115 kV New Line | Regional Reliability | 2025-04-02 | 2027-06-01 | 2024-11-04 | 2023 ITP | 6609874 | 2024 | 6775120.85 | 6072068 |  | Complete |  |  |  |  | Build a 1.7-mile 115 kV new east line from Atlantic 115 kV substation to Atlantic 115 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 435 MVA. | 115
220914 | 94930 | 170555 | OGE | AR/OK | Multi - Ft Smith - Muskogee 345 kV New Line Muskogee - Talequah 161 kV Rebuild | Ft Smith 500/345 kV Transformer Ckt 2 Terminal Equipment (345 kV) | Regional Reliability | 2028-12-31 | 2024-11-12 | 2025-05-13 | 2024 ITP | 3467800 | 2025 | 3554495 | 3467800 |  | Delay - Mitigation |  |  |  |  | Install terminal equipment for new 500/345 transformer at Ft Smith 345 kV substation with a summer emergency rating of 1481 MVA. | 345
220914 | 94930 | 170556 | OGE | AR/OK | Multi - Ft Smith - Muskogee 345 kV New Line Muskogee - Talequah 161 kV Rebuild | Ft Smith 500/345 kV Transformer Ckt 2 Terminal Equipment (500 kV) | Regional Reliability | 2030-12-31 | 2024-11-12 | 2025-05-13 | 2024 ITP | 30718812 | 2025 | 31486782.3 | 30718812 |  | Delay - Mitigation |  |  |  |  | Install terminal equipment for new 500/345 transformer at Ft Smith 500 kV substation with a summer emergency rating of 1481 MVA. | 345
220936 | 94805 | 170558 | SPS | NM | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Phantom 765/345 kV Transformer Ckt 2 (345 kV) | Regional Reliability | 2031-05-15 | 2025-04-01 | 2025-09-09 | 2024 ITP | 62235103 |  | 0 | 62235103 |  | NTC - Commitment Window |  |  |  |  | Install new 765/345 transformer at Phantom 345 kV substation | 765/345
220936 | 94805 | 170559 | SPS | TX | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Potter County 765/345 kV Transformer Ckt 2 (345 kV) | Regional Reliability | 2031-05-15 | 2025-04-01 | 2025-09-09 | 2024 ITP | 62235103 |  | 0 | 62235103 |  | NTC - Commitment Window |  |  |  |  | Install new 765/345 transformer at Potter County 345 kV substation | 765/345
220936 | 94805 | 170560 | SPS | NM | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Crossroads 765/345 kV Transformer Ckt 2 (345 kV) | Regional Reliability | 2031-05-15 | 2025-04-01 | 2025-09-09 | 2024 ITP | 63058628 |  | 0 | 63058628 |  | NTC - Commitment Window |  |  |  |  | Install new 765/345 transformer at Crossroads 345 kV substation | 765/345
220936 | 94805 | 170561 | SPS | NM | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Phantom 765/345 kV Transformer Ckt 3 (345 kV) | Regional Reliability | 2031-05-15 | 2025-04-01 | 2025-09-09 | 2024 ITP | 62235103 |  | 0 | 62235103 |  | NTC - Commitment Window |  |  |  |  | Install new 765/345 transformer at Phantom 345 kV substation | 765/345
220936 | 94805 | 170562 | SPS | TX | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Potter County 765/345 kV Transformer Ckt 3 (345 kV) | Regional Reliability | 2031-05-15 | 2025-04-01 | 2025-09-09 | 2024 ITP | 62235103 |  | 0 | 62235103 |  | NTC - Commitment Window |  |  |  |  | Install new 765/345 transformer at Potter County 345 kV substation | 765/345
220936 | 94805 | 170563 | SPS | NM | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Crossroads 765/345 kV Transformer Ckt 3 (345 kV) | Regional Reliability | 2031-05-15 | 2025-04-01 | 2025-09-09 | 2024 ITP | 63058628 |  | 0 | 63058628 |  | NTC - Commitment Window |  |  |  |  | Install new 765/345 transformer at Crossroads 345 kV substation | 765/345
220936 | 94805 | 170564 | SPS | NM | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Crossroads 765 kV Reactor 1 | Regional Reliability | 2031-05-15 | 2025-04-01 | 2025-09-09 | 2024 ITP | 37244896 |  | 0 | 37244896 |  | NTC - Commitment Window |  |  |  |  | Install at least -150 MVAR reactor at Crossroads 765 kV line to Potter County | 765/765
220940 | 94811 | 170565 | SEPC | KS | Line - Holcomb - Sidney 345 kV Ckt 1 New Line | Holcomb - Sidney 345 kV Ckt 1 New Line (SEPC) | Regional Reliability | 2030-10-01 | 2025-03-21 | 2025-09-23 | 2024 ITP | 500116820 |  | 0 | 540717664 |  | NTC - Commitment Window |  |  |  |  | Build a new 300-mile 345 kV Ckt 1 line from Holcomb 345 kV substation to Sidney 345 substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA. | 345
220938 | 94615 | 170566 | EKC | KS | Line - Buffalo Flats 345 kV - Delaware 345 kV New Line | Buffalo Flats - Delaware 345 kV Ckt 1 New Line (EKC) | Regional Reliability | 2029-12-31 | 2025-12-01 | 2025-09-18 | 2024 ITP | 363099787 | 2025 | 372177281.675 | 430182934 |  | Delay - Mitigation |  |  |  |  | Build Evergy Kansas Central's portion of the 154.6 mile 345 kV Ckt 1 new line from Buffalo Flats 345 kV substation to Delaware 345 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA. | 345
220947 | 94929 | 170567 | EDE | MO | Line - Delaware 345 kV - Monett 345 kV Ckt 1 New Line | Delaware - Monett 345 kV Ckt 1 New Line (EDE) | Regional Reliability |  | 2025-12-01 | 2025-11-04 | 2024 ITP | 163676482 | 2025 | 167768394.05 | 163676482 |  | NTC-C Project Estimate Window |  |  |  |  | Build a 114.5 mile 345 kV Ckt 1 line from Delaware 345 kV substation to Monett 345 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA. | 345 | 114.5
220893 | 94987 | 170569 | NPPD | NE | Line - Raun 345 kV - S3452 345 kV New Line (JTIQ) | Tekamah 345 kV Terminal Upgrade | Regional Reliability | 2032-01-15 | 2026-06-01 | 2025-02-20 | 2024 JTIQ (DOE) | 2570308 | 2025 | 2634565.7 | 2570308 |  | Delay - Mitigation |  |  |  |  | Install any necessary terminal equipment at Tekamah 345 kV substation to support a new line from Raun 345 kV substation to Tekamah 345 kV substation with a summer emergency rating of 558 MVA. | 345
220941 | 94811 | 170611 | TSGT | KS | Line - Holcomb - Sidney 345 kV Ckt 1 New Line | Holcomb - Sidney 345 kV Ckt 1 New Line (TSGT) | Regional Reliability | 2030-12-19 | 2025-03-21 | 2025-09-23 | 2024 ITP | 515000000 |  | 0 | 515000000 |  | NTC - Commitment Window |  |  |  |  | Build a new 300 mile 345 kV Ckt 1 line from CO/KS stateline (midpoint) to Sidney 345 kV substation and upgrade any necessary terminal equipment to achieve a summer emergency rating of 1792 MVA.
220936 | 94805 | 170614 | SPS | TX | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Potter County 765 kV Reactor 1 | Regional Reliability | 2031-05-15 | 2025-01-01 | 2025-09-09 | 2024 ITP | 36018258 |  | 0 | 36018258 |  | NTC - Commitment Window |  |  |  |  | Install at least -150 MVAR reactor at Potter County looking toward Crossroads
220936 | 94805 | 170615 | SPS | NM | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Phantom 765 kV Reactor 1 | Regional Reliability | 2031-05-15 | 2025-01-01 | 2025-09-09 | 2024 ITP | 62559830 |  | 0 | 62559830 |  | NTC - Commitment Window |  |  |  |  | Install at least -150 MVAR reactor at Phantom looking toward Crossroads
220936 | 94805 | 170616 | SPS | NM | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Crossroads 345 kV Substation Expansion | Regional Reliability | 2031-05-15 | 2025-01-01 | 2025-09-09 | 2024 ITP | 15254945 |  | 0 | 15254945 |  | NTC - Commitment Window |  |  |  |  | Expand Crossroads 345 kV substation
220936 | 94805 | 170617 | SPS | NM | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Phantom 345 kV Substation Expansion | Regional Reliability | 2031-05-15 | 2025-01-01 | 2025-09-09 | 2024 ITP | 57442852 |  | 0 | 57442852 |  | NTC - Commitment Window |  |  |  |  | Expand Phantom 345 kV substation
220936 | 94805 | 170618 | SPS | TX | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Potter County 345 kV Substation Expansion #1 | Regional Reliability | 2031-05-15 | 2025-01-01 | 2025-09-09 | 2024 ITP | 177624482 |  | 0 | 177624482 |  | NTC - Commitment Window |  |  |  |  | Expand Potter County 345 kV substation
220936 | 94805 | 170742 | SPS | NM | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Bandit 345 kV Substation | Regional Reliability | 2031-05-15 | 2025-01-01 | 2025-09-09 | 2024 ITP |  |  | 0 |  |  | NTC - Commitment Window |  |  |  |  | Build Bandit 345 kV substation
220936 | 94805 | 170743 | SPS | TX | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Tecovas 345 kV Substation | Regional Reliability | 2031-05-15 | 2025-01-01 | 2025-09-09 | 2024 ITP |  |  | 0 |  |  | NTC - Commitment Window |  |  |  |  | Build Tecovas 345 kV substation
220936 | 94805 | 170744 | SPS | TX | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Tecovas – Potter County 345 kV Ckt 1 New Line | Regional Reliability | 2031-05-15 | 2025-01-01 | 2025-09-09 | 2024 ITP |  |  | 0 | 40539317 |  | NTC - Commitment Window |  |  |  |  | Build a new 345 kV Ckt 1 line from Tecovas 345 kV substation to Potter County 345 kV substation.
220936 | 94805 | 170745 | SPS | TX | Line - Potter County 765 kV - Crossroads 765 kV - Phantom 765 kV | Tecovas – Potter County 345 kV Ckt 2 New Line | Regional Reliability | 2031-05-15 | 2025-01-01 | 2025-09-09 | 2024 ITP |  |  | 0 | 40539317 |  | NTC - Commitment Window |  |  |  |  | Build a new 345 kV Ckt 2 line from Tecovas 345 kV substation to Potter County 345 kV substation.
220965 | 95133 | 170831 | OGE | OK | Line - Trosper - Reno 138 kV Rebuild | Trosper - Reno 138 kV Ckt 1 Rebuild | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 3278000 |  | NTC - Commitment Window | 514963 | TROSPER 138 | 514973 | RENO 138 | Rebuild 2.62-mile Ckt 1 line from Trosper 138 kV substation to Reno 138 kV substation |  |  | 2.62
220965 | 95133 | 170832 | OGE | OK | Line - Trosper - Reno 138 kV Rebuild | Trosper 138 kV Ckt 1 Terminal Upgrade toward Reno 138 kV | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 400000 |  | NTC - Commitment Window | 514963 | TROSPER 138 | 514973 | RENO 138 | Upgrade terminal equipment at Trosper 138 kV substation for Ckt 1 toward Reno 138 kV
220965 | 95133 | 170833 | OGE | OK | Line - Trosper - Reno 138 kV Rebuild | Reno 138 kV Ckt 1 Terminal Upgrade toward Trosper 138 kV | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 2500000 |  | NTC - Commitment Window | 514973 | RENO 138 | 514963 | TROSPER 138 | Upgrade terminal equipment at Reno 138 kV substation for Ckt 1 toward Trosper 138 kV
220958 | 95134 | 170834 | MWE | ND | Sub - Lindahl - Simpson 115 kV Terminal Upgrade | Lindahl 115 kV Ckt 1 Terminal Upgrade toward Simpson 115 kV | Regional Reliability |  | 2028-05-12 | 2025-11-10 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 655910 |  | 655911 |  | Upgrade terminal equipment at Lindahl 115 kV substation for Ckt 1 toward Simpson 115 kV
220958 | 95134 | 170835 | MWE | ND | Sub - Lindahl - Simpson 115 kV Terminal Upgrade | Simpson 115 kV Ckt 1 Terminal Upgrade toward Lindahl 115 kV | Regional Reliability |  | 2028-05-12 | 2025-11-10 | 2025 ITP |  |  | 0 | 50000 |  | NTC - Commitment Window | 655911 |  | 655910 |  | Upgrade terminal equipment at Simpson 115 kV substation for Ckt 1 toward Lindahl 115 kV
220965 | 95135 | 170836 | OGE | OK | Line - Horseshoe Lake - Dunjee - Reno 138 kV Reconductor | Dunjee - Horseshoe Lake 138 kV Ckt 1 Rebuild | Regional Reliability |  | 2028-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 7948700 |  | NTC - Commitment Window | 514884 | DUNJEE 138 | 514941 | HORSESHOE LAKE 138 | Rebuild 7.87-mile Ckt 1 line from Dunjee 138 kV substation to Horseshoe Lake 138 kV substation |  |  | 7.87
220965 | 95135 | 170837 | OGE | OK | Line - Horseshoe Lake - Dunjee - Reno 138 kV Reconductor | Dunjee 138 kV Ckt 1 Terminal Upgrade toward Horseshoe Lake 138 kV | Regional Reliability |  | 2028-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 10000 |  | NTC - Commitment Window | 514884 | DUNJEE 138 | 514941 | HORSESHOE LAKE 138 | Upgrade terminal equipment at Dunjee 138 kV substation for Ckt 1 toward Horseshoe Lake 138 kV
220965 | 95135 | 170838 | OGE | OK | Line - Horseshoe Lake - Dunjee - Reno 138 kV Reconductor | Horseshoe Lake 138 kV Ckt 1 Terminal Upgrade toward Dunjee 138 kV | Regional Reliability |  | 2028-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 650000 |  | NTC - Commitment Window | 514941 | HORSESHOE LAKE 138 | 514884 | DUNJEE 138 | Upgrade terminal equipment at Horseshoe Lake 138 kV substation for Ckt 1 toward Dunjee 138 kV
220965 | 95135 | 170839 | OGE | OK | Line - Horseshoe Lake - Dunjee - Reno 138 kV Reconductor | Dunjee 138 kV Ckt 1 Terminal Upgrade toward Reno 138 kV | Regional Reliability |  | 2028-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 10000 |  | NTC - Commitment Window | 514884 | DUNJEE 138 | 514973 | RENO 138 | Upgrade terminal equipment at Dunjee 138 kV substation for Ckt 1 toward Reno 138 kV
220965 | 95135 | 170840 | OGE | OK | Line - Horseshoe Lake - Dunjee - Reno 138 kV Reconductor | Reno 138 kV Ckt 1 Terminal Upgrade toward Dunjee 138 kV | Regional Reliability |  | 2028-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 650000 |  | NTC - Commitment Window | 514973 | RENO 138 | 514884 | DUNJEE 138 | Upgrade terminal equipment at Reno 138 kV substation for Ckt 1 toward Dunjee 138 kV
220965 | 95135 | 170841 | OGE | OK | Line - Horseshoe Lake - Dunjee - Reno 138 kV Reconductor | Dunjee - Reno 138 kV Ckt 1 Rebuild | Regional Reliability |  | 2028-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 7393200 |  | NTC - Commitment Window | 514884 | DUNJEE 138 | 514973 | RENO 138 | Rebuild 7.32-mile Ckt 1 line from Dunjee 138 kV substation to Reno 138 kV substation |  |  | 7.32
220972 | 95136 | 170842 | SPS | NM | Line - Whitten - Jal 115 kV Rebuild | Whitten - Jal 115 kV Ckt 1 Rebuild | Regional Reliability |  | 2026-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 5740739 |  | NTC - Commitment Window | 528540 | Whitten Sub 115 kV | 528547 | South Jal Sub 115 kV | Rebuild 7.9-mile Ckt 1 line from Whitten 115 kV substation to Jal 115 kV substation |  |  | 7.9
220972 | 95136 | 170843 | SPS | NM | Line - Whitten - Jal 115 kV Rebuild | Whitten 115 kV Ckt 1 Terminal Upgrade toward Jal 115 kV | Regional Reliability |  | 2026-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 528540 | Whitten Sub 115 kV | 528547 | South Jal Sub 115 kV | Upgrade terminal equipment at Whitten 115 kV substation for Ckt 1 toward Jal 115 kV
220972 | 95136 | 170844 | SPS | NM | Line - Whitten - Jal 115 kV Rebuild | Jal 115 kV Ckt 1 Terminal Upgrade toward Whitten 115 kV | Regional Reliability |  | 2026-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 528547 | South Jal Sub 115 kV | 528540 | Whitten Sub 115 kV | Upgrade terminal equipment at Jal 115 kV substation for Ckt 1 toward Whitten 115 kV
220972 | 95137 | 170845 | SPS | NM | Line - Hobbs South - Switch 4J44 - Hobbs West S.W. Station 115 kV Rebuild | Hobbs South - Switch 4J44 115 kV Ckt 1 Rebuild | Regional Reliability |  | 2030-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 1900000 |  | NTC - Commitment Window | 528480 |  | 528484 | Switch #4J44 115 kV | Rebuild 1.9-mile Ckt 1 line from Hobbs South 115 kV substation to Switch 4J44 115 kV substation |  |  | 1.9
220972 | 95137 | 170846 | SPS | NM | Line - Hobbs South - Switch 4J44 - Hobbs West S.W. Station 115 kV Rebuild | Hobbs South 115 kV Ckt 1 Terminal Upgrade toward Switch 4J44 115 kV | Regional Reliability |  | 2030-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 528480 |  | 528484 | Switch #4J44 115 kV | Upgrade terminal equipment at Hobbs South 115 kV substation for Ckt 1 toward Switch 4J44 115 kV
220972 | 95137 | 170847 | SPS | NM | Line - Hobbs South - Switch 4J44 - Hobbs West S.W. Station 115 kV Rebuild | Switch 4J44 115 kV Ckt 1 Terminal Upgrade toward Hobbs South 115 kV | Regional Reliability |  | 2030-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 528484 | Switch #4J44 115 kV | 528480 |  | Upgrade terminal equipment at Switch 4J44 115 kV substation for Ckt 1 toward Hobbs South 115 kV
220972 | 95137 | 170848 | SPS | NM | Line - Hobbs South - Switch 4J44 - Hobbs West S.W. Station 115 kV Rebuild | Switch 4J44 - Hobbs West S.W. Sta. 115 kV Ckt 1 Rebuild | Regional Reliability |  | 2030-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 1000000 |  | NTC - Commitment Window | 528484 | Switch #4J44 115 kV | 528498 | West Hobbs Switching Station 115 kV | Rebuild 1-mile Ckt 1 line from Switch 4J44 115 kV substation to Hobbs West S.W. Sta. 115 kV substation |  |  | 1
220972 | 95137 | 170849 | SPS | NM | Line - Hobbs South - Switch 4J44 - Hobbs West S.W. Station 115 kV Rebuild | Switch 4J44 115 kV Ckt 1 Terminal Upgrade toward Hobbs West S.W. Sta. 115 kV | Regional Reliability |  | 2030-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 528484 | Switch #4J44 115 kV | 528498 | West Hobbs Switching Station 115 kV | Upgrade terminal equipment at Switch 4J44 115 kV substation for Ckt 1 toward Hobbs West S.W. Sta. 115 kV
220972 | 95137 | 170850 | SPS | NM | Line - Hobbs South - Switch 4J44 - Hobbs West S.W. Station 115 kV Rebuild | Hobbs West S.W. Sta. 115 kV Ckt 1 Terminal Upgrade toward Switch 4J44 115 kV | Regional Reliability |  | 2030-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 528498 | West Hobbs Switching Station 115 kV | 528484 | Switch #4J44 115 kV | Upgrade terminal equipment at Hobbs West S.W. Sta. 115 kV substation for Ckt 1 toward Switch 4J44 115 kV
220951 | 95139 | 170851 | EMW | MO | Line - TWA - North Congress 161 kV Rebuild | TWA - North Congress 161 kV Ckt 1 Rebuild | Economic |  | 2031-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 6088665.66 |  | NTC - Commitment Window | 541214 | TWA 161 KV | 541318 |  | Rebuild 2.85-mile Ckt 1 line from TWA 161 kV substation to North Congress 161 kV substation |  |  | 2.85
220951 | 95139 | 170852 | EMW | MO | Line - TWA - North Congress 161 kV Rebuild | TWA 161 kV Ckt 1 Terminal Upgrade toward North Congress 161 kV | Economic |  | 2031-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 1909407 |  | NTC - Commitment Window | 541214 | TWA 161 KV | 541318 |  | Upgrade terminal equipment at TWA 161 kV substation for Ckt 1 toward North Congress 161 kV
220951 | 95139 | 170853 | EMW | MO | Line - TWA - North Congress 161 kV Rebuild | North Congress 161 kV Ckt 1 Terminal Upgrade toward TWA 161 kV | Economic |  | 2031-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 205322 |  | NTC - Commitment Window | 541318 |  | 541214 | TWA 161 KV | Upgrade terminal equipment at North Congress 161 kV substation for Ckt 1 toward TWA 161 kV
220965 | 95140 | 170854 | OGE | OK | Line - NE 10th - Reno 138 kV Rebuild | NE 10th - Reno 138 kV Ckt 1 Rebuild | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 4992000 |  | NTC - Commitment Window | 514964 | NE 10TH 138 | 514973 | RENO 138 | Rebuild 4.16-mile Ckt 1 line from NE 10th 138 kV substation to Reno 138 kV substation |  |  | 4.16
220965 | 95140 | 170855 | OGE | OK | Line - NE 10th - Reno 138 kV Rebuild | NE 10th 138 kV Ckt 1 Terminal Upgrade toward Reno 138 kV | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 400000 |  | NTC - Commitment Window | 514964 | NE 10TH 138 | 514973 | RENO 138 | Upgrade terminal equipment at NE 10th 138 kV substation for Ckt 1 toward Reno 138 kV
220965 | 95140 | 170856 | OGE | OK | Line - NE 10th - Reno 138 kV Rebuild | Reno 138 kV Ckt 1 Terminal Upgrade toward NE 10th 138 kV | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 3000000 |  | NTC - Commitment Window | 514973 | RENO 138 | 514964 | NE 10TH 138 | Upgrade terminal equipment at Reno 138 kV substation for Ckt 1 toward NE 10th 138 kV
220965 | 95141 | 170857 | OGE | OK | Line - Horseshoe Lake - Midway 138 kV New Line | Horseshoe Lake - Midway 138 kV Ckt 2 New Line | Regional Reliability |  | 2028-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 7800000 |  | NTC - Commitment Window | 514941 | HORSESHOE LAKE 138 | 514966 | MIDWAY 138 | Build a 5.06-mile 138 kV Ckt 2 line from Horseshoe Lake to Midway |  | 5.06
220965 | 95141 | 170858 | OGE | OK | Line - Horseshoe Lake - Midway 138 kV New Line | Horseshoe Lake 138 kV Ckt 2 Terminal Upgrade toward Midway 138 kV | Regional Reliability |  | 2028-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 2000000 |  | NTC - Commitment Window | 514941 | HORSESHOE LAKE 138 | 514966 | MIDWAY 138 | Upgrade terminal equipment at Horseshoe Lake 138 kV substation for Ckt 2 toward Midway 138 kV
220965 | 95141 | 170859 | OGE | OK | Line - Horseshoe Lake - Midway 138 kV New Line | Midway 138 kV Ckt 2 Terminal Upgrade toward Horseshoe Lake 138 kV | Regional Reliability |  | 2028-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 4500000 |  | NTC - Commitment Window | 514966 | MIDWAY 138 | 514941 | HORSESHOE LAKE 138 | Upgrade terminal equipment at Midway 138 kV substation for Ckt 2 toward Horseshoe Lake 138 kV
220965 | 95142 | 170860 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Memorial 138 kV Ckt 1 Terminal Upgrade toward Bryant 138 kV | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 500000 |  | NTC - Commitment Window | 514835 | MEMORIAL 138 | 514839 | BRYANT 138 | Upgrade terminal equipment at Memorial 138 kV substation for Ckt 1 toward Bryant 138 kV
220965 | 95142 | 170861 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Bryant 138 kV Ckt 1 Terminal Upgrade toward Memorial 138 kV | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 10000 |  | NTC - Commitment Window | 514839 | BRYANT 138 | 514835 | MEMORIAL 138 | Upgrade terminal equipment at Bryant 138 kV substation for Ckt 1 toward Memorial 138 kV
220965 | 95142 | 170862 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Jones Tap 138 kV Ckt 1 Terminal Upgrade toward Horseshoe Lake 138 kV | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 514840 | JONES TAP 138 | 514941 | HORSESHOE LAKE 138 | Upgrade terminal equipment at Jones Tap 138 kV substation for Ckt 1 toward Horseshoe Lake 138 kV
220965 | 95142 | 170863 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Horseshoe Lake 138 kV Ckt 1 Terminal Upgrade toward Jones Tap 138 kV | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 1000000 |  | NTC - Commitment Window | 514941 | HORSESHOE LAKE 138 | 514840 | JONES TAP 138 | Upgrade terminal equipment at Horseshoe Lake 138 kV substation for Ckt 1 toward Jones Tap 138 kV
220965 | 95142 | 170864 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Jones Tap 138 kV Ckt 1 Terminal Upgrade toward Acorn 138 kV | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 500000 |  | NTC - Commitment Window | 514840 | JONES TAP 138 | 515459 |  | Upgrade terminal equipment at Jones Tap 138 kV substation for Ckt 1 toward Acorn 138 kV
220965 | 95142 | 170865 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Acorn 138 kV Ckt 1 Terminal Upgrade toward Jones Tap 138 kV | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 10000 |  | NTC - Commitment Window | 515459 |  | 514840 | JONES TAP 138 | Upgrade terminal equipment at Acorn 138 kV substation for Ckt 1 toward Jones Tap 138 kV
220965 | 95142 | 170866 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | NE 30th 69 kV to 138 kV Voltage Conversion | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 9000000 |  | NTC - Commitment Window | 514969 | NE 30TH 69 |  |  | Convert the 69 kV NE 30th substation to 138 kV
220965 | 95142 | 170867 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Green Pastures 69 kV to 138 kV Voltage Conversion | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 4000000 |  | NTC - Commitment Window | 514971 | GREEN PASTURES 69 |  |  | Convert the 69 kV Green Pastures substation to 138 kV
220964 | 95143 | 170868 | EM | KS | Device - Stilwell 161 kV Breakers | Stilwell 161 kV Breaker R13-22 Replacement | Regional Reliability |  | 2026-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 1309181 |  | NTC - Commitment Window | 542969 | STILWELL 161 KV |  |  | Replace Stilwell 161kV Breaker R13-22 with 63kA breakers
220964 | 95143 | 170869 | EM | KS | Device - Stilwell 161 kV Breakers | Stilwell 161 kV Breaker R4-13 Replacement | Regional Reliability |  | 2026-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 842154 |  | NTC - Commitment Window | 542969 | STILWELL 161 KV |  |  | Replace Stilwell 161kV Breaker R4-13 with 63kA breakers
220964 | 95143 | 170870 | EM | KS | Device - Stilwell 161 kV Breakers | Stilwell 161 kV Breaker R4-9 Replacement | Regional Reliability |  | 2026-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 842154 |  | NTC - Commitment Window | 542969 | STILWELL 161 KV |  |  | Replace Stilwell 161kV Breaker R4-9 with 63kA breakers
220964 | 95143 | 170871 | EM | KS | Device - Stilwell 161 kV Breakers | Stilwell 161 kV Breaker R6-15 Replacement | Regional Reliability |  | 2026-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 842154 |  | NTC - Commitment Window | 542969 | STILWELL 161 KV |  |  | Replace Stilwell 161kV Breaker R6-15 with 63kA breakers
220964 | 95143 | 170872 | EM | KS | Device - Stilwell 161 kV Breakers | Stilwell 161 kV Breaker R7-11 Replacement | Regional Reliability |  | 2026-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 842154 |  | NTC - Commitment Window | 542969 | STILWELL 161 KV |  |  | Replace Stilwell 161kV Breaker R7-11 with 63kA breakers
220964 | 95143 | 170873 | EM | KS | Device - Stilwell 161 kV Breakers | Stilwell 161 kV Breaker R7-14 Replacement | Regional Reliability |  | 2026-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 842154 |  | NTC - Commitment Window | 542969 | STILWELL 161 KV |  |  | Replace Stilwell 161kV Breaker R7-14 with 63kA breakers
220964 | 95143 | 170874 | EM | KS | Device - Stilwell 161 kV Breakers | Stilwell 161 kV Breaker R9-11 Replacement | Regional Reliability |  | 2026-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 842154 |  | NTC - Commitment Window | 542969 | STILWELL 161 KV |  |  | Replace Stilwell 161kV Breaker R9-11 with 63kA breakers
220964 | 95143 | 170875 | EM | KS | Device - Stilwell 161 kV Breakers | Stilwell 161 kV Breaker R6-22 Replacement | Regional Reliability |  | 2026-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 842574 |  | NTC - Commitment Window | 542969 | STILWELL 161 KV |  |  | Replace Stilwell 161kV Breaker R6-22 with 63kA breakers
220962 | 95144 | 170876 | EDE | MO | Device - Joplin West 7th 161 kV Breaker | Joplin West 7th 161 kV Circuit Switcher Brkr-16145 Replacement | Regional Reliability |  | 2026-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 519640 |  | NTC - Commitment Window | 547470 | SUB 145 - JOPLIN WEST 7TH |  |  | Replace existing circuit switcher and associated terminal equipment at Joplin West 7th 161kV Brkr-16145 breaker with to achieve a 40kA rating
220961 | 95138 | 170877 | BEPC | ND | Multi - Patent Gate - Pioneer 345 kV Line Tap at Marley | Patent Gate - Pioneer 345 kV Line Tap | Economic |  | 2028-01-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 12000000 |  | NTC - Commitment Window | 659390 |  | 659575 |  | Tap the planned Patent Gate - Pioneer 345 kV Ckt 1 line at new Marley substation
220961 | 95138 | 170878 | BEPC | ND | Multi - Patent Gate - Pioneer 345 kV Line Tap at Marley | Marley 345 kV New Substation | Economic |  | 2028-01-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 24188071 |  | NTC - Commitment Window |  |  |  |  | Install 345 kV substation at Marley
220961 | 95138 | 170879 | BEPC | ND | Multi - Patent Gate - Pioneer 345 kV Line Tap at Marley | Marley 345/115 kV Ckt 1 Transformer | Economic |  | 2028-01-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 15886035 |  | NTC - Commitment Window |  |  | 655793 |  | Install new 345/115 kV Ckt 1 transformer at Marley
220961 | 95138 | 170880 | BEPC | ND | Multi - Patent Gate - Pioneer 345 kV Line Tap at Marley | Marley 345 kV Ckt 1 Terminal Upgrade toward Marley 115 kV | Economic |  | 2028-01-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 2233100 |  | NTC - Commitment Window |  |  | 655793 |  | Upgrade terminal equipment at Marley 345 kV substation for Ckt 1 toward Marley 115 kV
220961 | 95138 | 170881 | BEPC | ND | Multi - Patent Gate - Pioneer 345 kV Line Tap at Marley | Marley 115 kV Ckt 1 Terminal Upgrade toward Marley 345 kV | Economic |  | 2028-01-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 404917 |  | NTC - Commitment Window | 655793 |  |  |  | Upgrade terminal equipment at Marley 115 kV substation for Ckt 1 toward Marley 345 kV
220961 | 95138 | 170882 | BEPC | ND | Multi - Patent Gate - Pioneer 345 kV Line Tap at Marley | Marley 345/115 kV Ckt 2 Transformer | Economic |  | 2028-01-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 16198065 |  | NTC - Commitment Window |  |  | 655793 |  | Install new 345/115 kV Ckt 2 transformer at Marley
220961 | 95138 | 170883 | BEPC | ND | Multi - Patent Gate - Pioneer 345 kV Line Tap at Marley | Marley 345 kV Ckt 2 Terminal Upgrade toward Marley 115 kV | Economic |  | 2028-01-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 2233100 |  | NTC - Commitment Window |  |  | 655793 |  | Upgrade terminal equipment at Marley 345 kV substation for Ckt 2 toward Marley 115 kV
220961 | 95138 | 170884 | BEPC | ND | Multi - Patent Gate - Pioneer 345 kV Line Tap at Marley | Marley 115 kV Ckt 2 Terminal Upgrade toward Marley 345 kV | Economic |  | 2028-01-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 404917 |  | NTC - Commitment Window | 655793 |  |  |  | Upgrade terminal equipment at Marley 115 kV substation for Ckt 2 toward Marley 345 kV
220965 | 95141 | 170885 | OGE | OK | Line - Horseshoe Lake - Midway 138 kV New Line | Horseshoe Lake 138 kV Substation Expansion or Rebuild | Regional Reliability |  | 2028-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 514941 | HORSESHOE LAKE 138 |  |  | Expand or rebuild Horseshoe Lake 138 kV substation
220965 | 95141 | 170886 | OGE | OK | Line - Horseshoe Lake - Midway 138 kV New Line | Midway 138 kV Substation Expansion or Rebuild | Regional Reliability |  | 2028-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 514966 | MIDWAY 138 |  |  | Expand or rebuild Midway 138 kV substation
220965 | 95142 | 170887 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Kelly Ave. - Remington Park Ckt 1 138 kV New Line | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 4100000 |  | NTC - Commitment Window | 514501 |  | 514874 | REMINGTON PARK 138 | Rebuild the existing 2.8-miles 138 kV ckt 1 line from Kelly Ave. - Remmington Tap then extend the line to Remington Park 138 kV substation |  | 2.8
220965 | 95142 | 170888 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Stonewall - Remington Park Ckt 1 138 kV New Line | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 3000000 |  | NTC - Commitment Window | 514870 | STONEWALL 138 | 514874 | REMINGTON PARK 138 | Rebuild the existing 2-miles 138 kV ckt 1 line from Stonewall - Remmington Tap then extend the line to Remington Park 138 kV substation |  | 1.94
220965 | 95142 | 170889 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Remove Remington Tap - Remington 138 kV Ckt 1 | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 514872 | REMNGTON PARK 138 | 514874 | REMINGTON PARK 138 | Switch out 138 kV Ckt 1 line from Remington Tap to Remington
220965 | 95142 | 170890 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Remington Park - NE 30th Ckt 1 138 kV Voltage Conversion | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 7000000 |  | NTC - Commitment Window | 514874 | REMINGTON PARK 138 | 514969 | NE 30TH 69 | Convert the existing 69 kV line from NE 30th to Deep Fork Tap to Remington Tap to 138 kV to create a Ckt 1 138 kV line from NE 30th to Remington Park |  |  |  | 1.62
220965 | 95142 | 170891 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Remington Park - Green Pastures Ckt 1 138 kV Voltage Conversion | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 12000000 |  | NTC - Commitment Window | 514874 | REMINGTON PARK 138 | 514971 | GREEN PASTURES 69 | Convert the existing 69 kV line from Green Pastures to Deep Fork Tap to Remington Tap to 138 kV to create a Ckt 1 138 kV line from Green Pastures to Remington Park |  |  |  | 8.24
220965 | 95142 | 170892 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Remove Horseshoe Lake - Green Pastures 69 kV Ckt 1 | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 514927 | HSLEAST 69 | 514971 | GREEN PASTURES 69 | Switch out 69 kV Ckt 1 line from Horseshoe Lake to Green Pastures
220965 | 95142 | 170893 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Horseshoe Lake - Green Pastures Ckt 1 138 kV Voltage Conversion | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 11000000 |  | NTC - Commitment Window | 514941 | HORSESHOE LAKE 138 | 514971 | GREEN PASTURES 69 | Convert the existing Horseshoe Lake - Green Pastures Ckt 1 line to 138 kV |  |  |  | 9.96
220965 | 95142 | 170894 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Remove NE 30th - Deep Fork Tap 69 kV Ckt 1 | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 514969 | NE 30TH 69 | 514970 | DEEP FORK 69 | Switch out 69 kV Ckt 1 line from NE 30th to Deep Fork Tap
220965 | 95142 | 170895 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | NE 30th - Reno Ckt 1 138 kV Voltage Conversion | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 2500000 |  | NTC - Commitment Window | 514969 | NE 30TH 69 | 514973 | RENO 138 | Convert the existing NE 30th - Reno Ckt 1 line to 138 kV |  |  |  | 2.84
220965 | 95142 | 170896 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Remove Deep Fork Tap - Green Pastures 69 kV Ckt 1 | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 514970 | DEEP FORK 69 | 514971 | GREEN PASTURES 69 | Switch out 69 kV Ckt 1 line from Deep Fork Tap to Green Pastures
220965 | 95142 | 170897 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Remove Deep Fork Tap - Deep Fork 69 kV Ckt 1 | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 514970 | DEEP FORK 69 | 514974 | DEEP FORK 69 | Switch out 69 kV Ckt 1 line from Deep Fork Tap to Deep Fork
220965 | 95142 | 170898 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Remove Deep Fork Capacitor 69 kV Ckt 1 | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 514974 | DEEP FORK 69 |  |  | Switch out 69 kV Ckt 1 Capacitor at Deep Fork
220965 | 95142 | 170899 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Remove Deep Fork Capacitor 69 kV Ckt 2 | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 514974 | DEEP FORK 69 |  |  | Switch out 69 kV Ckt 2 Capacitor at Deep Fork
220965 | 95142 | 170900 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Remove Remington Tap 138 kV Substation | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 514872 | REMNGTON PARK 138 |  |  | Switch out Remington Tap 138 substation
220965 | 95142 | 170901 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Remove Deep Fork Tap 69 kV Substation | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 514970 | DEEP FORK 69 |  |  | Switch out Deep Fork Tap 69 substation
220965 | 95142 | 170902 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Remove Deep Fork 69 kV Substation | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 514974 | DEEP FORK 69 |  |  | Switch out Deep Fork 69 substation
220950 | 95145 | 170903 | AEP | TX | Line - Beckville - Bearcat Tap - Henderson REC - Poynter 69 kV Rebuild | Beckville - Bearcat Tap 69 kV Ckt 1 Rebuild | Zonal Reliability |  | 2029-05-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 4575000 |  | NTC - Commitment Window | 509054 | BECKVILLE | 509127 |  | Rebuild 2-mile Ckt 1 line from Beckville 69 kV substation to Bearcat Tap 69 kV substation |  |  | 2
220950 | 95145 | 170904 | AEP | TX | Line - Beckville - Bearcat Tap - Henderson REC - Poynter 69 kV Rebuild | Beckville 69 kV Ckt 1 Terminal Upgrade toward Bearcat Tap 69 kV | Zonal Reliability |  | 2029-05-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 1000000 |  | NTC - Commitment Window | 509054 | BECKVILLE | 509127 |  | Upgrade terminal equipment at Beckville 69 kV substation for Ckt 1 toward Bearcat Tap 69 kV
220950 | 95145 | 170905 | AEP | TX | Line - Beckville - Bearcat Tap - Henderson REC - Poynter 69 kV Rebuild | Bearcat Tap 69 kV Ckt 1 Terminal Upgrade toward Beckville 69 kV | Zonal Reliability |  | 2029-05-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 1000000 |  | NTC - Commitment Window | 509127 |  | 509054 | BECKVILLE | Upgrade terminal equipment at Bearcat Tap 69 kV substation for Ckt 1 toward Beckville 69 kV
220950 | 95145 | 170906 | AEP | TX | Line - Beckville - Bearcat Tap - Henderson REC - Poynter 69 kV Rebuild | Henderson REC - Poynter 69 kV Ckt 1 Rebuild | Zonal Reliability |  | 2029-05-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 19259000 |  | NTC - Commitment Window | 509065 | HENDERSON REC | 509081 | POYNTER | Rebuild 8.42-mile Ckt 1 line from Henderson REC 69 kV substation to Poynter 69 kV substation |  |  | 8.42
220950 | 95145 | 170908 | AEP | TX | Line - Beckville - Bearcat Tap - Henderson REC - Poynter 69 kV Rebuild | Poynter 69 kV Ckt 1 Terminal Upgrade toward Henderson REC 69 kV | Zonal Reliability |  | 2029-05-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 1000000 |  | NTC - Commitment Window | 509081 | POYNTER | 509065 | HENDERSON REC | Upgrade terminal equipment at Poynter 69 kV substation for Ckt 1 toward Henderson REC 69 kV
220950 | 95145 | 170909 | AEP | TX | Line - Beckville - Bearcat Tap - Henderson REC - Poynter 69 kV Rebuild | Henderson REC - Bearcat Tap 69 kV Ckt 1 Rebuild | Zonal Reliability |  | 2029-05-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 26647000 |  | NTC - Commitment Window | 509065 | HENDERSON REC | 509127 |  | Rebuild 11.65-mile Ckt 1 line from Henderson REC 69 kV substation to Bearcat Tap 69 kV substation |  |  | 11.65
220950 | 95145 | 170910 | AEP | TX | Line - Beckville - Bearcat Tap - Henderson REC - Poynter 69 kV Rebuild | Henderson REC 69 kV Ckt 1 Terminal Upgrade toward Bearcat Tap 69 kV | Zonal Reliability |  | 2029-05-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 2500000 |  | NTC - Commitment Window | 509065 | HENDERSON REC | 509127 |  | Upgrade terminal equipment at Henderson REC 69 kV substation for Ckt 1 toward Bearcat Tap 69 kV
220950 | 95145 | 170911 | AEP | TX | Line - Beckville - Bearcat Tap - Henderson REC - Poynter 69 kV Rebuild | Bearcat Tap 69 kV Ckt 1 Terminal Upgrade toward Henderson REC 69 kV | Zonal Reliability |  | 2029-05-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509127 |  | 509065 | HENDERSON REC | Upgrade terminal equipment at Bearcat Tap 69 kV substation for Ckt 1 toward Henderson REC 69 kV
220954 | 95146 | 170912 | MIDW | KS | Line - Knoll - North Hays 115 kV Rebuild | Knoll 115 kV Ckt 1 Terminal Upgrade toward North Hays 115 kV | Regional Reliability |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 1725000 |  | NTC - Commitment Window | 530561 | KNOLL 115 KV | 530581 | NORTH HAYS 115 KV | Upgrade terminal equipment at Knoll 115 kV substation for Ckt 1 toward North Hays 115 kV
220954 | 95146 | 170913 | MIDW | KS | Line - Knoll - North Hays 115 kV Rebuild | North Hays 115 kV Ckt 1 Terminal Upgrade toward Knoll 115 kV | Regional Reliability |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 650000 |  | NTC - Commitment Window | 530581 | NORTH HAYS 115 KV | 530561 | KNOLL 115 KV | Upgrade terminal equipment at North Hays 115 kV substation for Ckt 1 toward Knoll 115 kV
220964 | 95147 | 170914 | EM | KS | Line - Craig - Lenexa Ckt 2 161 kV Rebuild | Craig 161 kV Ckt 2 Terminal Upgrade toward Lenexa 161 kV | Economic |  | 2025-11-18 | 2025-11-11 | 2025 ITP |  |  | 0 | 1775286.87 |  | NTC - Commitment Window | 542978 | CRAIG 161 KV | 543038 | LENEXA SOUTH 161 KV | Upgrade terminal equipment at Craig 161 kV substation for Ckt 2 toward Lenexa 161 kV
220964 | 95147 | 170915 | EM | KS | Line - Craig - Lenexa Ckt 2 161 kV Rebuild | Lenexa 161 kV Ckt 2 Terminal Upgrade toward Craig 161 kV | Economic |  | 2025-11-18 | 2025-11-11 | 2025 ITP |  |  | 0 | 3987409.87 |  | NTC - Commitment Window | 543038 | LENEXA SOUTH 161 KV | 542978 | CRAIG 161 KV | Upgrade terminal equipment at Lenexa 161 kV substation for Ckt 2 toward Craig 161 kV
220951 | 95148 | 170916 | EMW | MO | Line - Maryville - Midway - Avenue City - St. Joseph 161 kV Rebuild | Maryville - Midway 161 kV Ckt 1 Rebuild | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 23579742 |  | NTC - Commitment Window | 541251 | Maryville 161 KV | 541369 | MIDWAY 161 KV | Rebuild 19.5-mile Ckt 1 line from Maryville 161 kV substation to Midway 161 kV substation |  |  | 19.5
220951 | 95148 | 170917 | EMW | MO | Line - Maryville - Midway - Avenue City - St. Joseph 161 kV Rebuild | Maryville 161 kV Ckt 1 Terminal Upgrade toward Midway 161 kV | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 1220344.07 |  | NTC - Commitment Window | 541251 | Maryville 161 KV | 541369 | MIDWAY 161 KV | Upgrade terminal equipment at Maryville 161 kV substation for Ckt 1 toward Midway 161 kV
220951 | 95148 | 170918 | EMW | MO | Line - Maryville - Midway - Avenue City - St. Joseph 161 kV Rebuild | Midway 161 kV Ckt 1 Terminal Upgrade toward Maryville 161 kV | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 185722.96 |  | NTC - Commitment Window | 541369 | MIDWAY 161 KV | 541251 | Maryville 161 KV | Upgrade terminal equipment at Midway 161 kV substation for Ckt 1 toward Maryville 161 kV
220951 | 95148 | 170919 | EMW | MO | Line - Maryville - Midway - Avenue City - St. Joseph 161 kV Rebuild | St. Joseph - Avenue City Tap 161 kV Ckt 1 Rebuild | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 4771299.82 |  | NTC - Commitment Window | 541253 | ST Joe 161 KV | 541394 |  | Rebuild 3.32-mile Ckt 1 line from St. Joseph 161 kV substation to Avenue City Tap 161 kV substation |  |  | 3.32
220951 | 95148 | 170920 | EMW | MO | Line - Maryville - Midway - Avenue City - St. Joseph 161 kV Rebuild | St. Joseph 161 kV Ckt 1 Terminal Upgrade toward Avenue City Tap 161 kV | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 1655440.09 |  | NTC - Commitment Window | 541253 | ST Joe 161 KV | 541394 |  | Upgrade terminal equipment at St. Joseph 161 kV substation for Ckt 1 toward Avenue City Tap 161 kV
220951 | 95148 | 170921 | EMW | MO | Line - Maryville - Midway - Avenue City - St. Joseph 161 kV Rebuild | Avenue City Tap 161 kV Ckt 1 Terminal Upgrade toward St. Joseph 161 kV | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 62974.9 |  | NTC - Commitment Window | 541394 |  | 541253 | ST Joe 161 KV | Upgrade terminal equipment at Avenue City Tap 161 kV substation for Ckt 1 toward St. Joseph 161 kV
220951 | 95148 | 170922 | EMW | MO | Line - Maryville - Midway - Avenue City - St. Joseph 161 kV Rebuild | Midway - Avenue City Tap 161 kV Ckt 1 Rebuild | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 24305896.21 |  | NTC - Commitment Window | 541369 | MIDWAY 161 KV | 541394 |  | Rebuild 20.54-mile Ckt 1 line from Midway 161 kV substation to Avenue City Tap 161 kV substation |  |  | 20.54
220951 | 95148 | 170923 | EMW | MO | Line - Maryville - Midway - Avenue City - St. Joseph 161 kV Rebuild | Midway 161 kV Ckt 1 Terminal Upgrade toward Avenue City Tap 161 kV | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 213774.25 |  | NTC - Commitment Window | 541369 | MIDWAY 161 KV | 541394 |  | Upgrade terminal equipment at Midway 161 kV substation for Ckt 1 toward Avenue City Tap 161 kV
220951 | 95148 | 170924 | EMW | MO | Line - Maryville - Midway - Avenue City - St. Joseph 161 kV Rebuild | Avenue City Tap 161 kV Ckt 1 Terminal Upgrade toward Midway 161 kV | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 101256.89 |  | NTC - Commitment Window | 541394 |  | 541369 | MIDWAY 161 KV | Upgrade terminal equipment at Avenue City Tap 161 kV substation for Ckt 1 toward Midway 161 kV
220974 | 95149 | 170925 | ETEC | TX | Multi - FARMRAC - Ripley - Argo 69 kV, Rebuild Chapel Hill - Adora Closed Loop | Ripley - Argo 69 kV Ckt 1 Rebuild | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 17360000 |  | NTC - Commitment Window | 509640 |  | 509642 |  | Rebuild 8.59-mile Ckt 1 line from Ripley 69 kV substation to Argo 69 kV substation |  |  | 8.59
220974 | 95149 | 170926 | ETEC | TX | Multi - FARMRAC - Ripley - Argo 69 kV, Rebuild Chapel Hill - Adora Closed Loop | Ripley 69 kV Ckt 1 Terminal Upgrade toward Argo 69 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509640 |  | 509642 |  | Upgrade terminal equipment at Ripley 69 kV substation for Ckt 1 toward Argo 69 kV
220974 | 95149 | 170927 | ETEC | TX | Multi - FARMRAC - Ripley - Argo 69 kV, Rebuild Chapel Hill - Adora Closed Loop | Argo 69 kV Ckt 1 Terminal Upgrade toward Ripley 69 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509642 |  | 509640 |  | Upgrade terminal equipment at Argo 69 kV substation for Ckt 1 toward Ripley 69 kV
220974 | 95149 | 170928 | ETEC | TX | Multi - FARMRAC - Ripley - Argo 69 kV, Rebuild Chapel Hill - Adora Closed Loop | Ripley 69 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 8240000 |  | NTC - Commitment Window | 509640 |  |  |  | Expand or rebuild Ripley 69 kV substation
220974 | 95149 | 170929 | ETEC | TX | Multi - FARMRAC - Ripley - Argo 69 kV, Rebuild Chapel Hill - Adora Closed Loop | Adora 69 kV New Substation | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 10150000 |  | NTC - Commitment Window | 509663 |  |  |  | Expand or rebuild Adora 69 kV substation to accommodate new equipment if necessary
220974 | 95149 | 170930 | ETEC | TX | Multi - FARMRAC - Ripley - Argo 69 kV, Rebuild Chapel Hill - Adora Closed Loop | Ripley 69 kV Ckt NO Terminal Upgrade toward Adora 69 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509640 |  | 509663 |  | Upgrade terminal equipment at Ripley 69 kV substation for Ckt NO toward Adora 69 kV
220974 | 95149 | 170931 | ETEC | TX | Multi - FARMRAC - Ripley - Argo 69 kV, Rebuild Chapel Hill - Adora Closed Loop | Adora 69 kV Ckt NO Terminal Upgrade toward Ripley 69 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509663 |  | 509640 |  | Upgrade terminal equipment at Adora 69 kV substation for Ckt NO toward Ripley 69 kV
220974 | 95149 | 170932 | ETEC | TX | Multi - FARMRAC - Ripley - Argo 69 kV, Rebuild Chapel Hill - Adora Closed Loop | Argo 138 kV Ckt 1 Terminal Upgrade toward Liberty Hill 138 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509665 |  | 509643 |  | Upgrade terminal equipment at Argo 138 kV substation for Ckt 1 toward Liberty Hill 138 kV
220974 | 95149 | 170933 | ETEC | TX | Multi - FARMRAC - Ripley - Argo 69 kV, Rebuild Chapel Hill - Adora Closed Loop | Liberty Hill 138 kV Ckt 1 Terminal Upgrade toward Argo138 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509643 |  | 509665 |  | Upgrade terminal equipment at Liberty Hill 138 kV substation for Ckt 1 toward Argo 138 kV
220974 | 95149 | 170934 | ETEC | TX | Multi - FARMRAC - Ripley - Argo 69 kV, Rebuild Chapel Hill - Adora Closed Loop | Chapel Hill 138 kV Substation Expansion or Rebuild (ETEC) | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 4410000 |  | NTC - Commitment Window | 509664 |  |  |  | Expand or rebuild Chapel Hill 138 kV substation (Four terminal station)
220954 | 95146 | 170935 | MIDW | KS | Line - Knoll - North Hays 115 kV Rebuild | Knoll - North Hays 115 kV Ckt 1 Rebuild (2) | Regional Reliability |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 2600000 |  | NTC - Commitment Window | 530561 | KNOLL 115 KV | 530581 | NORTH HAYS 115 KV | Rebuild 2-mile Ckt 1 line from Knoll 115 kV substation to North Hays 115 kV substation using existing easements |  |  | 2
220974 | 95149 | 170936 | ETEC | TX | Multi - FARMRAC - Ripley - Argo 69 kV, Rebuild Chapel Hill - Adora Closed Loop | Ripley - Adora 69 kV Ckt NO Switch in Normally Open | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509640 |  | 509663 |  | Switch in normally open 9.11-mile 69 kV Ckt NO line from Ripley to Adora
220950 | 95150 | 170937 | AEP | TX | Multi - Buford - DeKalb 69 kV Line Tap | Buford - DeKalb 69 kV Line Tap | Zonal Reliability |  | 2031-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 2200000 |  | NTC - Commitment Window | 508287 | BUFORD SURVEY | 508289 | DEKALB | Tap the existing Buford - DeKalb 69 kV Ckt 1 line at new South Dekalb Switch Station substation
220974 | 95150 | 170938 | ETEC | TX | Multi - Buford - DeKalb 69 kV Line Tap | South Dekalb Switch Station 69 kV New Substation | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 5237500 |  | NTC - Commitment Window | 509660 |  |  |  | Install 69 kV substation at South Dekalb
220950 | 95150 | 170939 | AEP | TX | Multi - Buford - DeKalb 69 kV Line Tap | Buford 69 kV Substation Upgrade | Zonal Reliability |  | 2031-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 500000 |  | NTC - Commitment Window | 508287 | BUFORD SURVEY |  |  | Upgrade equipment at the Buford 69 kV Substation to accommodate tapping the existing Buford - DeKalb 69 kV Ckt 1 line at new South Dekalb Switch Station substation
220950 | 95150 | 170940 | AEP | TX | Multi - Buford - DeKalb 69 kV Line Tap | DeKalb 69 kV Substation Upgrade | Zonal Reliability |  | 2031-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 500000 |  | NTC - Commitment Window | 508289 | DEKALB |  |  | Upgrade equipment at the DeKalb 69 kV Substation to accommodate tapping the existing Buford - DeKalb 69 kV Ckt 1 line at new South Dekalb Switch Station substation
220950 | 95152 | 170941 | AEP | OK | Line - Weyco - Valliant 138 kV Ckt 2 New Line | Weyco - Valliant 138 kV Ckt 2 New Line | Zonal Reliability |  | 2028-02-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 10545400 |  | NTC - Commitment Window | 510866 | VALLIANT-WEYCO | 510918 | VALLIANT 138KV | Build a 3.57-mile 138 kV Ckt 2 line from Weyco to Valliant |  | 3.57
220950 | 95152 | 170942 | AEP | OK | Line - Weyco - Valliant 138 kV Ckt 2 New Line | Weyco 138 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2028-02-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 9921543 |  | NTC - Commitment Window | 510866 | VALLIANT-WEYCO |  |  | Expand or rebuild Weyco 138 kV substation
220950 | 95152 | 170943 | AEP | OK | Line - Weyco - Valliant 138 kV Ckt 2 New Line | Valliant 138 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2028-02-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 3893656 |  | NTC - Commitment Window | 510918 | VALLIANT 138KV |  |  | Expand or rebuild Valliant 138 kV substation
220950 | 95153 | 170946 | AEP | OK | Line - Lone Oak - Tuskahoma - Talihina 138 kV New Line | Sardis - Enogex Wilburton Tap 138 kV Line Tap | Zonal Reliability |  | 2027-07-30 | 2025-11-07 | 2025 ITP |  |  | 0 | 2200000 |  | NTC - Commitment Window | 510926 | Sardis 138 kV | 510944 | Enogex Wilburton Tap 138 kV | Tap the existing Sardis - Enogex Wilburton Tap 138 kV Ckt 1 line at new Yanush substation
220950 | 95153 | 170947 | AEP | OK | Line - Lone Oak - Tuskahoma - Talihina 138 kV New Line | Yanush 138 kV New Substation | Zonal Reliability |  | 2027-07-30 | 2025-11-07 | 2025 ITP |  |  | 0 | 9800000 |  | NTC - Commitment Window |  |  |  |  | Install 138 kV substation at Yanush
220950 | 95153 | 170948 | AEP | OK | Line - Lone Oak - Tuskahoma - Talihina 138 kV New Line | Talihina - Yanush 138 kV Ckt 1 New Line | Zonal Reliability |  | 2027-07-30 | 2025-11-07 | 2025 ITP |  |  | 0 | 35884000 |  | NTC - Commitment Window |  |  |  |  | Build a 18-mile 138 kV Ckt 1 line from Talihina to Yanush |  | 18
220974 | 95151 | 170951 | ETEC | TX | Multi - Center - Center South 138 kV Line Tap | Center - Center South 138 kV Line Tap | Zonal Reliability |  | 2028-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509058 | CENTER | 509121 |  | Tap the existing Center - Center South 138 kV Ckt 1 line at new DETEC Center substation
220974 | 95151 | 170952 | ETEC | TX | Multi - Center - Center South 138 kV Line Tap | DETEC Center 138 kV New Substation | Zonal Reliability |  | 2028-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 11480000 |  | NTC - Commitment Window |  |  |  |  | Install 138 kV substation at DETEC Center
220950 | 95157 | 170953 | AEP | OK | Line - Lindsay Water Flood - Choctaw 138 kV New Line | Lindsay Water Flood - Choctaw 138 kV Ckt 1 New Line | Zonal Reliability |  | 2028-03-31 | 2025-11-07 | 2025 ITP |  |  | 0 | 13189000 |  | NTC - Commitment Window | 511513 | LINDSAY WATER | 511567 |  | Build a 6-mile 138 kV Ckt 1 line from Lindsay Water Flood to Choctaw |  | 6
220950 | 95157 | 170954 | AEP | OK | Line - Lindsay Water Flood - Choctaw 138 kV New Line | Lindsay Water Flood 138 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2028-03-31 | 2025-11-07 | 2025 ITP |  |  | 0 | 750000 |  | NTC - Commitment Window | 511513 | LINDSAY WATER |  |  | Expand or rebuild Lindsay Water Flood 138 kV substation
220950 | 95157 | 170955 | AEP | OK | Line - Lindsay Water Flood - Choctaw 138 kV New Line | Choctaw 138 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2028-03-31 | 2025-11-07 | 2025 ITP |  |  | 0 | 9500000 |  | NTC - Commitment Window | 511567 |  |  |  | Expand or rebuild Choctaw 138 kV substation
220974 | 95158 | 170958 | ETEC | TX | Multi - Darco - Nesbitt 138 kV New Line, Lake O The Pines - Nesbitt 138 kV Voltage Conversion | Darco - Nesbitt 138 kV Ckt 1 New Line | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 24430000 |  | NTC - Commitment Window | 509605 |  | 509627 |  | Build a 11.4-mile 138 kV Ckt 1 line from Darco to Nesbitt/Convert retired 69 kV line from Old Darco to Nesbit |  | 11.4
220974 | 95158 | 170959 | ETEC | TX | Multi - Darco - Nesbitt 138 kV New Line, Lake O The Pines - Nesbitt 138 kV Voltage Conversion | Darco 138 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 840000 |  | NTC - Commitment Window | 509605 |  |  |  | Expand or rebuild Darco 138 kV substation
220974 | 95158 | 170960 | ETEC | TX | Multi - Darco - Nesbitt 138 kV New Line, Lake O The Pines - Nesbitt 138 kV Voltage Conversion | Nesbitt 69 kV to 138 kV Voltage Conversion | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 11660000 |  | NTC - Commitment Window | 509627 |  |  |  | Convert the 69 kV Nesbitt substation to 138 kV
220974 | 95158 | 170961 | ETEC | TX | Multi - Darco - Nesbitt 138 kV New Line, Lake O The Pines - Nesbitt 138 kV Voltage Conversion | Darco 138 kV Ckt 1 Terminal Upgrade toward Nesbitt 69 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509605 |  | 509627 |  | Upgrade terminal equipment at Darco 138 kV substation for Ckt 1 toward Nesbitt 69 kV
220974 | 95158 | 170962 | ETEC | TX | Multi - Darco - Nesbitt 138 kV New Line, Lake O The Pines - Nesbitt 138 kV Voltage Conversion | Nesbitt 69 kV Ckt 1 Terminal Upgrade toward Darco 138 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509627 |  | 509605 |  | Upgrade terminal equipment at Nesbitt 69 kV substation for Ckt 1 toward Darco 138 kV
220974 | 95158 | 170963 | ETEC | TX | Multi - Darco - Nesbitt 138 kV New Line, Lake O The Pines - Nesbitt 138 kV Voltage Conversion | Remove Lake O The Pines - Nesbitt 69 kV Ckt 1 | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509623 |  | 509627 |  | Switch out 69 kV Ckt 1 line from Lake O The Pines to Nesbitt
220974 | 95158 | 170964 | ETEC | TX | Multi - Darco - Nesbitt 138 kV New Line, Lake O The Pines - Nesbitt 138 kV Voltage Conversion | Lake O The Pines - Nesbitt Ckt 1 138 kV Voltage Conversion | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 17580000 |  | NTC - Commitment Window | 509624 |  | 509627 |  | Convert the 69kV line from Lake O The Pines to Nesbitt to 138 kV |  |  |  | 8.1
220974 | 95158 | 170965 | ETEC | TX | Multi - Darco - Nesbitt 138 kV New Line, Lake O The Pines - Nesbitt 138 kV Voltage Conversion | Lake O The Pines 138 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 9310000 |  | NTC - Commitment Window | 509624 |  |  |  | Expand or rebuild Lake O The Pines 138 kV substation
220974 | 95158 | 170966 | ETEC | TX | Multi - Darco - Nesbitt 138 kV New Line, Lake O The Pines - Nesbitt 138 kV Voltage Conversion | Lake O The Pines 138 kV Ckt 1 Terminal Upgrade toward Nesbitt 69 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509624 |  | 509627 |  | Upgrade terminal equipment at Lake O The Pines 138 kV substation for Ckt 1 toward Nesbitt 69 kV
220974 | 95158 | 170967 | ETEC | TX | Multi - Darco - Nesbitt 138 kV New Line, Lake O The Pines - Nesbitt 138 kV Voltage Conversion | Nesbitt 69 kV Ckt 1 Terminal Upgrade toward Lake O The Pines 138 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509627 |  | 509624 |  | Upgrade terminal equipment at Nesbitt 69 kV substation for Ckt 1 toward Lake O The Pines 138 kV
220950 | 95158 | 170968 | AEP | TX | Multi - Darco - Nesbitt 138 kV New Line, Lake O The Pines - Nesbitt 138 kV Voltage Conversion | Brandy Branch 138 kV Breaker Additions | Zonal Reliability |  | 2031-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 275000 |  | NTC - Commitment Window | 508569 | SOUTHEAST MARSHALL |  |  | Add breakers at AEP-Brandy Branch Substation
220974 | 95158 | 170969 | ETEC | TX | Multi - Darco - Nesbitt 138 kV New Line, Lake O The Pines - Nesbitt 138 kV Voltage Conversion | Jefferson Metering Point 138 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 560000 |  | NTC - Commitment Window | 508835 | JEFFERSON SWITCHING 138KV |  |  | Upgrade relaying and communications system at Jefferson Metering Point 138 kV substation
220974 | 95158 | 170970 | ETEC | TX | Multi - Darco - Nesbitt 138 kV New Line, Lake O The Pines - Nesbitt 138 kV Voltage Conversion | Lake O The Pines 138 kV Ckt 1 Terminal Upgrade toward Jefferson Metering Point 138 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509624 |  | 508835 | JEFFERSON SWITCHING 138KV | Lake O The Pines 138 kV Ckt 1 Terminal Upgrade toward Jefferson Metering Point 138 kV
220974 | 95159 | 170971 | ETEC | TX | Line - Nichols - Hill-Wilson 69 kV Close Normally Open Line | Nichols - Hill-Wilson 69 kV Ckt NO Close in Normally Open Circuit | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509684 |  | 509687 |  | Close the 13-mile normally open 69 kV Ckt NO line from Nichols to Hill-Wilson
220974 | 95159 | 170972 | ETEC | TX | Line - Nichols - Hill-Wilson 69 kV Close Normally Open Line | Hill-Wilson 69 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 130000 |  | NTC - Commitment Window | 509687 |  |  |  | Expand or rebuild Hill-Wilson 69 kV substation
220974 | 95159 | 170973 | ETEC | TX | Line - Nichols - Hill-Wilson 69 kV Close Normally Open Line | Nichols 69 kV Ckt NO Terminal Upgrade toward Hill-Wilson 69 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509684 |  | 509687 |  | Upgrade terminal equipment at Nichols 69 kV substation for Ckt NO toward Hill-Wilson 69 kV
220974 | 95159 | 170974 | ETEC | TX | Line - Nichols - Hill-Wilson 69 kV Close Normally Open Line | Hill-Wilson 69 kV Ckt NO Terminal Upgrade toward Nichols 69 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509687 |  | 509684 |  | Upgrade terminal equipment at Hill-Wilson 69 kV substation for Ckt NO toward Nichols 69 kV
220974 | 95159 | 170975 | ETEC | TX | Line - Nichols - Hill-Wilson 69 kV Close Normally Open Line | Hill-Wilson 69 kV Ckt 1 Terminal Upgrade toward D.O. Aldridge 69 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509687 |  | 509678 |  | Upgrade terminal equipment at Hill-Wilson 69 kV substation for Ckt 1 toward D.O. Aldridge 69 kV
220974 | 95159 | 170976 | ETEC | TX | Line - Nichols - Hill-Wilson 69 kV Close Normally Open Line | D.O. Aldridge 69 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 3830000 |  | NTC - Commitment Window | 509678 |  |  |  | Expand or rebuild D.O Aldridge 69 kV substation
220974 | 95159 | 170977 | ETEC | TX | Line - Nichols - Hill-Wilson 69 kV Close Normally Open Line | D.O. Aldridge 69 kV Ckt 1 Terminal Upgrade toward Hill-Wilson 69 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509678 |  | 509687 |  | Upgrade terminal equipment at D.O. Aldridge 69 kV substation for Ckt 1 toward Hill-Wilson 69 kV
220974 | 95159 | 170978 | ETEC | TX | Line - Nichols - Hill-Wilson 69 kV Close Normally Open Line | D.O. Aldridge 69 kV Ckt 1 Terminal Upgrade toward Scroggins 69 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509678 |  | 508314 | SCROGGINS | Upgrade terminal equipment at D.O. Aldridge 69 kV substation for Ckt 1 toward Scroggins 69 kV
220972 | 95160 | 170980 | SPS | NM | Multi - Battle Axe - Wolfcamp Tap 115 kV DblCkt, Battle Axe - Ponderosa - Dollarhide 115 kV New Line | Battle Axe 115 kV Substation Expansion or Rebuild | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 22944668 |  | NTC - Commitment Window | 528040 |  |  |  | Expand or rebuild Battle Axe 115 kV substation
220972 | 95160 | 170981 | SPS | NM | Multi - Battle Axe - Wolfcamp Tap 115 kV DblCkt, Battle Axe - Ponderosa - Dollarhide 115 kV New Line | Wolfcamp Tap 115 kV Substation Expansion or Rebuild | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 16310948 |  | NTC - Commitment Window | 528235 |  |  |  | Expand or rebuild Wolfcamp Tap 115 kV substation
220972 | 95160 | 170982 | SPS | NM | Multi - Battle Axe - Wolfcamp Tap 115 kV DblCkt, Battle Axe - Ponderosa - Dollarhide 115 kV New Line | Battle Axe 115 kV Ckt 1 Terminal Upgrade toward Wolfcamp Tap 115 kV | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2112080 |  | NTC - Commitment Window | 528040 |  | 528235 |  | Upgrade terminal equipment at Battle Axe 115 kV substation for Ckt 1 toward Wolfcamp Tap 115 kV
220972 | 95160 | 170983 | SPS | NM | Multi - Battle Axe - Wolfcamp Tap 115 kV DblCkt, Battle Axe - Ponderosa - Dollarhide 115 kV New Line | Wolfcamp Tap 115 kV Ckt 1 Terminal Upgrade toward Battle Axe 115 kV | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 1965291 |  | NTC - Commitment Window | 528235 |  | 528040 |  | Upgrade terminal equipment at Wolfcamp Tap 115 kV substation for Ckt 1 toward Battle Axe 115 kV
220972 | 95160 | 170985 | SPS | NM | Multi - Battle Axe - Wolfcamp Tap 115 kV DblCkt, Battle Axe - Ponderosa - Dollarhide 115 kV New Line | Battle Axe 115 kV Ckt 2 Terminal Upgrade toward Wolfcamp Tap 115 kV | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2108426 |  | NTC - Commitment Window | 528040 |  | 528235 |  | Upgrade terminal equipment at Battle Axe 115 kV substation for Ckt 2 toward Wolfcamp Tap 115 kV
220972 | 95160 | 170986 | SPS | NM | Multi - Battle Axe - Wolfcamp Tap 115 kV DblCkt, Battle Axe - Ponderosa - Dollarhide 115 kV New Line | Wolfcamp Tap 115 kV Ckt 2 Terminal Upgrade toward Battle Axe 115 kV | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 1541844 |  | NTC - Commitment Window | 528235 |  | 528040 |  | Upgrade terminal equipment at Wolfcamp Tap 115 kV substation for Ckt 2 toward Battle Axe 115 kV
220972 | 95160 | 170988 | SPS | NM | Multi - Battle Axe - Wolfcamp Tap 115 kV DblCkt, Battle Axe - Ponderosa - Dollarhide 115 kV New Line | Ponderosa 115 kV Substation Expansion or Rebuild | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 14354533 |  | NTC - Commitment Window | 528240 |  |  |  | Expand or rebuild Ponderosa 115 kV substation
220972 | 95160 | 170989 | SPS | NM | Multi - Battle Axe - Wolfcamp Tap 115 kV DblCkt, Battle Axe - Ponderosa - Dollarhide 115 kV New Line | Battle Axe 115 kV Ckt 1 Terminal Upgrade toward Ponderosa 115 kV | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2108814 |  | NTC - Commitment Window | 528040 |  | 528240 |  | Upgrade terminal equipment at Battle Axe 115 kV substation for Ckt 1 toward Ponderosa 115 kV
220972 | 95160 | 170990 | SPS | NM | Multi - Battle Axe - Wolfcamp Tap 115 kV DblCkt, Battle Axe - Ponderosa - Dollarhide 115 kV New Line | Ponderosa 115 kV Ckt 1 Terminal Upgrade toward Battle Axe 115 kV | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 1576377 |  | NTC - Commitment Window | 528240 |  | 528040 |  | Upgrade terminal equipment at Ponderosa 115 kV substation for Ckt 1 toward Battle Axe 115 kV
220972 | 95160 | 170992 | SPS | NM | Multi - Battle Axe - Wolfcamp Tap 115 kV DblCkt, Battle Axe - Ponderosa - Dollarhide 115 kV New Line | Dollarhide 115 kV Substation Expansion or Rebuild | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 14899626 |  | NTC - Commitment Window | 528561 | Dollarhide Sub 115 kV |  |  | Expand or rebuild Dollarhide 115 kV substation
220972 | 95160 | 170993 | SPS | NM | Multi - Battle Axe - Wolfcamp Tap 115 kV DblCkt, Battle Axe - Ponderosa - Dollarhide 115 kV New Line | Ponderosa 115 kV Ckt 1 Terminal Upgrade toward Dollarhide 115 kV | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2107928 |  | NTC - Commitment Window | 528240 |  | 528561 | Dollarhide Sub 115 kV | Upgrade terminal equipment at Ponderosa 115 kV substation for Ckt 1 toward Dollarhide 115 kV
220972 | 95160 | 170994 | SPS | NM | Multi - Battle Axe - Wolfcamp Tap 115 kV DblCkt, Battle Axe - Ponderosa - Dollarhide 115 kV New Line | Dollarhide 115 kV Ckt 1 Terminal Upgrade toward Ponderosa 115 kV | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2003173 |  | NTC - Commitment Window | 528561 | Dollarhide Sub 115 kV | 528240 |  | Upgrade terminal equipment at Dollarhide 115 kV substation for Ckt 1 toward Ponderosa 115 kV
220972 | 95161 | 170995 | SPS | NM | Multi - Hobbs - Kiowa 345 kV Line Tap at Lea National 115 kV | Lea National 115 kV Substation Expansion or Rebuild | Regional Reliability |  | 2028-12-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 24399993.53 |  | NTC - Commitment Window | 528399 | Lea National Sub 115 kV |  |  | Expand or rebuild Lea National 115 kV substation
220972 | 95162 | 170996 | SPS | NM | Multi - Kiowa - Road Runner 345 kV Line Tap at Sand Dunes 115 kV | Kiowa - Road Runner 345 kV Line Tap | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 4120902 |  | NTC - Commitment Window | 527965 |  | 528027 | Road Runner 345 kV | Tap the existing Kiowa - Road Runner 345 kV Ckt 1 line at new Sand Dunes substation
220972 | 95162 | 170997 | SPS | NM | Multi - Kiowa - Road Runner 345 kV Line Tap at Sand Dunes 115 kV | Sand Dunes 345 kV New Substation | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 17445707 |  | NTC - Commitment Window |  |  |  |  | Install 345 kV substation at Sand Dunes
220972 | 95162 | 170998 | SPS | NM | Multi - Kiowa - Road Runner 345 kV Line Tap at Sand Dunes 115 kV | Sand Dunes 115/345 kV Ckt 1 Transformer | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 17651761 |  | NTC - Commitment Window | 528016 | Sand Dunes Sub 115 kV |  |  | Install new 115/345 kV Ckt 1 transformer at Sand Dunes
220972 | 95162 | 170999 | SPS | NM | Multi - Kiowa - Road Runner 345 kV Line Tap at Sand Dunes 115 kV | Sand Dunes 115 kV Substation Expansion or Rebuild | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 25871328 |  | NTC - Commitment Window | 528016 | Sand Dunes Sub 115 kV |  |  | Expand or rebuild Sand Dunes 115 kV substation
220972 | 95162 | 171000 | SPS | NM | Multi - Kiowa - Road Runner 345 kV Line Tap at Sand Dunes 115 kV | Sand Dunes 115 kV Ckt 1 Terminal Upgrade toward Sand Dunes 345 kV | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 703866 |  | NTC - Commitment Window | 528016 | Sand Dunes Sub 115 kV |  |  | Upgrade terminal equipment at Sand Dunes 115 kV substation for Ckt 1 toward Sand Dunes 345 kV
220972 | 95162 | 171001 | SPS | NM | Multi - Kiowa - Road Runner 345 kV Line Tap at Sand Dunes 115 kV | Sand Dunes 345 kV Ckt 1 Terminal Upgrade toward Sand Dunes 115 kV | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 946024 |  | NTC - Commitment Window |  |  | 528016 | Sand Dunes Sub 115 kV | Upgrade terminal equipment at Sand Dunes 345 kV substation for Ckt 1 toward Sand Dunes 115 kV
220965 | 95163 | 171002 | OGE | OK | Multi - Muskogee - Ft. Smith 345 kV Line Tap, Pecan Creek - Keefton 345 kV New Line | Pecan Creek 345 kV Substation Expansion or Rebuild | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 515235 | PECAN CREEK 345 |  |  | Expand or rebuild Pecan Creek 345 kV substation
220959 | 95164 | 171003 | NPPD | NE | XFR - Axtell 345/115 kV New Transformer | Axtell 115/345 kV Ckt 2 Transformer | Economic |  | 2033-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 15500000 |  | NTC - Commitment Window | 640066 | Axtell | 640065 | Axtell | Install new 115/345 kV Ckt 2 transformer at Axtell
220959 | 95164 | 171006 | NPPD | NE | XFR - Axtell 345/115 kV New Transformer | Axtell 115 kV Ckt 2 Terminal Upgrade toward Axtell 345 kV | Economic |  | 2033-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 16400000 |  | NTC - Commitment Window | 640066 | Axtell | 640065 | Axtell | Upgrade terminal equipment at Axtell 115 kV substation for Ckt 2 toward Axtell 345 kV
220959 | 95164 | 171007 | NPPD | NE | XFR - Axtell 345/115 kV New Transformer | Axtell 345 kV Ckt 2 Terminal Upgrade toward Axtell 115 kV | Economic |  | 2033-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 8000000 |  | NTC - Commitment Window | 640065 | Axtell | 640066 | Axtell | Upgrade terminal equipment at Axtell 345 kV substation for Ckt 2 toward Axtell 115 kV
220963 | 95165 | 171008 | EKC | KS | Multi - Altamont Tap - Katy 69 kV Rebuild, Katy 69 kV Convert Substation | Altamont Tap - Katy 69 kV Ckt 1 Rebuild | Zonal Reliability |  | 2027-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 17738055 |  | NTC - Commitment Window | 533672 | ALTAMONT SWITCHING STATION 69 KV | 533704 | PARSONS 69 KV | Rebuild 10-mile Ckt 1 line from Altamont Tap 69 kV substation to Katy 69 kV substation |  |  | 10
220963 | 95165 | 171009 | EKC | KS | Multi - Altamont Tap - Katy 69 kV Rebuild, Katy 69 kV Convert Substation | Altamont Tap 69 kV Ckt 1 Terminal Upgrade toward Katy 69 kV | Zonal Reliability |  | 2027-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 533672 | ALTAMONT SWITCHING STATION 69 KV | 533704 | PARSONS 69 KV | Upgrade terminal equipment at Altamont Tap 69 kV substation for Ckt 1 toward Katy 69 kV
220963 | 95165 | 171010 | EKC | KS | Multi - Altamont Tap - Katy 69 kV Rebuild, Katy 69 kV Convert Substation | Katy 69 kV Ckt 1 Terminal Upgrade toward Altamont Tap 69 kV | Zonal Reliability |  | 2027-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 806231 |  | NTC - Commitment Window | 533704 | PARSONS 69 KV | 533672 | ALTAMONT SWITCHING STATION 69 KV | Upgrade terminal equipment at Katy 69 kV substation for Ckt 1 toward Altamont Tap 69 kV
220963 | 95165 | 171011 | EKC | KS | Multi - Altamont Tap - Katy 69 kV Rebuild, Katy 69 kV Convert Substation | Katy 69 kV New Substation | Zonal Reliability |  | 2027-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 10704941 |  | NTC - Commitment Window | 533704 | PARSONS 69 KV |  |  | Install 69 kV substation at Katy
220950 | 95166 | 171012 | AEP | OK | Line - Duncan - Duncan Tap - Duncan Eastside - Rush Springs Tap - Marlow 138 kV Rebuild | Duncan - Duncan Tap 138 kV Ckt 1 Rebuild | Zonal Reliability |  | 2026-05-21 | 2025-11-07 | 2025 ITP |  |  | 0 | 30500000 |  | NTC - Commitment Window | 511453 | DUNCAN 138KV | 511552 |  | Rebuild 1.6-mile Ckt 1 line from Duncan 138 kV substation to Duncan Tap 138 kV substation |  |  | 1.6
220950 | 95167 | 171027 | AEP | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Camp County POD 138 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2034-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 10000000 |  | NTC - Commitment Window | 508286 | CAMP COUNTY REC |  |  | Expand or rebuild Camp County POD 138 kV substation
220974 | 95167 | 171028 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Ebenezer 69 kV to 138 kV Voltage Conversion | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 8370000 |  | NTC - Commitment Window | 509609 |  |  |  | Convert the existing 69 kV Ebenezer substation to 138 kV
220974 | 95167 | 171029 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Camp County POD 138 kV Ckt 1 Terminal Upgrade toward Ebenezer 138 kV | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 508286 | CAMP COUNTY REC | 509609 |  | Upgrade terminal equipment at Camp County POD 138 kV substation for Ckt 1 toward Ebenezer 138 kV
220974 | 95167 | 171030 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Ebenezer 138 kV Ckt 1 Terminal Upgrade toward Camp County POD 138 kV | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509609 |  | 508286 | CAMP COUNTY REC | Upgrade terminal equipment at Ebenezer 138 kV substation for Ckt 1 toward Camp County POD 138 kV
220974 | 95167 | 171031 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Cox - Pittsburg 69 kV Ckt 1 Reroute Line | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 2400000 |  | NTC - Commitment Window | 509604 |  |  |  | Reroute the existing 10-mile 69 kV Ckt 1 line from Cox to Pittsburg |  | 10
220974 | 95167 | 171032 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Cox 69 kV Ckt 1 Terminal Upgrade toward Pittsburg 69 kV | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509604 |  |  |  | Upgrade terminal equipment at Cox 69 kV substation for Ckt 1 toward Pittsburg 69 kV
220974 | 95167 | 171033 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Pittsburg 69 kV Ckt 1 Terminal Upgrade toward Cox 69 kV | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window |  |  | 509604 |  | Upgrade terminal equipment at Pittsburg 69 kV substation for Ckt 1 toward Cox 69 kV
220974 | 95167 | 171034 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Remove Ebenezer - Camp County Tap 69 kV Ckt 1 | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509609 |  | 509619 |  | Switch out 69 kV Ckt 1 line from Ebenezer to Camp County Tap
220974 | 95167 | 171035 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Remove Ebenezer - Pittsburg 69 kV Ckt 1 | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509609 |  | 509631 |  | Switch out 69 kV Ckt 1 line from Ebenezer to Pittsburg
220974 | 95167 | 171036 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Ebenezer - Pittsburg Ckt 1 138 kV Voltage Conversion | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 15730000 |  | NTC - Commitment Window | 509609 |  | 509631 |  | Convert the Ebenezer - Pittsburg line from 69 kV to 138 kV |  |  |  | 6.85
220974 | 95167 | 171038 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Ebenezer 138 kV Ckt 1 Terminal Upgrade toward Pittsburg 138 kV | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509609 |  | 509631 |  | Upgrade terminal equipment at Ebenezer 138 kV substation for Ckt 1 toward Pittsburg 138 kV
220974 | 95167 | 171039 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Pittsburg 138 kV Ckt 1 Terminal Upgrade toward Ebenezer 138 kV | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509631 |  | 509609 |  | Upgrade terminal equipment at Pittsburg 138 kV substation for Ckt 1 toward Ebenezer 138 kV
220974 | 95167 | 171040 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Remove Gilmer - Pittsburg 69 kV Ckt NO | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509611 |  | 509631 |  | Switch out 69 kV Ckt NO line from Little Mound to Pittsburg
220974 | 95167 | 171041 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Gilmer - Pittsburg (Cox Tap) 138 kV Ckt 1 Voltage Conversion | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 29300000 |  | NTC - Commitment Window | 509612 |  | 509631 |  | Convert a 15.2 mile section of 69 kV transmission line to 138 kV from Gilmer to Pittsburg (Cox Tap) |  |  |  | 15.2
220974 | 95167 | 171042 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Gilmer 138 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 9290000 |  | NTC - Commitment Window | 509612 |  |  |  | Expand or rebuild Gilmer 138 kV substation
220974 | 95167 | 171043 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Gilmer 138 kV Ckt 1 Terminal Upgrade toward Pittsburg 138 kV | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509612 |  | 509631 |  | Upgrade terminal equipment at Gilmer 138 kV substation for Ckt 1 toward Pittsburg 138 kV
220974 | 95167 | 171044 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Pittsburg 138 kV Ckt 1 Terminal Upgrade toward Gilmer 138 kV | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509631 |  | 509612 |  | Upgrade terminal equipment at Pittsburg 138 kV substation for Ckt 1 toward Gilmer 138 kV
220974 | 95167 | 171046 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Pittsburg 138 kV New Substation | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 15080000 |  | NTC - Commitment Window | 509631 |  |  |  | Install 138 kV substation at Pittsburg
220974 | 95167 | 171047 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Pittsburg 69 kV Upgrade Substation | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window |  |  |  |  | Upgrade the existing 69 kV substation at Pittsburg
220974 | 95167 | 171048 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Pittsburg 138/69 kV Ckt 1 Transformer | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509631 |  |  |  | Install new 138/69 kV Ckt 1 transformer at Pittsburg
220974 | 95167 | 171049 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Pittsburg 138 kV Ckt 1 Terminal Upgrade toward Pittsburg 69 kV | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509631 |  |  |  | Upgrade terminal equipment at Pittsburg 138 kV substation for Ckt 1 toward Pittsburg 69 kV
220974 | 95167 | 171050 | ETEC | TX | Multi - Camp County POD - Ebenezer - Pittsburg - Gilmer 138 kV Voltage Conversion | Pittsburg 69 kV Ckt 1 Terminal Upgrade toward Pittsburg 138 kV | Zonal Reliability |  | 2034-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window |  |  | 509631 |  | Upgrade terminal equipment at Pittsburg 69 kV substation for Ckt 1 toward Pittsburg 138 kV
220972 | 95161 | 171051 | SPS | NM | Multi - Hobbs - Kiowa 345 kV Line Tap at Lea National 115 kV | Hobbs - Kiowa 345 kV Line Tap | Regional Reliability |  | 2028-12-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2977710.88 |  | NTC - Commitment Window | 527896 | Hobbs Interchange 345 kV | 527965 |  | Tap the existing Hobbs - Kiowa 345 kV Ckt 1 line at new Lea National substation
220972 | 95161 | 171052 | SPS | NM | Multi - Hobbs - Kiowa 345 kV Line Tap at Lea National 115 kV | Lea National 345 kV New Substation | Regional Reliability |  | 2028-12-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 26127351.04 |  | NTC - Commitment Window |  |  |  |  | Install 345 kV substation at Lea National
220972 | 95161 | 171053 | SPS | NM | Multi - Hobbs - Kiowa 345 kV Line Tap at Lea National 115 kV | Lea National 115/345 kV Ckt 1 Transformer | Regional Reliability |  | 2028-12-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 16908188.08 |  | NTC - Commitment Window | 528399 | Lea National Sub 115 kV |  |  | Install new 115/345 kV Ckt 1 transformer at Lea National
220972 | 95161 | 171054 | SPS | NM | Multi - Hobbs - Kiowa 345 kV Line Tap at Lea National 115 kV | Lea National 115 kV Ckt 1 Terminal Upgrade toward Lea National 345 kV | Regional Reliability |  | 2028-12-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 851206.91 |  | NTC - Commitment Window | 528399 | Lea National Sub 115 kV |  |  | Upgrade terminal equipment at Lea National 115 kV substation for Ckt 1 toward Lea National 345 kV
220972 | 95161 | 171055 | SPS | NM | Multi - Hobbs - Kiowa 345 kV Line Tap at Lea National 115 kV | Lea National 345 kV Ckt 1 Terminal Upgrade toward Lea National 115 kV | Regional Reliability |  | 2028-12-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 1022599.18 |  | NTC - Commitment Window |  |  | 528399 | Lea National Sub 115 kV | Upgrade terminal equipment at Lea National 345 kV substation for Ckt 1 toward Lea National 115 kV
220972 | 95161 | 171056 | SPS | NM | Multi - Hobbs - Kiowa 345 kV Line Tap at Lea National 115 kV | Lea National 115/345 kV Ckt 2 Transformer | Regional Reliability |  | 2028-12-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 16908188.08 |  | NTC - Commitment Window | 528399 | Lea National Sub 115 kV |  |  | Install new 115/345 kV Ckt 2 transformer at Lea National
220972 | 95161 | 171057 | SPS | NM | Multi - Hobbs - Kiowa 345 kV Line Tap at Lea National 115 kV | Lea National 115 kV Ckt 2 Terminal Upgrade toward Lea National 345 kV | Regional Reliability |  | 2028-12-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 973458.56 |  | NTC - Commitment Window | 528399 | Lea National Sub 115 kV |  |  | Upgrade terminal equipment at Lea National 115 kV substation for Ckt 2 toward Lea National 345 kV
220972 | 95161 | 171058 | SPS | NM | Multi - Hobbs - Kiowa 345 kV Line Tap at Lea National 115 kV | Lea National 345 kV Ckt 2 Terminal Upgrade toward Lea National 115 kV | Regional Reliability |  | 2028-12-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 900573.18 |  | NTC - Commitment Window |  |  | 528399 | Lea National Sub 115 kV | Upgrade terminal equipment at Lea National 345 kV substation for Ckt 2 toward Lea National 115 kV
220965 | 95163 | 171059 | OGE | OK | Multi - Muskogee - Ft. Smith 345 kV Line Tap, Pecan Creek - Keefton 345 kV New Line | Muskogee - Ft. Smith 345 kV Line Tap | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 500000 |  | NTC - Commitment Window | 515224 | MUSKOGEE 345 | 515302 | FT SMITH 345 | Tap the existing Muskogee - Ft. Smith 345 kV Ckt 1 line at new Keefton substation
220965 | 95163 | 171060 | OGE | OK | Multi - Muskogee - Ft. Smith 345 kV Line Tap, Pecan Creek - Keefton 345 kV New Line | Muskogee - Oktaha 345 kV Line Tap | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 500000 |  | NTC - Commitment Window | 515224 | MUSKOGEE 345 | 516091 |  | Tap the existing Muskogee - Oktaha 345 kV Ckt 1 line at new Keefton substation
220965 | 95163 | 171061 | OGE | OK | Multi - Muskogee - Ft. Smith 345 kV Line Tap, Pecan Creek - Keefton 345 kV New Line | Muskogee 345 kV Ckt 2 Terminal Upgrade toward Keefton 345 kV | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 10000 |  | NTC - Commitment Window | 515224 | MUSKOGEE 345 |  |  | Upgrade terminal equipment at Muskogee 345 kV substation for Ckt 2 toward Keefton 345 kV
220965 | 95163 | 171062 | OGE | OK | Multi - Muskogee - Ft. Smith 345 kV Line Tap, Pecan Creek - Keefton 345 kV New Line | Keefton 345 kV Ckt 2 Terminal Upgrade toward Muskogee 345 kV | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window |  |  | 515224 | MUSKOGEE 345 | Upgrade terminal equipment at Keefton 345 kV substation for Ckt 2 toward Muskogee 345 kV
220965 | 95163 | 171063 | OGE | OK | Multi - Muskogee - Ft. Smith 345 kV Line Tap, Pecan Creek - Keefton 345 kV New Line | Pecan Creek - Keefton 345 kV Ckt 1 New Line | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 37332865 |  | NTC - Commitment Window | 515235 | PECAN CREEK 345 |  |  | Build a 11.3-mile 345 kV Ckt 1 line from Pecan Creek to Keefton utilizing the existing 8.8 mile de-energized line and extending an additional 2.5 miles |  | 11.3
220965 | 95163 | 171064 | OGE | OK | Multi - Muskogee - Ft. Smith 345 kV Line Tap, Pecan Creek - Keefton 345 kV New Line | Pecan Creek 345 kV Ckt 1 Terminal Upgrade toward Keefton 345 kV | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 8000000 |  | NTC - Commitment Window | 515235 | PECAN CREEK 345 |  |  | Upgrade terminal equipment at Pecan Creek 345 kV substation for Ckt 1 toward Keefton 345 kV
220965 | 95163 | 171065 | OGE | OK | Multi - Muskogee - Ft. Smith 345 kV Line Tap, Pecan Creek - Keefton 345 kV New Line | Keefton 345 kV Ckt 1 Terminal Upgrade toward Pecan Creek 345 kV | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window |  |  | 515235 | PECAN CREEK 345 | Upgrade terminal equipment at Keefton 345 kV substation for Ckt 1 toward Pecan Creek 345 kV
220965 | 95163 | 171066 | OGE | OK | Multi - Muskogee - Ft. Smith 345 kV Line Tap, Pecan Creek - Keefton 345 kV New Line | Keefton 345 kV New Substation | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 21000000 |  | NTC - Commitment Window |  |  |  |  | Install 345 kV substation at Keefton
220974 | 95168 | 171068 | ETEC | TX | Multi - Lake Hawkins - Piney Wood - Little Mound 138 kV New Line, Little Mound - Gilmer 138 kV Conv | Lake Hawkins - Piney Wood 138 kV Ckt 1 New Line | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 23600000 |  | NTC - Commitment Window | 508358 | LAKE HAWKINS | 509630 |  | Build a 9.5-mile 138 kV Ckt 1 line from Lake Hawkins to Piney Wood |  | 9.5
220974 | 95168 | 171069 | ETEC | TX | Multi - Lake Hawkins - Piney Wood - Little Mound 138 kV New Line, Little Mound - Gilmer 138 kV Conv | Lake Hawkins 138 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 10050000 |  | NTC - Commitment Window | 508358 | LAKE HAWKINS |  |  | Expand or rebuild Lake Hawkins 138 kV substation
220974 | 95168 | 171070 | ETEC | TX | Multi - Lake Hawkins - Piney Wood - Little Mound 138 kV New Line, Little Mound - Gilmer 138 kV Conv | Piney Wood Substation Voltage Conversion from 69 kV to 138 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509630 |  |  |  | Convert the existing 69 kV Piney Wood substation to 138 kV
220974 | 95168 | 171071 | ETEC | TX | Multi - Lake Hawkins - Piney Wood - Little Mound 138 kV New Line, Little Mound - Gilmer 138 kV Conv | Lake Hawkins 138 kV Ckt 1 Terminal Upgrade toward Piney Wood 138 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 508358 | LAKE HAWKINS | 509630 |  | Upgrade terminal equipment at Lake Hawkins 138 kV substation for Ckt 1 toward Piney Wood 138 kV
220974 | 95168 | 171072 | ETEC | TX | Multi - Lake Hawkins - Piney Wood - Little Mound 138 kV New Line, Little Mound - Gilmer 138 kV Conv | Piney Wood 138 kV Ckt 1 Terminal Upgrade toward Lake Hawkins 138 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509630 |  | 508358 | LAKE HAWKINS | Upgrade terminal equipment at Piney Wood 138 kV substation for Ckt 1 toward Lake Hawkins 138 kV
220974 | 95168 | 171073 | ETEC | TX | Multi - Lake Hawkins - Piney Wood - Little Mound 138 kV New Line, Little Mound - Gilmer 138 kV Conv | Little Mound - Gilmer Ckt 1 138 kV Voltage Conversion | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 17790000 |  | NTC - Commitment Window | 509626 |  | 509612 |  | Convert the Little Mound - Gilmer Ckt 1 line from 69 kV to 138 kV |  |  |  | 8.5
220974 | 95168 | 171074 | ETEC | TX | Multi - Lake Hawkins - Piney Wood - Little Mound 138 kV New Line, Little Mound - Gilmer 138 kV Conv | Gilmer 69 kV Substation Voltage Conversion | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509611 |  |  |  | Convert the existing 69 kV Gilmer substation to 138 kV
220974 | 95168 | 171075 | ETEC | TX | Multi - Lake Hawkins - Piney Wood - Little Mound 138 kV New Line, Little Mound - Gilmer 138 kV Conv | Little Mound 138 kV Ckt 1 Terminal Upgrade toward Gilmer 138 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509611 |  | 509612 |  | Upgrade terminal equipment at Little Mound 138 kV substation for Ckt 1 toward Gilmer 138 kV
220974 | 95168 | 171076 | ETEC | TX | Multi - Lake Hawkins - Piney Wood - Little Mound 138 kV New Line, Little Mound - Gilmer 138 kV Conv | Gilmer 138 kV Ckt 1 Terminal Upgrade toward Little Mound 138 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509612 |  | 509611 |  | Upgrade terminal equipment at Gilmer 138 kV substation for Ckt 1 toward Little Mound 138 kV
220974 | 95168 | 171077 | ETEC | TX | Multi - Lake Hawkins - Piney Wood - Little Mound 138 kV New Line, Little Mound - Gilmer 138 kV Conv | Little Mound - Piney Wood Ckt 1 138 kV Voltage Conversion | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 14600000 |  | NTC - Commitment Window | 509611 |  | 509630 |  | Convert the Little Mound - Piney Wood Ckt 1 line from 69 kV to 138 kV |  |  |  | 7
220974 | 95168 | 171078 | ETEC | TX | Multi - Lake Hawkins - Piney Wood - Little Mound 138 kV New Line, Little Mound - Gilmer 138 kV Conv | Little Mound 138 kV Ckt 1 Terminal Upgrade toward Piney Wood 138 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509611 |  | 509630 |  | Upgrade terminal equipment at Little Mound 138 kV substation for Ckt 1 toward Piney Wood 138 kV
220974 | 95168 | 171079 | ETEC | TX | Multi - Lake Hawkins - Piney Wood - Little Mound 138 kV New Line, Little Mound - Gilmer 138 kV Conv | Piney Wood 138 kV Ckt 1 Terminal Upgrade toward Little Mound 138 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509630 |  | 509626 |  | Upgrade terminal equipment at Piney Wood 138 kV substation for Ckt 1 toward Little Mound 138 kV
220974 | 95168 | 171080 | ETEC | TX | Multi - Lake Hawkins - Piney Wood - Little Mound 138 kV New Line, Little Mound - Gilmer 138 kV Conv | Gilmer 138 kV New Substation | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509611 |  |  |  | Install 138 kV substation at Gilmer
220974 | 95168 | 171081 | ETEC | TX | Multi - Lake Hawkins - Piney Wood - Little Mound 138 kV New Line, Little Mound - Gilmer 138 kV Conv | Piney Wood 138 kV New Substation | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 8120000 |  | NTC - Commitment Window | 509630 |  |  |  | Install 138 kV substation at Piney Wood
220974 | 95168 | 171082 | ETEC | TX | Multi - Lake Hawkins - Piney Wood - Little Mound 138 kV New Line, Little Mound - Gilmer 138 kV Conv | Remove Gilmer 69/138 kV Ckt 1 Transformer | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509611 |  | 509612 |  | Switch out 69/138 kV Ckt 1 transformer at Little Mound
220974 | 95168 | 171083 | ETEC | TX | Multi - Lake Hawkins - Piney Wood - Little Mound 138 kV New Line, Little Mound - Gilmer 138 kV Conv | Little Mound 138/69 kV Ckt 2 Transformer | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509611 |  | 509626 |  | Install new 138/69 kV Ckt 2 transformer at Little Mound
220974 | 95168 | 171084 | ETEC | TX | Multi - Lake Hawkins - Piney Wood - Little Mound 138 kV New Line, Little Mound - Gilmer 138 kV Conv | Little Mound 138 kV New Substation | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 15750000 |  | NTC - Commitment Window | 509626 |  |  |  | Install 138 kV substation at Little Mound
220974 | 95168 | 171085 | ETEC | TX | Multi - Lake Hawkins - Piney Wood - Little Mound 138 kV New Line, Little Mound - Gilmer 138 kV Conv | Little Mound 138 kV Ckt 2 Terminal Upgrade toward Little Mound 69 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509611 |  | 509626 |  | Upgrade terminal equipment at Little Mound 138 kV substation for Ckt 2 toward Little Mound 69 kV
220974 | 95168 | 171086 | ETEC | TX | Multi - Lake Hawkins - Piney Wood - Little Mound 138 kV New Line, Little Mound - Gilmer 138 kV Conv | Little Mound 69 kV Ckt 2 Terminal Upgrade toward Little Mound 138 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509626 |  | 509611 |  | Upgrade terminal equipment at Little Mound 69 kV substation for Ckt 2 toward Little Mound 138 kV
220974 | 95169 | 171087 | ETEC | TX | Multi - Loop in 138 kV Diana East - Diana -Noonday - Hallsville - Gum Springs | URECC-Gum Springs to URECC-Hallsville 138 kV Ckt 1 New Line | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 12090000 |  | NTC - Commitment Window |  |  | 509615 |  | Build a 5.3-mile 138 kV Ckt 1 line from URECC-Gum Springs to URECC-Hallsville |  | 5.3
220974 | 95169 | 171088 | ETEC | TX | Multi - Loop in 138 kV Diana East - Diana -Noonday - Hallsville - Gum Springs | URECC-Gum Springs 138 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 10500000 |  | NTC - Commitment Window |  |  |  |  | Expand or rebuild URECC-Gum Springs 138 kV substation
220974 | 95169 | 171089 | ETEC | TX | Multi - Loop in 138 kV Diana East - Diana -Noonday - Hallsville - Gum Springs | URECC Hallsville 138 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 2970000 |  | NTC - Commitment Window | 509615 |  |  |  | Expand or rebuild URECC-Hallsville 138 kV substation
220974 | 95169 | 171090 | ETEC | TX | Multi - Loop in 138 kV Diana East - Diana -Noonday - Hallsville - Gum Springs | URECC-Gum Springs 138 kV Ckt 1 Terminal Upgrade toward URECC-Hallsville 138 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window |  |  | 509615 |  | Upgrade terminal equipment at URECC-Gum Springs 138 kV substation for Ckt 1 toward URECC-Hallsville138 kV
220974 | 95169 | 171091 | ETEC | TX | Multi - Loop in 138 kV Diana East - Diana -Noonday - Hallsville - Gum Springs | URECC-Hallsville 138 kV Ckt 1 Terminal Upgrade toward URECC-Gum Springs 138 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509615 |  |  |  | Upgrade terminal equipment at URECC-Hallsville 138 kV substation for Ckt 1 toward URECC-Gum Springs 138 kV
220950 | 95169 | 171092 | AEP | TX | Multi - Loop in 138 kV Diana East - Diana -Noonday - Hallsville - Gum Springs | AEP-Diana East 138 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2031-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 508831 | DIANA 138KV |  |  | Expand or rebuild AEP-Diana East 138 kV substation
220974 | 95169 | 171093 | ETEC | TX | Multi - Loop in 138 kV Diana East - Diana -Noonday - Hallsville - Gum Springs | URECC-Diana 138 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 10310000 |  | NTC - Commitment Window | 509607 |  |  |  | Expand or rebuild URECC-Diana 138 kV substation
220950 | 95169 | 171094 | AEP | TX | Multi - Loop in 138 kV Diana East - Diana -Noonday - Hallsville - Gum Springs | AEP-Diana East 138 kV Ckt 1 Terminal Upgrade toward URECC-Diana 138 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 1000000 |  | NTC - Commitment Window | 508831 | DIANA 138KV | 509607 |  | Upgrade terminal equipment at AEP-Diana East 138 kV substation for Ckt 1 toward URECC-Diana 138 kV
220974 | 95169 | 171095 | ETEC | TX | Multi - Loop in 138 kV Diana East - Diana -Noonday - Hallsville - Gum Springs | URECC-Diana 138 kV Ckt 1 Terminal Upgrade toward AEP-Diana East 138 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509607 |  | 508831 | DIANA 138KV | Upgrade terminal equipment at URECC-Diana 138 kV substation for Ckt 1 toward AEP-Diana East 138 kV
220974 | 95169 | 171096 | ETEC | TX | Multi - Loop in 138 kV Diana East - Diana -Noonday - Hallsville - Gum Springs | Remove AEP-Diana East - Diana Switch 138 kV Ckt 1 | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 508831 | DIANA 138KV | 509639 |  | Switch out 138 kV Ckt 1 line from AEP-Diana East to Diana Switch
220974 | 95169 | 171097 | ETEC | TX | Multi - Loop in 138 kV Diana East - Diana -Noonday - Hallsville - Gum Springs | URECC-Diana - Noonday 138 kV Ckt 1 Retermination | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 1730000 |  | NTC - Commitment Window | 509607 |  | 509628 |  | Reterminate the 138 kV line from Noonday to URECC-Diana Switch as Noonday to URECC-Diana. Use shared double circuit structure with 138 kV line from URECC-Diana to URECC-Diana Metering Point |  | 8.3
220974 | 95169 | 171098 | ETEC | TX | Multi - Loop in 138 kV Diana East - Diana -Noonday - Hallsville - Gum Springs | Noonday 138 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 5790000 |  | NTC - Commitment Window | 509628 |  |  |  | Expand or rebuild Noonday 138 kV substation
220974 | 95169 | 171099 | ETEC | TX | Multi - Loop in 138 kV Diana East - Diana -Noonday - Hallsville - Gum Springs | URECC-Diana 138 kV Ckt 1 Terminal Upgrade toward Noonday 138 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509607 |  | 509628 |  | Upgrade terminal equipment at URECC-Diana 138 kV substation for Ckt 1 toward Noonday 138 kV
220974 | 95169 | 171100 | ETEC | TX | Multi - Loop in 138 kV Diana East - Diana -Noonday - Hallsville - Gum Springs | Noonday 138 kV Ckt 1 Terminal Upgrade toward URECC-Diana 138 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 2020000 |  | NTC - Commitment Window | 509628 |  | 509607 |  | Upgrade terminal equipment at Noonday 138 kV substation for Ckt 1 toward URECC-Diana 138 kV
220974 | 95169 | 171101 | ETEC | TX | Multi - Loop in 138 kV Diana East - Diana -Noonday - Hallsville - Gum Springs | URECC-Hallsville - Noonday 138 kV Ckt 1 Rebuild | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 14010000 |  | NTC - Commitment Window | 509615 |  | 509628 |  | Rebuild 7.5-mile Ckt 1 line from URECC-Hallsville 138 kV substation to Noonday 138 kV substation |  |  | 7.5
220974 | 95169 | 171102 | ETEC | TX | Multi - Loop in 138 kV Diana East - Diana -Noonday - Hallsville - Gum Springs | URECC-Hallsville 138 kV Ckt 1 Terminal Upgrade toward Noonday 138 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509615 |  | 509628 |  | Upgrade terminal equipment at URECC-Hallsville 138 kV substation for Ckt 1 toward Noonday 138 kV
220974 | 95169 | 171103 | ETEC | TX | Multi - Loop in 138 kV Diana East - Diana -Noonday - Hallsville - Gum Springs | Noonday 138 kV Ckt 1 Terminal Upgrade toward URECC-Hallsville 138 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509628 |  | 509615 |  | Upgrade terminal equipment at Noonday 138 kV substation for Ckt 1 toward URECC-Hallsville 138 kV
220974 | 95169 | 171104 | ETEC | TX | Multi - Loop in 138 kV Diana East - Diana -Noonday - Hallsville - Gum Springs | Diana Switch 138 kV Retire Substation | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 440000 |  | NTC - Commitment Window | 509639 |  |  |  | Retire Diana Switch 138 kV substation
220974 | 95170 | 171105 | ETEC | TX | Multi - Lake Murvaul - Tenaska Gateway 138 kV New Line, Murvaul Tap - Lake Murvaul 138 kV Reconduct | Lake Murvaul - Tenaska Gateway 138 kV Ckt 1 New Line | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 22840000 |  | NTC - Commitment Window | 509049 | MURVAUL REC TAP |  |  | Build a 10.21-mile 138 kV Ckt 1 line from Lake Murvaul to Tenaska Gateway |  | 10.21
220974 | 95170 | 171106 | ETEC | TX | Multi - Lake Murvaul - Tenaska Gateway 138 kV New Line, Murvaul Tap - Lake Murvaul 138 kV Reconduct | Lake Murvaul 138 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 1650000 |  | NTC - Commitment Window | 509049 | MURVAUL REC TAP |  |  | Expand or rebuild Lake Murvaul 138 kV substation
220974 | 95170 | 171107 | ETEC | TX | Multi - Lake Murvaul - Tenaska Gateway 138 kV New Line, Murvaul Tap - Lake Murvaul 138 kV Reconduct | Lake Murvaul 138 kV Ckt 1 Terminal Upgrade toward Tenaska Gateway 138 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509049 | MURVAUL REC TAP |  |  | Upgrade terminal equipment at Lake Murvaul 138 kV substation for Ckt 1 toward Tenaska Gateway 138 kV
220974 | 95170 | 171108 | ETEC | TX | Multi - Lake Murvaul - Tenaska Gateway 138 kV New Line, Murvaul Tap - Lake Murvaul 138 kV Reconduct | Tenaska Gateway 138 kV Ckt 1 Terminal Upgrade toward Lake Murvaul 138 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window |  |  | 509049 | MURVAUL REC TAP | Upgrade terminal equipment at Tenaska Gateway 138 kV substation for Ckt 1 toward Lake Murvaul 138 kV
220974 | 95170 | 171109 | ETEC | TX | Multi - Lake Murvaul - Tenaska Gateway 138 kV New Line, Murvaul Tap - Lake Murvaul 138 kV Reconduct | Tenaska Gateway 138 kV New Substation | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 19030000 |  | NTC - Commitment Window |  |  |  |  | Install 138 kV substation at Tenaska Gateway
220974 | 95170 | 171110 | ETEC | TX | Multi - Lake Murvaul - Tenaska Gateway 138 kV New Line, Murvaul Tap - Lake Murvaul 138 kV Reconduct | Tenaska Gateway 138/345 kV Ckt 3 Transformer | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window |  |  | 508585 | TENASKA RUSK COUNTY | Install new 138/345 kV Ckt 3 transformer at Tenaska Gateway
220950 | 95170 | 171111 | AEP | TX | Multi - Lake Murvaul - Tenaska Gateway 138 kV New Line, Murvaul Tap - Lake Murvaul 138 kV Reconduct | Tenaska Switch 345 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2033-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 15000000 |  | NTC - Commitment Window | 508585 | TENASKA RUSK COUNTY |  |  | Expand or rebuild Tenaska Switch 345 kV substation
220974 | 95170 | 171112 | ETEC | TX | Multi - Lake Murvaul - Tenaska Gateway 138 kV New Line, Murvaul Tap - Lake Murvaul 138 kV Reconduct | Tenaska Gateway 138 kV Ckt 3 Terminal Upgrade toward Tenaska Switch 345 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window |  |  | 508585 | TENASKA RUSK COUNTY | Upgrade terminal equipment at Tenaska Gateway 138 kV substation for Ckt 3 toward Tenaska Switch 345 kV
220974 | 95170 | 171114 | ETEC | TX | Multi - Lake Murvaul - Tenaska Gateway 138 kV New Line, Murvaul Tap - Lake Murvaul 138 kV Reconduct | Murvaul Tap Switch - Lake Murvaul 138 kV Ckt 1 Line Reconductor | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 18230000 |  | NTC - Commitment Window | 509048 |  | 509049 | MURVAUL REC TAP | Reconductor the 9-mile 138 kV Ckt 1 line from Murvaul Tap Switch to Lake Murvaul |  |  | 9
220950 | 95170 | 171115 | AEP | TX | Multi - Lake Murvaul - Tenaska Gateway 138 kV New Line, Murvaul Tap - Lake Murvaul 138 kV Reconduct | Murvaul Tap Switch 138 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2033-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 14000000 |  | NTC - Commitment Window | 509048 |  |  |  | Expand or rebuild Murvaul Tap Switch 138 kV substation
220974 | 95170 | 171117 | ETEC | TX | Multi - Lake Murvaul - Tenaska Gateway 138 kV New Line, Murvaul Tap - Lake Murvaul 138 kV Reconduct | Lake Murvaul 138 kV Ckt 1 Terminal Upgrade toward Murvaul Tap Switch 138 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509049 | MURVAUL REC TAP | 509048 |  | Upgrade terminal equipment at Lake Murvaul 138 kV substation for Ckt 1 toward Murvaul Tap Switch 138 kV
220974 | 95171 | 171118 | ETEC | TX | Line - Sawmill - Turnertown 69 kV New Line | Sawmill - Turnertown 69 kV Ckt 1 New Line | Zonal Reliability |  | 2032-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 38480000 |  | NTC - Commitment Window | 509084 | SAWMILL | 509089 | TURNERTOWN | Build a 14-mile 69 kV Ckt 1 line from Sawmill to Turnertown |  | 14
220974 | 95171 | 171119 | ETEC | TX | Line - Sawmill - Turnertown 69 kV New Line | Sawmill 69 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2032-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 5040000 |  | NTC - Commitment Window | 509084 | SAWMILL |  |  | Expand or rebuild Sawmill 69 kV substation
220950 | 95171 | 171120 | AEP | TX | Line - Sawmill - Turnertown 69 kV New Line | Turnertown 69 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2032-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509089 | TURNERTOWN |  |  | Expand or rebuild Turnertown 69 kV substation
220974 | 95171 | 171121 | ETEC | TX | Line - Sawmill - Turnertown 69 kV New Line | Sawmill 69 kV Ckt 1 Terminal Upgrade toward Turnertown 69 kV | Zonal Reliability |  | 2032-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509084 | SAWMILL | 509089 | TURNERTOWN | Upgrade terminal equipment at Sawmill 69 kV substation for Ckt 1 toward Turnertown 69 kV
220974 | 95171 | 171122 | ETEC | TX | Line - Sawmill - Turnertown 69 kV New Line | Turnertown 69 kV Ckt 1 Terminal Upgrade toward Sawmill 69 kV | Zonal Reliability |  | 2032-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 1300000 |  | NTC - Commitment Window | 509089 | TURNERTOWN | 509084 | SAWMILL | Upgrade terminal equipment at Turnertown 69 kV substation for Ckt 1 toward Sawmill 69 kV
220950 | 95171 | 171123 | AEP | TX | Line - Sawmill - Turnertown 69 kV New Line | Evenside 69 kV Substation Relay Upgrade | Zonal Reliability |  | 2032-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509061 | EVENSIDE |  |  | Upgrade the relays at Evenside 69 kV substation to accommodate line looping
220950 | 95171 | 171124 | AEP | TX | Line - Sawmill - Turnertown 69 kV New Line | North Laneville 69 kV Hard Tap Modification | Zonal Reliability |  | 2032-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509074 | NORTH LANEVILLE |  |  | Modify Hard Tap at North Laneville 69 kV substation
220950 | 95171 | 171125 | AEP | TX | Line - Sawmill - Turnertown 69 kV New Line | Fears Corner 69 kV Hard Tap Modification | Zonal Reliability |  | 2032-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509086 | FEARS CORNER |  |  | Modify Hard Tap at Fears Corner 69 kV substation
220974 | 95172 | 171126 | ETEC | TX | Multi - AEP Baldwin - ETEC/PHEC-Baldwin 69 kV New Line, Cross Roads - Leigh 69 kV Line Switch-out | ETEC/PHEC-Baldwin Switch - PHEC-Baldwin 69 kV Ckt 1 New Line | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 8120000 |  | NTC - Commitment Window | 508830 | BALDWIN | 509677 |  | Build a 3-mile 69 kV Ckt 1 line from ETEC/PHECC-Baldwin Switch to PHEC-Baldwin |  | 3
220950 | 95172 | 171127 | AEP | TX | Multi - AEP Baldwin - ETEC/PHEC-Baldwin 69 kV New Line, Cross Roads - Leigh 69 kV Line Switch-out | AEP Baldwin 69 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2031-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 3610000 |  | NTC - Commitment Window | 508830 | BALDWIN |  |  | Expand or rebuild AEP Baldwin 69 kV substation
220974 | 95172 | 171128 | ETEC | TX | Multi - AEP Baldwin - ETEC/PHEC-Baldwin 69 kV New Line, Cross Roads - Leigh 69 kV Line Switch-out | PHEC-Baldwin 69 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 5670000 |  | NTC - Commitment Window | 509677 |  |  |  | Expand or rebuild PHEC-Baldwin 69 kV substation
220950 | 95172 | 171129 | AEP | TX | Multi - AEP Baldwin - ETEC/PHEC-Baldwin 69 kV New Line, Cross Roads - Leigh 69 kV Line Switch-out | AEP Baldwin 69 kV Ckt 1 Terminal Upgrade toward Baldwin 69 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 1300000 |  | NTC - Commitment Window | 508830 | BALDWIN | 509677 |  | Upgrade terminal equipment at AEP Baldwin 69 kV substation for Ckt 1 toward ETEC/PHEC-Baldwin 69 kV
220974 | 95172 | 171130 | ETEC | TX | Multi - AEP Baldwin - ETEC/PHEC-Baldwin 69 kV New Line, Cross Roads - Leigh 69 kV Line Switch-out | ETEC/PHEC-Baldwin Switch 69 kV Ckt 1 Terminal Upgrade toward AEP Baldwin 69 kV | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509677 |  | 508830 | BALDWIN | Upgrade terminal equipment at ETEC/PHEC-Baldwin Switch 69 kV substation for Ckt 1 toward AEP Baldwin 69 kV
220974 | 95172 | 171131 | ETEC | TX | Multi - AEP Baldwin - ETEC/PHEC-Baldwin 69 kV New Line, Cross Roads - Leigh 69 kV Line Switch-out | Switch Cross Roads - Leigh 69 kV Ckt 1 to Normally Open | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509672 |  | 509674 |  | Switch out 69 kV Ckt 1 line from Cross Roads to Leigh to operate as normally open
220974 | 95173 | 171132 | ETEC | LA | Line - Stanley - Huxley 69 kV New Line | Stanley - Huxley 69 kV Ckt 1 New Line | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 60160000 |  | NTC - Commitment Window | 509051 | STANLEY REC T | 509115 |  | Build a 22-mile 69 kV Ckt 1 line from Stanley to Huxley |  | 22
220974 | 95173 | 171133 | ETEC | LA | Line - Stanley - Huxley 69 kV New Line | Stanley 69 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 4220000 |  | NTC - Commitment Window | 509051 | STANLEY REC T |  |  | Expand or rebuild Stanley 69 kV substation
220974 | 95173 | 171134 | ETEC | TX | Line - Stanley - Huxley 69 kV New Line | Huxley 69 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 6080000 |  | NTC - Commitment Window | 509115 |  |  |  | Expand or rebuild Huxley 69 kV substation
220974 | 95173 | 171135 | ETEC | TX | Line - Stanley - Huxley 69 kV New Line | Hurstown 69 kV Substation Reconfiguration | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 4220000 |  | NTC - Commitment Window | 509113 |  |  |  | Reconfigure Hurstown 69 kV substation for MOABS, upgrade communication and SCADA system
220974 | 95173 | 171136 | ETEC | TX | Line - Stanley - Huxley 69 kV New Line | Center South 69 kV Substation Terminal Upgrade | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 1000000 |  | NTC - Commitment Window | 509122 |  | 509114 |  | Upgrade equipment at Center South 69 kV substation for Ckt 1 towards Hurston Tap 69 kV
220974 | 95173 | 171137 | ETEC | LA | Line - Stanley - Huxley 69 kV New Line | Stanley 69 kV Ckt 1 Terminal Upgrade toward Huxley 69 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509051 | STANLEY REC T | 509115 |  | Upgrade terminal equipment at Stanley 69 kV substation for Ckt 1 toward Huxley 69 kV
220974 | 95173 | 171138 | ETEC | TX | Line - Stanley - Huxley 69 kV New Line | Huxley 69 kV Ckt 1 Terminal Upgrade toward Stanley 69 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509115 |  | 509051 | STANLEY REC T | Upgrade terminal equipment at Huxley 69 kV substation for Ckt 1 toward Stanley 69 kV
220950 | 95174 | 171139 | AEP | TX | Multi - Liberty City - Kilgore - Mt. Eara 138 kV New Line, Big Sandy - Mt. Eara 138 kV Conv | Liberty City - Kilgore 138 kV Ckt 1 New Line | Zonal Reliability |  | 2033-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 10000000 |  | NTC - Commitment Window | 508535 | LIBERTY CITY |  |  | Build a 4.5-mile 138 kV Ckt 1 line from Liberty City to Kilgore |  | 4.5
220950 | 95174 | 171140 | AEP | TX | Multi - Liberty City - Kilgore - Mt. Eara 138 kV New Line, Big Sandy - Mt. Eara 138 kV Conv | Liberty City 138 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2033-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 13000000 |  | NTC - Commitment Window | 508535 | LIBERTY CITY |  |  | Expand or rebuild Liberty City 138 kV substation
220950 | 95174 | 171141 | AEP | TX | Multi - Liberty City - Kilgore - Mt. Eara 138 kV New Line, Big Sandy - Mt. Eara 138 kV Conv | Liberty City 138 kV Ckt 1 Terminal Upgrade toward Kilgore 138 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 5050000 |  | NTC - Commitment Window | 508535 | LIBERTY CITY |  |  | Upgrade terminal equipment at Liberty City 138 kV substation for Ckt 1 toward Kilgore 138 kV
220974 | 95174 | 171142 | ETEC | TX | Multi - Liberty City - Kilgore - Mt. Eara 138 kV New Line, Big Sandy - Mt. Eara 138 kV Conv | Kilgore 138 kV Ckt 1 Terminal Upgrade toward Liberty City 138 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window |  |  | 508535 | LIBERTY CITY | Upgrade terminal equipment at Kilgore 138 kV substation for Ckt 1 toward Liberty City 138 kV
220974 | 95174 | 171143 | ETEC | TX | Multi - Liberty City - Kilgore - Mt. Eara 138 kV New Line, Big Sandy - Mt. Eara 138 kV Conv | Big Sandy - Mt. Eara Ckt 1 138 kV Voltage Conversion | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 39940000 |  | NTC - Commitment Window | 509603 |  | 509637 |  | Convert the existing Big Sandy to Mt. Eara Tap Ckt 1 line and Mount Eara Tap to Mount Eara Ckt 1 line from 69 kV to 138 kV. Join to create a single 138 kV line from Big Sandy to Mount Eara. |  |  |  | 14.4
220974 | 95174 | 171144 | ETEC | TX | Multi - Liberty City - Kilgore - Mt. Eara 138 kV New Line, Big Sandy - Mt. Eara 138 kV Conv | Remove Kilgore - Mt. Eara Tap 69 kV Ckt 1 | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509622 |  | 509637 |  | Switch out 69 kV Ckt 1 line from Kilgore to Mt. Eara Tap
220974 | 95174 | 171146 | ETEC | TX | Multi - Liberty City - Kilgore - Mt. Eara 138 kV New Line, Big Sandy - Mt. Eara 138 kV Conv | Mt. Eara - Kilgore Ckt 1 138 kV New Line | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 21680000 |  | NTC - Commitment Window | 509636 |  |  |  | Build an 8-mile 138 kV Ckt 1 line from Kilgore to Mt Eara |  | 8
220974 | 95174 | 171147 | ETEC | TX | Multi - Liberty City - Kilgore - Mt. Eara 138 kV New Line, Big Sandy - Mt. Eara 138 kV Conv | Mt. Eara 138 kV Substation Voltage Conversion | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 6970000 |  | NTC - Commitment Window | 509636 |  |  |  | Convert the existing 69 kV Mt. Eara substation to 138 kV
220974 | 95174 | 171149 | ETEC | TX | Multi - Liberty City - Kilgore - Mt. Eara 138 kV New Line, Big Sandy - Mt. Eara 138 kV Conv | Kilgore 138 kV New Substation | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 16410000 |  | NTC - Commitment Window |  |  |  |  | Install 138 kV substation at Kilgore
220974 | 95174 | 171150 | ETEC | TX | Multi - Liberty City - Kilgore - Mt. Eara 138 kV New Line, Big Sandy - Mt. Eara 138 kV Conv | Kilgore 69/138 kV Ckt 1 Transformer | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509622 |  |  |  | Install new 69/138 kV Ckt 1 transformer at Kilgore
220974 | 95174 | 171151 | ETEC | TX | Multi - Liberty City - Kilgore - Mt. Eara 138 kV New Line, Big Sandy - Mt. Eara 138 kV Conv | Kilgore 69 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509622 |  |  |  | Expand or rebuild Kilgore 69 kV substation
220974 | 95174 | 171152 | ETEC | TX | Multi - Liberty City - Kilgore - Mt. Eara 138 kV New Line, Big Sandy - Mt. Eara 138 kV Conv | Kilgore 69 kV Ckt 1 Terminal Upgrade toward Kilgore 138 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509622 |  |  |  | Upgrade terminal equipment at Kilgore 69 kV substation for Ckt 1 toward Kilgore 138 kV
220974 | 95174 | 171153 | ETEC | TX | Multi - Liberty City - Kilgore - Mt. Eara 138 kV New Line, Big Sandy - Mt. Eara 138 kV Conv | Kilgore 138 kV Ckt 1 Terminal Upgrade toward Kilgore 69 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window |  |  | 509622 |  | Upgrade terminal equipment at Kilgore 138 kV substation for Ckt 1 toward Kilgore 69 kV
220974 | 95174 | 171154 | ETEC | TX | Multi - Liberty City - Kilgore - Mt. Eara 138 kV New Line, Big Sandy - Mt. Eara 138 kV Conv | Big Sandy 138 kV Substation Voltage Conversion | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 9010000 |  | NTC - Commitment Window | 509603 |  |  |  | Convert the existing 69 kV Big Sandy substation to a 138 kV ring bus station
220950 | 95174 | 171156 | AEP | TX | Multi - Liberty City - Kilgore - Mt. Eara 138 kV New Line, Big Sandy - Mt. Eara 138 kV Conv | Perdue 138 kV Substation Upgrades | Zonal Reliability |  | 2033-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 500000 |  | NTC - Commitment Window | 508351 | PERDUE 138KV |  |  | Upgrade or reconfigure Perdue 138 kV Substation
220965 | 95175 | 171157 | OGE | OK | Line - Lone Oak - Chisholm Creek 138 kV New Line | Lone Oak - Chisholm Creek 138 kV Ckt 1 New Line | Regional Reliability |  | 2025-11-18 | 2025-11-11 | 2025 ITP |  |  | 0 | 5250000 |  | NTC - Commitment Window | 514873 | LONEOAK 138 | 515374 | CHISHOLM CREEK | Build a 3.53-mile 138 kV Ckt 1 line from Lone Oak to Chisholm Creek |  | 3.53
220965 | 95175 | 171158 | OGE | OK | Line - Lone Oak - Chisholm Creek 138 kV New Line | Lone Oak 138 kV Substation Expansion or Rebuild | Regional Reliability |  | 2025-11-18 | 2025-11-11 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 514873 | LONEOAK 138 |  |  | Expand or rebuild Lone Oak 138 kV substation
220965 | 95175 | 171159 | OGE | OK | Line - Lone Oak - Chisholm Creek 138 kV New Line | Chisholm Creek 138 kV Substation Expansion or Rebuild | Regional Reliability |  | 2025-11-18 | 2025-11-11 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 515374 | CHISHOLM CREEK |  |  | Expand or rebuild Chisholm Creek 138 kV substation
220965 | 95175 | 171160 | OGE | OK | Line - Lone Oak - Chisholm Creek 138 kV New Line | Lone Oak 138 kV Ckt 1 Terminal Upgrade toward Chisholm Creek 138 kV | Regional Reliability |  | 2025-11-18 | 2025-11-11 | 2025 ITP |  |  | 0 | 4000000 |  | NTC - Commitment Window | 514873 | LONEOAK 138 | 515374 | CHISHOLM CREEK | Upgrade terminal equipment at Lone Oak 138 kV substation for Ckt 1 toward Chisholm Creek 138 kV
220965 | 95175 | 171161 | OGE | OK | Line - Lone Oak - Chisholm Creek 138 kV New Line | Chisholm Creek 138 kV Ckt 1 Terminal Upgrade toward Lone Oak 138 kV | Regional Reliability |  | 2025-11-18 | 2025-11-11 | 2025 ITP |  |  | 0 | 4500000 |  | NTC - Commitment Window | 515374 | CHISHOLM CREEK | 514873 | LONEOAK 138 | Upgrade terminal equipment at Chisholm Creek 138 kV substation for Ckt 1 toward Lone Oak 138 kV
220960 | 95177 | 171168 | WAPA | SD | Multi - Aurora 115 kV New Lines, White 345/115 kV New Transformer | Aurora 115 kV Substation Expansion or Rebuild | Regional Reliability | 2031-12-31 | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 11000000 |  | NTC - Commitment Window | 652474 | Aurora |  |  | Expand or rebuild Aurora 115 kV substation
220960 | 95177 | 171169 | WAPA | SD | Multi - Aurora 115 kV New Lines, White 345/115 kV New Transformer | White 115 kV Substation Expansion or Rebuild | Regional Reliability | 2035-06-30 | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 11000000 |  | NTC - Commitment Window | 652538 | WHITE |  |  | Expand or rebuild White 115 kV substation
220960 | 95177 | 171170 | WAPA | SD | Multi - Aurora 115 kV New Lines, White 345/115 kV New Transformer | Aurora 115 kV Ckt 1 Terminal Upgrade toward White 115 kV | Regional Reliability | 2031-12-31 | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 652474 | Aurora | 652538 | WHITE | Install and upgrade any terminal equipment at Aurora 115 kV substation to support a Ckt 1 new line to White 115 kV substation that meets or exceeds a summer emergency rating of 200 MVA .
220960 | 95177 | 171171 | WAPA | SD | Multi - Aurora 115 kV New Lines, White 345/115 kV New Transformer | White 115 kV Ckt 1 Terminal Upgrade toward Aurora 115 kV | Regional Reliability | 2035-06-30 | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 652538 | WHITE | 652474 | Aurora | Install and upgrade any terminal equipment at White 115 kV substation to support a Ckt 1 new line to Aurora 115 kV substation
220952 | 95177 | 171172 | EREC | SD | Multi - Aurora 115 kV New Lines, White 345/115 kV New Transformer | Aurora Industrial - BMU East 115 kV Ckt 1 New Line (EREC) | Regional Reliability |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 2950000 |  | NTC - Commitment Window | 655379 |  | 658156 |  | Build a 3.96-mile 115 kV Ckt 1 line from Aurora Industrial to BMU East |  | 3.96
220952 | 95177 | 171173 | EREC | SD | Multi - Aurora 115 kV New Lines, White 345/115 kV New Transformer | Aurora Industrial 115 kV Substation Expansion or Rebuild | Regional Reliability |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 4500000 |  | NTC - Commitment Window | 655379 |  |  |  | Expand or rebuild Aurora Industrial 115 kV substation
220956 | 95177 | 171174 | MRES | SD | Multi - Aurora 115 kV New Lines, White 345/115 kV New Transformer | BMU East 115 kV New Substation | Regional Reliability |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 6200000 |  | NTC - Commitment Window | 658156 |  |  |  | Install new BMU East 115 kV substation
220952 | 95177 | 171175 | EREC | SD | Multi - Aurora 115 kV New Lines, White 345/115 kV New Transformer | Aurora Industrial 115 kV Ckt 1 Terminal Upgrade toward BMU East 115 kV | Regional Reliability |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 1100000 |  | NTC - Commitment Window | 655379 |  | 658156 |  | Upgrade terminal equipment at Aurora Industrial 115 kV substation for Ckt 1 toward BMU East 115 kV
220956 | 95177 | 171176 | MRES | SD | Multi - Aurora 115 kV New Lines, White 345/115 kV New Transformer | BMU East 115 kV Ckt 1 Terminal Upgrade toward Aurora Industrial 115 kV | Regional Reliability |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 1100000 |  | NTC - Commitment Window | 658156 |  | 655379 |  | Upgrade terminal equipment at BMU East 115 kV substation for Ckt 1 toward Aurora Industrial 115 kV
220956 | 95177 | 171177 | MRES | SD | Multi - Aurora 115 kV New Lines, White 345/115 kV New Transformer | Energize BMU Brookings East - BMU Brookings West 115 kV Ckt 1 | Regional Reliability |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 3300000 |  | NTC - Commitment Window | 658142 |  | 658158 |  | Switch in 1.32-mile 115 kV Ckt 1 line from BMU Brookings East to BMU Brookings West
220960 | 95177 | 171178 | WAPA | SD | Multi - Aurora 115 kV New Lines, White 345/115 kV New Transformer | White 345/115 kV Ckt 2 Transformer | Regional Reliability | 2035-06-30 | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 10000000 |  | NTC - Commitment Window | 652537 | WHITE | 652538 | WHITE | Install new 345/115 kV Ckt 2 transformer at White
220960 | 95177 | 171179 | WAPA | SD | Multi - Aurora 115 kV New Lines, White 345/115 kV New Transformer | White 345 kV Substation Expansion or Rebuild | Regional Reliability | 2035-06-30 | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 2000000 |  | NTC - Commitment Window | 652537 | WHITE |  |  | Expand or rebuild White 345 kV substation
220960 | 95177 | 171180 | WAPA | SD | Multi - Aurora 115 kV New Lines, White 345/115 kV New Transformer | White 345 kV Ckt 2 Terminal Upgrade toward White 115 kV | Regional Reliability | 2035-06-30 | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 2800000 |  | NTC - Commitment Window | 652537 | WHITE | 652538 | WHITE | Install and upgrade any terminal equipment at White 345 kV substation to support the addition of a 2nd White 345/115 kV transformer (Ckt 2)
220960 | 95177 | 171181 | WAPA | SD | Multi - Aurora 115 kV New Lines, White 345/115 kV New Transformer | White 115 kV Ckt 2 Terminal Upgrade toward White 345 kV | Regional Reliability | 2035-06-30 | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 2800000 |  | NTC - Commitment Window | 652538 | WHITE | 652537 | WHITE | Install and upgrade any terminal equipment at White 115 kV substation to support the addition of a 2nd White 345/115 kV transformer (Ckt 2)
220960 | 95177 | 171182 | WAPA | SD | Multi - Aurora 115 kV New Lines, White 345/115 kV New Transformer | Aurora - White 115 kV Ckt 1 New Line (2) | Regional Reliability | 2031-12-31 | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 22500000 |  | NTC - Commitment Window | 652474 | Aurora | 652538 | WHITE | Build a 14.4-mile 115 kV Ckt 1 line from Aurora to White |  | 14.4
220972 | 95178 | 171183 | SPS | NM | Line - Maddox - Pearl 115 kV Rebuild | Maddox - Pearl 115 kV Ckt 1 Rebuild (2) | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 15090000 |  | NTC - Commitment Window | 528355 | Maddox Station 115 kV | 528392 | Pearl Sub 115 kV | Rebuild 15.09-mile Ckt 1 line from Maddox 115 kV substation to Pearl 115 kV substation |  |  | 15.09
220972 | 95178 | 171184 | SPS | NM | Line - Maddox - Pearl 115 kV Rebuild | Maddox 115 kV Ckt 1 Terminal Upgrade toward Pearl 115 kV | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 528355 | Maddox Station 115 kV | 528392 | Pearl Sub 115 kV | Upgrade terminal equipment at Maddox 115 kV substation for Ckt 1 toward Pearl 115 kV
220972 | 95178 | 171185 | SPS | NM | Line - Maddox - Pearl 115 kV Rebuild | Pearl 115 kV Ckt 1 Terminal Upgrade toward Maddox 115 kV | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 528392 | Pearl Sub 115 kV | 528355 | Maddox Station 115 kV | Upgrade terminal equipment at Pearl 115 kV substation for Ckt 1 toward Maddox 115 kV
220972 | 95179 | 171186 | SPS | TX | XFR - Lamb Co. 115/69 kV | Lamb Co. 69/115 kV Ckt 4 Transformer | Regional Reliability |  | 2026-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 4725000 |  | NTC - Commitment Window | 525635 | Lamb County Interchange 69 kV | 525636 | Lamb County Interchange 115 kV | Install new 69/115 kV Ckt 4 transformer at Lamb Co.
220972 | 95179 | 171187 | SPS | TX | XFR - Lamb Co. 115/69 kV | Lamb Co. 69 kV Substation Expansion or Rebuild | Regional Reliability |  | 2026-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 525635 | Lamb County Interchange 69 kV |  |  | Expand or rebuild Lamb Co. 69 kV substation
220972 | 95179 | 171188 | SPS | TX | XFR - Lamb Co. 115/69 kV | Lamb Co. 115 kV Substation Expansion or Rebuild | Regional Reliability |  | 2026-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 525636 | Lamb County Interchange 115 kV |  |  | Expand or rebuild Lamb Co. 115 kV substation
220972 | 95179 | 171189 | SPS | TX | XFR - Lamb Co. 115/69 kV | Lamb Co. 69 kV Ckt 4 Terminal Upgrade toward Lamb Co. 115 kV | Regional Reliability |  | 2026-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 248675 |  | NTC - Commitment Window | 525635 | Lamb County Interchange 69 kV | 525636 | Lamb County Interchange 115 kV | Upgrade terminal equipment at Lamb Co. 69 kV substation for Ckt 4 toward Lamb Co. 115 kV
220972 | 95179 | 171190 | SPS | TX | XFR - Lamb Co. 115/69 kV | Lamb Co. 115 kV Ckt 4 Terminal Upgrade toward Lamb Co. 69 kV | Regional Reliability |  | 2026-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 385333 |  | NTC - Commitment Window | 525636 | Lamb County Interchange 115 kV | 525635 | Lamb County Interchange 69 kV | Upgrade terminal equipment at Lamb Co. 115 kV substation for Ckt 4 toward Lamb Co. 69 kV
220953 | 95180 | 171191 | LEA | TX | XFR - Plains Int 115/69 kV | Plains Int 115/69 kV Ckt 2 Transformer | Regional Reliability |  | 2029-06-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 3558015 |  | NTC - Commitment Window | 526928 | Lea County REC-Plains Interchange115 kV | 528626 | Lea County REC-Plains Interchange 69 kV | Install new 115/69 kV Ckt 2 transformer at Plains Int
220972 | 95180 | 171192 | SPS | TX | XFR - Plains Int 115/69 kV | Plains Int 115 kV Substation Expansion or Rebuild | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 526928 | Lea County REC-Plains Interchange115 kV |  |  | Expand or rebuild Plains Int 115 kV substation
220953 | 95180 | 171193 | LEA | TX | XFR - Plains Int 115/69 kV | Plains Int 69 kV Substation Expansion or Rebuild | Regional Reliability |  | 2029-06-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 4241985 |  | NTC - Commitment Window | 528626 | Lea County REC-Plains Interchange 69 kV |  |  | Expand or rebuild Plains Int 69 kV substation
220972 | 95180 | 171194 | SPS | TX | XFR - Plains Int 115/69 kV | Plains Int 115 kV Ckt 2 Terminal Upgrade toward Plains Int 69 kV | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 385333 |  | NTC - Commitment Window | 526928 | Lea County REC-Plains Interchange115 kV | 528626 | Lea County REC-Plains Interchange 69 kV | Upgrade terminal equipment at Plains Int 115 kV substation for Ckt 2 toward Plains Int 69 kV
220953 | 95180 | 171195 | LEA | TX | XFR - Plains Int 115/69 kV | Plains Int 69 kV Ckt 2 Terminal Upgrade toward Plains Int 115 kV | Regional Reliability |  | 2029-06-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 3500000 |  | NTC - Commitment Window | 528626 | Lea County REC-Plains Interchange 69 kV | 526928 | Lea County REC-Plains Interchange115 kV | Upgrade terminal equipment at Plains Int 69 kV substation for Ckt 2 toward Plains Int 115 kV
220959 | 95182 | 171201 | NPPD | NE | Line - Columbus Southeast - Columbus Hydro 115 kV Rebuild | Columbus Southeast - Columbus Hydro 115 kV Ckt 1 Rebuild | Economic |  | 2026-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 3600000 |  | NTC - Commitment Window | 640124 | Columbus Southeast | 640136 | Columbus | Rebuild 3.88-mile Ckt 1 (L1153A) line from Columbus Southeast 115 kV substation to Columbus Hydro 115 kV substation |  |  | 3.88
220959 | 95182 | 171202 | NPPD | NE | Line - Columbus Southeast - Columbus Hydro 115 kV Rebuild | Columbus Southeast 115 kV Ckt 1 Terminal Upgrade toward Columbus Hydro 115 kV | Economic |  | 2026-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 150000 |  | NTC - Commitment Window | 640124 | Columbus Southeast | 640136 | Columbus | Upgrade terminal equipment at Columbus Southeast 115 kV substation for Ckt 1 toward Columbus Hydro 115 kV
220959 | 95182 | 171203 | NPPD | NE | Line - Columbus Southeast - Columbus Hydro 115 kV Rebuild | Columbus Hydro 115 kV Ckt 1 Terminal Upgrade toward Columbus Southeast 115 kV | Economic |  | 2026-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 100000 |  | NTC - Commitment Window | 640136 | Columbus | 640124 | Columbus Southeast | Upgrade terminal equipment at Columbus Hydro 115 kV substation for Ckt 1 toward Columbus Southeast 115 kV
220972 | 95185 | 171209 | SPS | TX | Line - Lubbock South - Wolfforth 230 kV Rebuild | Lubbock South - Wolfforth 230 kV Ckt 1 Rebuild | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 27778000 |  | NTC - Commitment Window | 526269 | Lubbock South Interchange 230 kV | 526525 | Wolfforth Interchange 230 kV | Rebuild 14.62-mile Ckt 1 line from Lubbock South 230 kV substation to Wolfforth 230 kV substation |  |  | 14.62
220972 | 95185 | 171210 | SPS | TX | Line - Lubbock South - Wolfforth 230 kV Rebuild | Lubbock South 230 kV Ckt 1 Terminal Upgrade toward Wolfforth 230 kV | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 3600000 |  | NTC - Commitment Window | 526269 | Lubbock South Interchange 230 kV | 526525 | Wolfforth Interchange 230 kV | Upgrade terminal equipment at Lubbock South 230 kV substation for Ckt 1 toward Wolfforth 230 kV
220972 | 95185 | 171211 | SPS | TX | Line - Lubbock South - Wolfforth 230 kV Rebuild | Wolfforth 230 kV Ckt 1 Terminal Upgrade toward Lubbock South 230 kV | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 3600000 |  | NTC - Commitment Window | 526525 | Wolfforth Interchange 230 kV | 526269 | Lubbock South Interchange 230 kV | Upgrade terminal equipment at Wolfforth 230 kV substation for Ckt 1 toward Lubbock South 230 kV
220955 | 95186 | 171212 | GRDA | OK | Line - Pruek - Osage 69 kV Rebuild | Pruek - Osage 69 kV Ckt 1 Rebuild | Regional Reliability |  | 2026-06-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 7582000 |  | NTC - Commitment Window | 512875 |  | 512876 |  | Rebuild 8.92-mile Ckt 1 line from Pruek 69 kV substation to Osage 69 kV substation |  |  | 8.92
220955 | 95186 | 171213 | GRDA | OK | Line - Pruek - Osage 69 kV Rebuild | Pruek 69 kV Ckt 1 Terminal Upgrade toward Osage 69 kV | Regional Reliability |  | 2026-06-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 1300000 |  | NTC - Commitment Window | 512875 |  | 512876 |  | Upgrade terminal equipment at Pruek 69 kV substation for Ckt 1 toward Osage 69 kV
220955 | 95186 | 171214 | GRDA | OK | Line - Pruek - Osage 69 kV Rebuild | Osage 69 kV Ckt 1 Terminal Upgrade toward Pruek 69 kV | Regional Reliability |  | 2026-06-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 1300000 |  | NTC - Commitment Window | 512876 |  | 512875 |  | Upgrade terminal equipment at Osage 69 kV substation for Ckt 1 toward Pruek 69 kV
220951 | 95188 | 171221 | EMW | MO | Multi - Roanridge Corridor Rebuilds 161 kV | KCI - Ferrelview 161 kV Ckt 1 Rebuild | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 6795000 |  | NTC - Commitment Window | 541212 | KCI 161 KV | 541213 | Ferrelview 161 KV | Rebuild 4.53-mile Ckt 1 line from KCI 161 kV substation to Ferrelview 161 kV substation |  |  | 4.53
220951 | 95188 | 171222 | EMW | MO | Multi - Roanridge Corridor Rebuilds 161 kV | KCI 161 kV Ckt 1 Terminal Upgrade toward Ferrelview 161 kV | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 3100000 |  | NTC - Commitment Window | 541212 | KCI 161 KV | 541213 | Ferrelview 161 KV | Upgrade terminal equipment at KCI 161 kV substation for Ckt 1 toward Ferrelview 161 kV
220951 | 95188 | 171223 | EMW | MO | Multi - Roanridge Corridor Rebuilds 161 kV | Ferrelview 161 kV Ckt 1 Terminal Upgrade toward KCI 161 kV | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 3100000 |  | NTC - Commitment Window | 541213 | Ferrelview 161 KV | 541212 | KCI 161 KV | Upgrade terminal equipment at Ferrelview 161 kV substation for Ckt 1 toward KCI 161 kV
220951 | 95188 | 171224 | EMW | MO | Multi - Roanridge Corridor Rebuilds 161 kV | KCI - Platte City 161 kV Ckt 1 Rebuild | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 10125000 |  | NTC - Commitment Window | 541212 | KCI 161 KV | 541221 | Platte City 161 KV | Rebuild 6.75-mile Ckt 1 line from KCI 161 kV substation to Platte City 161 kV substation |  |  | 6.75
220951 | 95188 | 171225 | EMW | MO | Multi - Roanridge Corridor Rebuilds 161 kV | KCI 161 kV Ckt 1 Terminal Upgrade toward Platte City 161 kV | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 3100000 |  | NTC - Commitment Window | 541212 | KCI 161 KV | 541221 | Platte City 161 KV | Upgrade terminal equipment at KCI 161 kV substation for Ckt 1 toward Platte City 161 kV
220951 | 95188 | 171226 | EMW | MO | Multi - Roanridge Corridor Rebuilds 161 kV | Platte City 161 kV Ckt 1 Terminal Upgrade toward KCI 161 kV | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 3100000 |  | NTC - Commitment Window | 541221 | Platte City 161 KV | 541212 | KCI 161 KV | Upgrade terminal equipment at Platte City 161 kV substation for Ckt 1 toward KCI 161 kV
220951 | 95188 | 171227 | EMW | MO | Multi - Roanridge Corridor Rebuilds 161 kV | Ferrelview - TWA 161 kV Ckt 1 Rebuild | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 3450000 |  | NTC - Commitment Window | 541213 | Ferrelview 161 KV | 541214 | TWA 161 KV | Rebuild 2.3-mile Ckt 1 line from Ferrelview 161 kV substation to TWA 161 kV substation |  |  | 2.3
220951 | 95188 | 171228 | EMW | MO | Multi - Roanridge Corridor Rebuilds 161 kV | Ferrelview 161 kV Ckt 1 Terminal Upgrade toward TWA 161 kV | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 3100000 |  | NTC - Commitment Window | 541213 | Ferrelview 161 KV | 541214 | TWA 161 KV | Upgrade terminal equipment at Ferrelview 161 kV substation for Ckt 1 toward TWA 161 kV
220951 | 95188 | 171229 | EMW | MO | Multi - Roanridge Corridor Rebuilds 161 kV | TWA 161 kV Ckt 1 Terminal Upgrade toward Ferrelview 161 kV | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 3100000 |  | NTC - Commitment Window | 541214 | TWA 161 KV | 541213 | Ferrelview 161 KV | Upgrade terminal equipment at TWA 161 kV substation for Ckt 1 toward Ferrelview 161 kV
220951 | 95188 | 171230 | EMW | MO | Multi - Roanridge Corridor Rebuilds 161 kV | Roanridge - North Congress 161 kV Ckt 1 Rebuild | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 2730000 |  | NTC - Commitment Window | 541230 | Roanridge 161 KV | 541318 |  | Rebuild 1.82-mile Ckt 1 line from Roanridge 161 kV substation to North Congress 161 kV substation |  |  | 1.82
220951 | 95188 | 171231 | EMW | MO | Multi - Roanridge Corridor Rebuilds 161 kV | Roanridge 161 kV Ckt 1 Terminal Upgrade toward North Congress 161 kV | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 3100000 |  | NTC - Commitment Window | 541230 | Roanridge 161 KV | 541318 |  | Upgrade terminal equipment at Roanridge 161 kV substation for Ckt 1 toward North Congress 161 kV
220951 | 95188 | 171232 | EMW | MO | Multi - Roanridge Corridor Rebuilds 161 kV | North Congress 161 kV Ckt 1 Terminal Upgrade toward Roanridge 161 kV | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 3100000 |  | NTC - Commitment Window | 541318 |  | 541230 | Roanridge 161 KV | Upgrade terminal equipment at North Congress 161 kV substation for Ckt 1 toward Roanridge 161 kV
220951 | 95188 | 171233 | EMW | MO | Multi - Roanridge Corridor Rebuilds 161 kV | Roanridge 161 kV Ckt 1 Terminal Upgrade toward First Creek 161 kV | Economic |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 1902215 |  | NTC - Commitment Window | 541230 | Roanridge 161 KV | 543039 | LENEXA NORTH 161 KV | Upgrade terminal equipment at Roanridge 161 kV substation for Ckt 1 toward First Creek 161 kV
220964 | 95188 | 171234 | EM | KS | Multi - Roanridge Corridor Rebuilds 161 kV | First Creek 161 kV Ckt 1 Terminal Upgrade toward Roanridge 161 kV | Economic |  | 2025-11-18 | 2025-11-11 | 2025 ITP |  |  | 0 | 23823.71 |  | NTC - Commitment Window | 543039 | LENEXA NORTH 161 KV | 541230 | Roanridge 161 KV | Upgrade terminal equipment at First Creek 161 kV substation for Ckt 1 toward Roanridge 161 kV
220964 | 95188 | 171235 | EM | MO | Multi - Roanridge Corridor Rebuilds 161 kV | Roanridge - First Creek 161 kV Ckt 1 Rebuild | Economic |  | 2025-11-18 | 2025-11-11 | 2025 ITP |  |  | 0 | 9729334 |  | NTC - Commitment Window | 541230 | Roanridge 161 KV | 543039 | LENEXA NORTH 161 KV | Rebuild 5.16-mile Ckt 1 line from Roanridge 161 kV substation to First Creek 161 kV substation |  |  | 5.16
220960 | 95183 | 171236 | WAPA | SD | XFR - Ft. Thompson 345/230 kV | Ft. Thompson 345/230 kV Ckt 3 Transformer | Economic | 2034-12-31 | 2031-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 18450000 |  | NTC - Commitment Window | 652506 | FT THOMPSON | 652507 | FT THOMPSON | Install new 345/230 kV Ckt 3 transformer at Ft. Thompson
220960 | 95183 | 171237 | WAPA | SD | XFR - Ft. Thompson 345/230 kV | Ft. Thompson 345 kV Substation Expansion or Rebuild | Economic | 2034-12-31 | 2031-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 17450000 |  | NTC - Commitment Window | 652506 | FT THOMPSON |  |  | Expand or rebuild Ft. Thompson 345 kV substation
220960 | 95183 | 171238 | WAPA | SD | XFR - Ft. Thompson 345/230 kV | Ft. Thompson 230 kV Substation Expansion or Rebuild | Economic | 2034-12-31 | 2031-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 4200000 |  | NTC - Commitment Window | 652507 | FT THOMPSON |  |  | Expand or rebuild Ft. Thompson 230 kV substation
220960 | 95183 | 171242 | WAPA | SD | XFR - Ft. Thompson 345/230 kV | Ft. Thompson 345 kV Ckt 3 Terminal Upgrade toward Ft. Thompson 230 kV | Economic | 2034-12-31 | 2031-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 4450000 |  | NTC - Commitment Window | 652506 | FT THOMPSON | 652507 | FT THOMPSON | Install and upgrade any terminal equipment at Ft. Thompson 345 kV substation to support the addition of a 3rd Ft. Thompson 345/230 kV transformer (Ckt 3)
220960 | 95183 | 171243 | WAPA | SD | XFR - Ft. Thompson 345/230 kV | Ft. Thompson 230 kV Ckt 3 Terminal Upgrade toward Ft. Thompson 345 kV | Economic | 2034-12-31 | 2031-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 4450000 |  | NTC - Commitment Window | 652507 | FT THOMPSON | 652506 | FT THOMPSON | Install and upgrade any terminal equipment at Ft. Thompson 230 kV substation to support the addition of a 3rd Ft. Thompson 345/230 kV transformer (Ckt 3)
220952 | 95189 | 171244 | EREC | SD | Multi - Harrisburg - Dayton - La Valley - Virgil Fodness 115 kV Rebuild | Harrisburg - Dayton 115 kV Ckt 1 Rebuild | Economic |  | 2028-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 1200000 |  | NTC - Commitment Window | 655404 |  | 655518 |  | Rebuild 2.07-mile Ckt 1 line from Harrisburg 115 kV substation to Dayton 115 kV substation |  |  | 2.07
220952 | 95189 | 171245 | EREC | SD | Multi - Harrisburg - Dayton - La Valley - Virgil Fodness 115 kV Rebuild | Harrisburg 115 kV Ckt 1 Terminal Upgrade toward Dayton 115 kV | Economic |  | 2028-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 275000 |  | NTC - Commitment Window | 655404 |  | 655518 |  | Upgrade terminal equipment at Harrisburg 115 kV Motor Operated Switch for Ckt 1 toward Dayton 115 kV
220952 | 95189 | 171246 | EREC | SD | Multi - Harrisburg - Dayton - La Valley - Virgil Fodness 115 kV Rebuild | Dayton 115 kV Ckt 1 Terminal Upgrade toward Harrisburg 115 kV | Economic |  | 2028-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 560000 |  | NTC - Commitment Window | 655518 |  | 655404 |  | Upgrade terminal equipment at Dayton 115 kV substation for Ckt 1 toward Harrisburg 115 kV
220972 | 95190 | 171247 | SPS | NM | Multi - Hobbs - Millen - Hobbs N.E. - Taylor S.W. Station 115 kV Rebuild | Hobbs - Millen 115 kV Ckt 1 Rebuild | Economic |  | 2029-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 10150000 |  | NTC - Commitment Window | 527891 | Hobbs Interchange 115 kV | 528434 |  | Rebuild 10.15-mile Ckt 1 line from Hobbs 115 kV substation to Millen 115 kV substation |  |  | 10.15
220972 | 95190 | 171248 | SPS | NM | Multi - Hobbs - Millen - Hobbs N.E. - Taylor S.W. Station 115 kV Rebuild | Hobbs 115 kV Ckt 1 Terminal Upgrade toward Millen 115 kV | Economic |  | 2029-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 527891 | Hobbs Interchange 115 kV | 528434 |  | Upgrade terminal equipment at Hobbs 115 kV substation for Ckt 1 toward Millen 115 kV
220972 | 95190 | 171249 | SPS | NM | Multi - Hobbs - Millen - Hobbs N.E. - Taylor S.W. Station 115 kV Rebuild | Millen 115 kV Ckt 1 Terminal Upgrade toward Hobbs 115 kV | Economic |  | 2029-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 528434 |  | 527891 | Hobbs Interchange 115 kV | Upgrade terminal equipment at Millen 115 kV substation for Ckt 1 toward Hobbs 115 kV
220972 | 95190 | 171250 | SPS | NM | Multi - Hobbs - Millen - Hobbs N.E. - Taylor S.W. Station 115 kV Rebuild | Taylor S.W. Station - Hobbs N.E. 115 kV Ckt 1 Rebuild | Economic |  | 2029-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 3490000 |  | NTC - Commitment Window | 528413 | Taylor Switching Station 115 kV | 528442 | Northeast Hobbs Sub 115 kV | Rebuild 3.49-mile Ckt 1 line from Taylor S.W. Station 115 kV substation to Hobbs N.E. 115 kV substation |  |  | 3.49
220972 | 95190 | 171251 | SPS | NM | Multi - Hobbs - Millen - Hobbs N.E. - Taylor S.W. Station 115 kV Rebuild | Taylor S.W. Station 115 kV Ckt 1 Terminal Upgrade toward Hobbs N.E. 115 kV | Economic |  | 2029-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 528413 | Taylor Switching Station 115 kV | 528442 | Northeast Hobbs Sub 115 kV | Upgrade terminal equipment at Taylor S.W. Station 115 kV substation for Ckt 1 toward Hobbs N.E. 115 kV
220972 | 95190 | 171252 | SPS | NM | Multi - Hobbs - Millen - Hobbs N.E. - Taylor S.W. Station 115 kV Rebuild | Hobbs N.E. 115 kV Ckt 1 Terminal Upgrade toward Taylor S.W. Station 115 kV | Economic |  | 2029-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 528442 | Northeast Hobbs Sub 115 kV | 528413 | Taylor Switching Station 115 kV | Upgrade terminal equipment at Hobbs N.E. 115 kV substation for Ckt 1 toward Taylor S.W. Station 115 kV
220972 | 95190 | 171253 | SPS | NM | Multi - Hobbs - Millen - Hobbs N.E. - Taylor S.W. Station 115 kV Rebuild | Millen - Hobbs N.E. 115 kV Ckt 1 Rebuild | Economic |  | 2029-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 3324677 |  | NTC - Commitment Window | 528436 |  | 528442 | Northeast Hobbs Sub 115 kV | Rebuild 2-mile Ckt 1 line from Millen 115 kV substation to Hobbs N.E. 115 kV substation |  |  | 2
220972 | 95190 | 171254 | SPS | NM | Multi - Hobbs - Millen - Hobbs N.E. - Taylor S.W. Station 115 kV Rebuild | Millen 115 kV Ckt 1 Terminal Upgrade toward Hobbs N.E. 115 kV | Economic |  | 2029-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 528436 |  | 528442 | Northeast Hobbs Sub 115 kV | Upgrade terminal equipment at Millen 115 kV substation for Ckt 1 toward Hobbs N.E. 115 kV
220972 | 95190 | 171255 | SPS | NM | Multi - Hobbs - Millen - Hobbs N.E. - Taylor S.W. Station 115 kV Rebuild | Hobbs N.E. 115 kV Ckt 1 Terminal Upgrade toward Millen 115 kV | Economic |  | 2029-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 528442 | Northeast Hobbs Sub 115 kV | 528436 |  | Upgrade terminal equipment at Hobbs N.E. 115 kV substation for Ckt 1 toward Millen 115 kV
220963 | 95191 | 171256 | EKC | KS | Sub - Jarbalo Jct. - 53 & Mund 115 kV Terminal Upgrades | 166th Street 115 kV Ckt 1 Terminal Upgrade toward Jaggard 115 kV | Economic |  | 2027-01-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 533233 | 166TH STREET 115 KV | 533243 | JAGGARD JUNCTION 115 KV | Upgrade terminal equipment at 166th Street 115 kV substation for Ckt 1 toward Jaggard J115 kV
220963 | 95191 | 171257 | EKC | KS | Sub - Jarbalo Jct. - 53 & Mund 115 kV Terminal Upgrades | Jaggard 115 kV Ckt 1 Terminal Upgrade toward 166th Street 115 kV | Economic |  | 2027-01-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 533243 | JAGGARD JUNCTION 115 KV | 533233 | 166TH STREET 115 KV | Upgrade terminal equipment at Jaggard 115 kV substation for Ckt 1 toward 166th Street 115 kV
220963 | 95191 | 171258 | EKC | KS | Sub - Jarbalo Jct. - 53 & Mund 115 kV Terminal Upgrades | 166th Street 115 kV Ckt 1 Terminal Upgrade toward Jarbalo Jct. 115 kV | Economic |  | 2027-01-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 533233 | 166TH STREET 115 KV | 533244 | JARBALO JUNCTION SWITCHING STATION 115 KV | Upgrade terminal equipment at 166th Street 115 kV substation for Ckt 1 toward Jarbalo Jct. 115 kV
220963 | 95191 | 171259 | EKC | KS | Sub - Jarbalo Jct. - 53 & Mund 115 kV Terminal Upgrades | Jarbalo Jct. 115 kV Ckt 1 Terminal Upgrade toward 166th Street 115 kV | Economic |  | 2027-01-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 533244 | JARBALO JUNCTION SWITCHING STATION 115 KV | 533233 | 166TH STREET 115 KV | Upgrade terminal equipment at Jarbalo Jct. 115 kV substation for Ckt 1 toward 166th Street 115 kV
220963 | 95191 | 171260 | EKC | KS | Sub - Jarbalo Jct. - 53 & Mund 115 kV Terminal Upgrades | Jaggard 115 kV Ckt 1 Terminal Upgrade toward Pentagon 115 kV | Economic |  | 2027-01-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 533243 | JAGGARD JUNCTION 115 KV | 533261 | PENTAGON 115 KV | Upgrade terminal equipment at Jaggard 115 kV substation for Ckt 1 toward Pentagon 115 kV
220963 | 95191 | 171261 | EKC | KS | Sub - Jarbalo Jct. - 53 & Mund 115 kV Terminal Upgrades | Pentagon 115 kV Ckt 1 Terminal Upgrade toward Jaggard 115 kV | Economic |  | 2027-01-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 533261 | PENTAGON 115 KV | 533243 | JAGGARD JUNCTION 115 KV | Upgrade terminal equipment at Pentagon 115 kV substation for Ckt 1 toward Jaggard 115 kV
220963 | 95191 | 171262 | EKC | KS | Sub - Jarbalo Jct. - 53 & Mund 115 kV Terminal Upgrades | Pentagon 115 kV Ckt 1 Terminal Upgrade toward 53rd & Mund 115 kV | Economic |  | 2027-01-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 533261 | PENTAGON 115 KV | 533282 | MUND 115KV | Upgrade terminal equipment at Pentagon 115 kV substation for Ckt 1 toward 53rd & Mund 115 kV
220963 | 95191 | 171263 | EKC | KS | Sub - Jarbalo Jct. - 53 & Mund 115 kV Terminal Upgrades | 53rd & Mund 115 kV Ckt 1 Terminal Upgrade toward Pentagon 115 kV | Economic |  | 2027-01-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 533282 | MUND 115KV | 533261 | PENTAGON 115 KV | Upgrade terminal equipment at 53rd & Mund 115 kV substation for Ckt 1 toward Pentagon 115 kV
220968 | 95192 | 171264 | BEPC | ND | Line - Belfield - Roundup 345 kV New Line | Belfield - Roundup 345 kV Ckt 1 New Line | Economic |  | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 156240000 |  | NTC-C Project Estimate Window | 652424 | BELFIELD | 659384 |  | Build a 50.4-mile 345 kV Ckt 1 line from Belfield to Roundup |  | 50.4
220971 | 95192 | 171265 | WAPA | ND | Line - Belfield - Roundup 345 kV New Line | Belfield 345 kV Substation Expansion or Rebuild | Economic | 2033-07-01 | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 15000000 |  | NTC-C Project Estimate Window | 652424 | BELFIELD |  |  | Expand or rebuild Belfield 345 kV substation
220968 | 95192 | 171266 | BEPC | ND | Line - Belfield - Roundup 345 kV New Line | Roundup 345 kV Substation Expansion or Rebuild | Economic |  | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 0 |  | NTC-C Project Estimate Window | 659384 |  |  |  | Expand or rebuild Roundup 345 kV substation
220971 | 95192 | 171267 | WAPA | ND | Line - Belfield - Roundup 345 kV New Line | Belfield 2 or Belfield 345 kV Ckt 1 Terminal Upgrade toward Roundup 345 kV | Economic | 2033-07-01 | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 5200000 |  | NTC-C Project Estimate Window | 652424 | BELFIELD | 659384 |  | Install any terminal equipment at Belfield 2 345 kV or Belfield 345 kV substation to support a new line to Roundup 345 kV substation that meets or exceeds a summer emergency rating of 1792 MVA.
220968 | 95192 | 171268 | BEPC | ND | Line - Belfield - Roundup 345 kV New Line | Roundup 345 kV Ckt 1 Terminal Upgrade toward Belfield 345 kV | Economic |  | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 5000000 |  | NTC-C Project Estimate Window | 659384 |  | 652424 | BELFIELD | Upgrade terminal equipment at Roundup 345 kV substation for Ckt 1 toward Belfield 345 kV
220971 | 95192 | 171269 | WAPA | ND | Line - Belfield - Roundup 345 kV New Line | Belfield 2 or Belfield 345 kV Reactor | Economic | 2033-07-01 | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2520000 |  | NTC-C Project Estimate Window | 652424 | BELFIELD |  |  | Install 25.2 MVAR reactor at Belfield 2 345 kV or Belfield 345 kV substation tied to the new Belfield to Roundup 345 kV line that meets or exceeds a summer emergency rating of 1792 MVA.
220968 | 95192 | 171270 | BEPC | ND | Line - Belfield - Roundup 345 kV New Line | Roundup 345 kV Reactor | Economic |  | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2520000 |  | NTC-C Project Estimate Window | 659384 |  |  |  | Install 25 MVAR reactor at Roundup 345 kV substation
220967 | 95193 | 171271 | AEP | TX | Device - Diana & SW Shreveport STATCOMS | Diana East 345/138 kV Ckt 1 Transformer | Regional Reliability |  | 2028-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 10800000 |  | NTC-C Project Estimate Window | 508832 | DIANA 345KV |  |  | Install new 345/138 kV Ckt 1 transformer at Diana East
220967 | 95193 | 171272 | AEP | TX | Device - Diana & SW Shreveport STATCOMS | Diana East 345 kV Substation Expansion or Rebuild | Regional Reliability |  | 2028-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 0 |  | NTC-C Project Estimate Window | 508832 | DIANA 345KV |  |  | Expand or rebuild Diana East 345 kV substation
220967 | 95193 | 171273 | AEP | TX | Device - Diana & SW Shreveport STATCOMS | Diana East 345 kV Ckt 1 Terminal Upgrade toward Diana 138 kV | Regional Reliability |  | 2028-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 1537869 |  | NTC-C Project Estimate Window | 508832 | DIANA 345KV |  |  | Upgrade terminal equipment at Diana East 345 kV substation for Ckt 1 toward Diana 138 kV
220967 | 95193 | 171274 | AEP | TX | Device - Diana & SW Shreveport STATCOMS | Diana East 138 kV Ckt 1 Terminal Upgrade toward Diana East 345 kV | Regional Reliability |  | 2028-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 425503 |  | NTC-C Project Estimate Window |  |  | 508832 | DIANA 345KV | Upgrade terminal equipment at Diana East 138 kV substation for Ckt 1 toward Diana East 345 kV
220967 | 95193 | 171275 | AEP | LA | Device - Diana & SW Shreveport STATCOMS | Southwest Shreveport 345/138 kV Ckt 1 Transformer | Regional Reliability |  | 2028-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 10800000 |  | NTC-C Project Estimate Window | 507760 | SOUTHWEST SHREVEPORT 345KV |  |  | Install new 345/138 kV Ckt 1 transformer at Southwest Shreveport
220967 | 95193 | 171276 | AEP | LA | Device - Diana & SW Shreveport STATCOMS | Southwest Shreveport 345 kV Substation Expansion or Rebuild | Regional Reliability |  | 2028-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 0 |  | NTC-C Project Estimate Window | 507760 | SOUTHWEST SHREVEPORT 345KV |  |  | Expand or rebuild Southwest Shreveport 345 kV substation
220967 | 95193 | 171277 | AEP | LA | Device - Diana & SW Shreveport STATCOMS | Southwest Shreveport 345 kV Ckt 1 Terminal Upgrade toward Southwest Shreveport 138 kV | Regional Reliability |  | 2028-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 1537869 |  | NTC-C Project Estimate Window | 507760 | SOUTHWEST SHREVEPORT 345KV |  |  | Upgrade terminal equipment at Southwest Shreveport 345 kV substation for Ckt 1 toward Southwest Shreveport 138 kV
220967 | 95193 | 171278 | AEP | LA | Device - Diana & SW Shreveport STATCOMS | Southwest Shreveport 138 kV Ckt 1 Terminal Upgrade toward Southwest Shreveport 345 kV | Regional Reliability |  | 2028-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 425503 |  | NTC-C Project Estimate Window |  |  | 507760 | SOUTHWEST SHREVEPORT 345KV | Upgrade terminal equipment at Southwest Shreveport 138 kV substation for Ckt 1 toward Southwest Shreveport 345 kV
220952 | 95189 | 171279 | EREC | SD | Multi - Harrisburg - Dayton - La Valley - Virgil Fodness 115 kV Rebuild | Virgil Fodness - La Valley 115 kV Ckt 1 Rebuild | Economic |  | 2028-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 2880000 |  | NTC - Commitment Window | 655468 |  |  |  | Rebuild 5.94-mile Ckt 1 line from Virgil Fodness 115 kV substation to La Valley 115 kV manual switch |  |  | 5.94
220952 | 95189 | 171280 | EREC | SD | Multi - Harrisburg - Dayton - La Valley - Virgil Fodness 115 kV Rebuild | Virgil Fodness 115 kV Ckt 1 Terminal Upgrade toward La Valley 115 kV | Economic |  | 2028-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 500000 |  | NTC - Commitment Window | 655468 |  |  |  | Upgrade terminal equipment at Virgil Fodness 115 kV substation for Ckt 1 toward La Valley 115 kV
220952 | 95189 | 171281 | EREC | SD | Multi - Harrisburg - Dayton - La Valley - Virgil Fodness 115 kV Rebuild | La Valley 115 kV Ckt 1 Terminal Upgrade toward Virgil Fodness 115 kV | Economic |  | 2028-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 275000 |  | NTC - Commitment Window |  |  | 655468 |  | Upgrade terminal equipment at La Valley 115 kV manual switch for Ckt 1 toward Virgil Fodness 115 kV
220952 | 95189 | 171282 | EREC | SD | Multi - Harrisburg - Dayton - La Valley - Virgil Fodness 115 kV Rebuild | La Valley - Dayton 115 kV Ckt 1 Rebuild | Economic |  | 2028-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 2525000 |  | NTC - Commitment Window |  |  | 655518 |  | Rebuild 5.11-mile Ckt 1 line from La Valley 115 kV manual switch to Dayton 115 kV substation |  |  | 5.11
220952 | 95189 | 171283 | EREC | SD | Multi - Harrisburg - Dayton - La Valley - Virgil Fodness 115 kV Rebuild | La Valley 115 kV Ckt 1 Terminal Upgrade toward Dayton 115 kV | Economic |  | 2028-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 275000 |  | NTC - Commitment Window |  |  | 655518 |  | Upgrade terminal equipment at La Valley 115 kV manual switch for Ckt 1 toward Dayton 115 kV
220952 | 95189 | 171284 | EREC | SD | Multi - Harrisburg - Dayton - La Valley - Virgil Fodness 115 kV Rebuild | Dayton 115 kV Ckt 1 Terminal Upgrade toward La Valley 115 kV | Economic |  | 2028-01-01 | 2025-11-10 | 2025 ITP |  |  | 0 | 560000 |  | NTC - Commitment Window | 655518 |  |  |  | Upgrade terminal equipment at Dayton 115 kV substation for Ckt 1 toward La Valley 115 kV
220967 | 95193 | 171285 | AEP | LA | Device - Diana & SW Shreveport STATCOMS | Southwest Shreveport 345 kV STATCOM Ckt 1 | Regional Reliability |  | 2028-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 47000000 |  | NTC-C Project Estimate Window | 507760 | SOUTHWEST SHREVEPORT 345KV |  |  | Install 150 MVAR STATCOM Ckt 1 at Southwest Shreveport 345 kV substation
220967 | 95193 | 171286 | AEP | LA | Device - Diana & SW Shreveport STATCOMS | Southwest Shreveport 345 kV STATCOM Ckt 2 | Regional Reliability |  | 2028-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 47000000 |  | NTC-C Project Estimate Window | 507760 | SOUTHWEST SHREVEPORT 345KV |  |  | Install 150 MVAR STATCOM Ckt 2 at Southwest Shreveport 345 kV substation
220967 | 95193 | 171287 | AEP | TX | Device - Diana & SW Shreveport STATCOMS | Diana East 345 kV STATCOM Ckt 1 | Regional Reliability |  | 2028-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 47000000 |  | NTC-C Project Estimate Window | 508832 | DIANA 345KV |  |  | Install 150 MVAR STATCOM Ckt 1 at Diana East 345 kV substation
220967 | 95193 | 171288 | AEP | TX | Device - Diana & SW Shreveport STATCOMS | Diana East 345 kV STATCOM Ckt 2 | Regional Reliability |  | 2028-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 47000000 |  | NTC-C Project Estimate Window | 508832 | DIANA 345KV |  |  | Install 150 MVAR STATCOM Ckt 2 at Diana East 345 kV substation
220966 | 95196 | 171346 | OGE | OK | Line - Woodward - Crawfish Draw 765 kV New Line | Woodward 765 kV Ckt 1 Terminal Upgrade toward Crawfish Draw 765 kV | Regional Reliability |  | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 18000000 |  | NTC-C Project Estimate Window |  |  |  |  | Upgrade terminal equipment at Woodward 765 kV substation for Ckt 1 toward Crawfish Draw 765 kV
220966 | 95196 | 171348 | OGE | OK | Line - Woodward - Crawfish Draw 765 kV New Line | Woodward 765 kV Line Reactor | Regional Reliability |  | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 30000000 |  | NTC-C Project Estimate Window |  |  |  |  | Install 131.95 MVAR line reactor at Woodward 765 kV substation toward Crawfish Draw 765 kV
220966 | 95196 | 171349 | OGE | OK | Line - Woodward - Crawfish Draw 765 kV New Line | Woodward 765 kV New Substation | Regional Reliability |  | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 80000000 |  | NTC-C Project Estimate Window |  |  |  |  | Install 765 kV substation at Woodward
220966 | 95196 | 171350 | OGE | OK | Line - Woodward - Crawfish Draw 765 kV New Line | Woodward 345 kV Reactor | Regional Reliability |  | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 26000000 |  | NTC-C Project Estimate Window | 515375 | Woodward EHV 345kv |  |  | Install 225 MVAR reactor at Woodward 345 kV substation
220966 | 95196 | 171351 | OGE | OK | Line - Woodward - Crawfish Draw 765 kV New Line | Woodward 345 kV Substation Expansion or Rebuild | Regional Reliability |  | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 0 |  | NTC-C Project Estimate Window | 515375 | Woodward EHV 345kv |  |  | Expand or rebuild Woodward 345 kV substation
220966 | 95196 | 171352 | OGE | OK | Line - Woodward - Crawfish Draw 765 kV New Line | Woodward 765 kV Reactor | Regional Reliability |  | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 30000000 |  | NTC-C Project Estimate Window |  |  |  |  | Install 375 MVAR reactor at Woodward 765 kV substation
220966 | 95196 | 171353 | OGE | OK | Line - Woodward - Crawfish Draw 765 kV New Line | Woodward 345/765 kV Ckt 1 Transformer | Regional Reliability |  | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 61500000 |  | NTC-C Project Estimate Window | 515375 | Woodward EHV 345kv |  |  | Install new 345/765 kV Ckt 1 transformer at Woodward
220966 | 95196 | 171354 | OGE | OK | Line - Woodward - Crawfish Draw 765 kV New Line | Woodward 345 kV Ckt 1 Terminal Upgrade toward Woodward 765 kV | Regional Reliability |  | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 5000000 |  | NTC-C Project Estimate Window | 515375 | Woodward EHV 345kv |  |  | Upgrade terminal equipment at Woodward 345 kV substation for Ckt 1 toward Woodward 765 kV
220966 | 95196 | 171355 | OGE | OK | Line - Woodward - Crawfish Draw 765 kV New Line | Woodward 765 kV Ckt 1 Terminal Upgrade toward Woodward 345 kV | Regional Reliability |  | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 18000000 |  | NTC-C Project Estimate Window |  |  | 515375 | Woodward EHV 345kv | Upgrade terminal equipment at Woodward 765 kV substation for Ckt 1 toward Woodward 345 kV
220966 | 95196 | 171356 | OGE | OK | Line - Woodward - Crawfish Draw 765 kV New Line | Woodward 345/765 kV Ckt 2 Transformer | Regional Reliability |  | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 61500000 |  | NTC-C Project Estimate Window | 515375 | Woodward EHV 345kv |  |  | Install new 345/765 kV Ckt 2 transformer at Woodward
220966 | 95196 | 171357 | OGE | OK | Line - Woodward - Crawfish Draw 765 kV New Line | Woodward 345 kV Ckt 2 Terminal Upgrade toward Woodward 765 kV | Regional Reliability |  | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 5000000 |  | NTC-C Project Estimate Window | 515375 | Woodward EHV 345kv |  |  | Upgrade terminal equipment at Woodward 345 kV substation for Ckt 2 toward Woodward 765 kV
220966 | 95196 | 171358 | OGE | OK | Line - Woodward - Crawfish Draw 765 kV New Line | Woodward 765 kV Ckt 2 Terminal Upgrade toward Woodward 345 kV | Regional Reliability |  | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 18000000 |  | NTC-C Project Estimate Window |  |  | 515375 | Woodward EHV 345kv | Upgrade terminal equipment at Woodward 765 kV substation for Ckt 2 toward Woodward 345 kV
220972 | 95197 | 171359 | SPS | NM | Device - Quahada 115 kV New Capacitor | Quahada 115 kV Capacitor | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2880000 |  | NTC - Commitment Window | 528394 | Quahada 115 kV |  |  | Install 28.8 MVAR capacitor at Quahada 115 kV substation
220972 | 95197 | 171360 | SPS | NM | Device - Quahada 115 kV New Capacitor | Quahada 115 kV Substation Expansion or Rebuild | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 528394 | Quahada 115 kV |  |  | Expand or rebuild Quahada 115 kV substation
220972 | 95198 | 171361 | SPS | NM | Line - Lynch Tap - Pearl 115 kV Rebuild | Lynch Tap - Pearl 115 kV Ckt 1 Rebuild | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 4853022 |  | NTC - Commitment Window | 528390 |  | 528392 | Pearl Sub 115 kV | Rebuild 5.5-mile Ckt 1 line from Lynch Tap 115 kV substation to Pearl 115 kV substation |  |  | 5.5
220972 | 95198 | 171362 | SPS | NM | Line - Lynch Tap - Pearl 115 kV Rebuild | Lynch Tap 115 kV Ckt 1 Terminal Upgrade toward Pearl 115 kV | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 528390 |  | 528392 | Pearl Sub 115 kV | Upgrade terminal equipment at Lynch Tap 115 kV substation for Ckt 1 toward Pearl 115 kV
220972 | 95198 | 171363 | SPS | NM | Line - Lynch Tap - Pearl 115 kV Rebuild | Pearl 115 kV Ckt 1 Terminal Upgrade toward Lynch Tap 115 kV | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2100000 |  | NTC - Commitment Window | 528392 | Pearl Sub 115 kV | 528390 |  | Upgrade terminal equipment at Pearl 115 kV substation for Ckt 1 toward Lynch Tap 115 kV
220972 | 95199 | 171364 | SPS | OK | Device - Twist 115 kV New Capacitor | Twist 115 kV Capacitor (2) | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 4500000 |  | NTC - Commitment Window | 523300 |  |  |  | Install 45 MVAR capacitor at Twist 115 kV substation
220972 | 95199 | 171365 | SPS | OK | Device - Twist 115 kV New Capacitor | Twist 115 kV Substation Expansion or Rebuild | Regional Reliability |  | 2029-06-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 523300 |  |  |  | Expand or rebuild Twist 115 kV substation
220972 | 95200 | 171366 | SPS | NM | XFR - Hobbs 230/115 kV | Hobbs 230/345 kV Ckt 2 Transformer | Economic |  | 2027-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 16400000 |  | NTC - Commitment Window | 527894 | Hobbs Interchange 230 kV | 527896 | Hobbs Interchange 345 kV | Install new 230/345 kV Ckt 2 transformer at Hobbs
220972 | 95200 | 171367 | SPS | NM | XFR - Hobbs 230/115 kV | Hobbs 230 kV Substation Expansion or Rebuild | Economic |  | 2027-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 527894 | Hobbs Interchange 230 kV |  |  | Expand or rebuild Hobbs 230 kV substation
220972 | 95200 | 171368 | SPS | NM | XFR - Hobbs 230/115 kV | Hobbs 345 kV Substation Expansion or Rebuild | Economic |  | 2027-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 527896 | Hobbs Interchange 345 kV |  |  | Expand or rebuild Hobbs 345 kV substation
220972 | 95200 | 171369 | SPS | NM | XFR - Hobbs 230/115 kV | Hobbs 230 kV Ckt 2 Terminal Upgrade toward Hobbs 345 kV | Economic |  | 2027-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 936276 |  | NTC - Commitment Window | 527894 | Hobbs Interchange 230 kV | 527896 | Hobbs Interchange 345 kV | Upgrade terminal equipment at Hobbs 230 kV substation for Ckt 2 toward Hobbs 345 kV
220972 | 95200 | 171370 | SPS | NM | XFR - Hobbs 230/115 kV | Hobbs 345 kV Ckt 2 Terminal Upgrade toward Hobbs 230 kV | Economic |  | 2027-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 1537869 |  | NTC - Commitment Window | 527896 | Hobbs Interchange 345 kV | 527894 | Hobbs Interchange 230 kV | Upgrade terminal equipment at Hobbs 345 kV substation for Ckt 2 toward Hobbs 230 kV
220966 | 95201 | 171373 | OGE | OK | Multi - Anthem - Seminole 765 kV New Line, Anthem 345/138 kV New Transformer | Seminole 765 kV Ckt 1 Terminal Upgrade toward Anthem 765 kV | Economic |  | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 18000000 |  | NTC-C Project Estimate Window | 515049 | WARWICK 138 |  |  | Upgrade terminal equipment at Seminole 765 kV substation for Ckt 1 toward Anthem 765 kV
220967 | 95201 | 171375 | AEP | OK | Multi - Anthem - Seminole 765 kV New Line, Anthem 345/138 kV New Transformer | Anthem 765 kV New Substation | Economic |  | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 377000000 |  | NTC-C Project Estimate Window |  |  |  |  | Install 765 kV substation at Anthem
220967 | 95201 | 171378 | AEP | OK | Multi - Anthem - Seminole 765 kV New Line, Anthem 345/138 kV New Transformer | Anthem 345 kV Substation Expansion or Rebuild | Economic |  | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 50000000 |  | NTC-C Project Estimate Window | 509915 |  |  |  | Expand or rebuild Anthem 345 kV substation
220966 | 95201 | 171388 | OGE | OK | Multi - Anthem - Seminole 765 kV New Line, Anthem 345/138 kV New Transformer | Seminole 765 kV Line Reactor (2) | Economic |  | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 6565000 |  | NTC-C Project Estimate Window | 515049 | WARWICK 138 |  |  | Install 65.65 MVAR line reactor at Seminole 765 kV substation
220954 | 95202 | 171390 | MIDW | KS | Line - Smoky Hills - Summit 230 kV Rebuild (2) | Smoky Hills 230 kV Ckt 1 Terminal Upgrade toward Summit 230 kV | Regional Reliability |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 500000 |  | NTC - Commitment Window | 530592 | SMOKY HILL TAP 230 KV | 532873 | SUMMIT 230 KV | Upgrade terminal equipment at Smoky Hills 230 kV substation for Ckt 1 toward Summit 230 kV
220963 | 95202 | 171391 | EKC | KS | Line - Smoky Hills - Summit 230 kV Rebuild (2) | Summit 230 kV Ckt 1 Terminal Upgrade toward Smoky Hills 230 kV | Regional Reliability |  | 2025-11-18 | 2025-11-11 | 2025 ITP |  |  | 0 | 1170063 |  | NTC - Commitment Window | 532873 | SUMMIT 230 KV | 530592 | SMOKY HILL TAP 230 KV | Upgrade terminal equipment at Summit 230 kV substation for Ckt 1 toward Smoky Hills 230 kV
220963 | 95202 | 171392 | EKC | KS | Line - Smoky Hills - Summit 230 kV Rebuild (2) | Smoky Hills - Summit 230 kV Ckt 1 Rebuild (2) (EKC) | Regional Reliability |  | 2025-11-18 | 2025-11-11 | 2025 ITP |  |  | 0 | 42654300 |  | NTC - Commitment Window | 530592 | SMOKY HILL TAP 230 KV | 532873 | SUMMIT 230 KV | Rebuild 22.4 miles of 38.56-mile Ckt 1 line from Smoky Hills 230 kV substation to Summit 230 kV substation |  |  | 22.45
220974 | 95204 | 171393 | ETEC | TX | Line - Jarred Williamson - V.B. Shaw Tap 69 kV Line Switch-in | Energize Jarred Williamson - V.B. Shaw Tap 69 kV Ckt NO | Zonal Reliability |  | 2031-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509680 |  | 509681 |  | Switch in 69 kV Ckt NO line from Jarred Williamson to V.B. Shaw Tap
220972 | 95205 | 171394 | SPS | NM | XFR - Kiowa 345/115 kV New Transformer | Kiowa 345/115 kV Ckt 2 Transformer | Regional Reliability |  | 2027-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 9700000 |  | NTC - Commitment Window | 527965 |  | 527966 |  | Install new 345/115 kV Ckt 2 transformer at Kiowa
220972 | 95205 | 171395 | SPS | NM | XFR - Kiowa 345/115 kV New Transformer | Kiowa 345 kV Substation Expansion or Rebuild | Regional Reliability |  | 2027-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 527965 |  |  |  | Expand or rebuild Kiowa 345 kV substation
220972 | 95205 | 171396 | SPS | NM | XFR - Kiowa 345/115 kV New Transformer | Kiowa 115 kV Substation Expansion or Rebuild | Regional Reliability |  | 2027-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 527966 |  |  |  | Expand or rebuild Kiowa 115 kV substation
220972 | 95205 | 171397 | SPS | NM | XFR - Kiowa 345/115 kV New Transformer | Kiowa 345 kV Ckt 2 Terminal Upgrade toward Kiowa 115 kV | Regional Reliability |  | 2027-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 1537869 |  | NTC - Commitment Window | 527965 |  | 527966 |  | Upgrade terminal equipment at Kiowa 345 kV substation for Ckt 2 toward Kiowa 115 kV
220972 | 95205 | 171398 | SPS | NM | XFR - Kiowa 345/115 kV New Transformer | Kiowa 115 kV Ckt 2 Terminal Upgrade toward Kiowa 345 kV | Regional Reliability |  | 2027-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 385333 |  | NTC - Commitment Window | 527966 |  | 527965 |  | Upgrade terminal equipment at Kiowa 115 kV substation for Ckt 2 toward Kiowa 345 kV
220950 | 95153 | 171401 | AEP | OK | Line - Lone Oak - Tuskahoma - Talihina 138 kV New Line | Talihina 138/69 kV Ckt 1 Transformer | Zonal Reliability |  | 2027-07-30 | 2025-11-07 | 2025 ITP |  |  | 0 | 17000000 |  | NTC - Commitment Window |  |  | 510930 | TALIHINA WEST 69 | Install new 138/69 kV Ckt 1 transformer at Talihina
220950 | 95153 | 171402 | AEP | OK | Line - Lone Oak - Tuskahoma - Talihina 138 kV New Line | Talihina West 69 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2027-07-30 | 2025-11-07 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 510930 | TALIHINA WEST 69 |  |  | Expand or rebuild Talihina West 69 kV substation
220950 | 95153 | 171403 | AEP | OK | Line - Lone Oak - Tuskahoma - Talihina 138 kV New Line | Talihina 138 kV Ckt 1 Terminal Upgrade toward Talihina West 69 kV | Zonal Reliability |  | 2027-07-30 | 2025-11-07 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window |  |  | 510930 | TALIHINA WEST 69 | Upgrade terminal equipment at Talihina 138 kV substation for Ckt 1 toward Talihina West 69 kV
220950 | 95153 | 171404 | AEP | OK | Line - Lone Oak - Tuskahoma - Talihina 138 kV New Line | Talihina West 69 kV Ckt 1 Terminal Upgrade toward Talihina 138 kV | Zonal Reliability |  | 2027-07-30 | 2025-11-07 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 510930 | TALIHINA WEST 69 |  |  | Upgrade terminal equipment at Talihina West 69 kV substation for Ckt 1 toward Talihina 138 kV
220950 | 95155 | 171405 | AEP | TX | Line - Adora - Pilgrims Pride 69 kV New Line | Adora - Pilgrims Pride 69 kV Ckt 1 New Line | Zonal Reliability |  | 2026-12-30 | 2025-11-07 | 2025 ITP |  |  | 0 | 8475000 |  | NTC - Commitment Window | 508284 | ADORA REC | 508311 | PILGRIM'S PRIDE | Build a 1.8-mile 69 kV Ckt 1 line from Adora to Pilgrims Pride |  | 1.8
220950 | 95155 | 171406 | AEP | TX | Line - Adora - Pilgrims Pride 69 kV New Line | Adora 69 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2026-12-30 | 2025-11-07 | 2025 ITP |  |  | 0 | 14700000 |  | NTC - Commitment Window | 508284 | ADORA REC |  |  | Expand or rebuild Adora 69 kV substation
220950 | 95156 | 171411 | AEP | OK | Device - Choctaw 138 kV New Capacitor | Choctaw 138 kV Capacitor | Zonal Reliability |  | 2027-11-30 | 2025-11-07 | 2025 ITP |  |  | 0 | 2000000 |  | NTC - Commitment Window | 511567 |  |  |  | Install 23 MVAR capacitor at Choctaw 138 kV substation
220964 | 95147 | 171412 | EM | KS | Line - Craig - Lenexa Ckt 2 161 kV Rebuild | Craig - Lenexa 161 kV Ckt 2 Rebuild (2) | Economic |  | 2025-11-18 | 2025-11-11 | 2025 ITP |  |  | 0 | 7449983 |  | NTC - Commitment Window | 542978 | CRAIG 161 KV | 543038 | LENEXA SOUTH 161 KV | Rebuild 2.98-mile Ckt 2 line from Craig 161 kV substation to Lenexa 161 kV substation |  |  | 2.98
220977 | 95209 | 171415 | WFEC | OK | Line - Cleo Corner - Cleo Springs Switch Station 69 kV Rebuild | Cleo Corner - Cleo Springs Switch Station 69 kV Ckt 1 Rebuild | Transmission Service | 2027-09-01 | 2025-12-01 | 2025-11-26 | SPP-2025-AG1-AFS-3 |  |  | 0 | 1750000 |  | Pending NTC/NTC-C |  |  |  |  | Rebuild 1.58 mile to 795ASCR 100/127 MVA Summer/Winter.
220974 | 95221 | 171429 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | J.G. Walker - Cathey 69 kV Ckt NO Close in Normally Open Circuit | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509686 |  | 509688 |  | Close in normally open 69 kV Ckt NO line from J.G. Walker to Cathey
220974 | 95221 | 171430 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | J.G. Walker 69 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 3510000 |  | NTC - Commitment Window | 509686 |  |  |  | Expand or rebuild J.G. Walker 69 kV substation
220974 | 95221 | 171431 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | Cathey 69 kV Substation Upgrades | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 880000 |  | NTC - Commitment Window | 509688 |  |  |  | Upgrade or reconfigure Cathey 69 kV substation
220974 | 95221 | 171432 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | J.G. Walker 69 kV Ckt NO Terminal Upgrade toward Cathey 69 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509686 |  | 509688 |  | Upgrade terminal equipment at J.G. Walker 69 kV substation for Ckt NO toward Cathey 69 kV
220974 | 95221 | 171433 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | Cathey 69 kV Ckt NO Terminal Upgrade toward J.G. Walker 69 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509688 |  | 509686 |  | Upgrade terminal equipment at Cathey 69 kV substation for Ckt NO toward J.G. Walker 69 kV
220974 | 95221 | 171434 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | Nichols 69 kV Capacitor | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509684 |  |  |  | Install 12 MVAR capacitor at Nichols 69 kV substation
220974 | 95221 | 171435 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | Nichols 69 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 12720000 |  | NTC - Commitment Window | 509684 |  |  |  | Expand or rebuild Nichols 69 kV substation to a 6 breaker ring bus design
220974 | 95221 | 171436 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | Pilgrim's Rest REC (Williamson-Ziegler) 69 kV Substation Reconfiguration (ETEC) | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 5485000 |  | NTC - Commitment Window | 508352 | PILGRIM'S REST REC |  |  | Reconfigure the Pilgrim's Rest REC 69 kV substation to 4 or 5 breaker ring bus design
220974 | 95221 | 171437 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | Pilgrim's Rest REC (Williamson-Ziegler) 69 kV Ckt 1 Terminal Upgrade toward Cathey 69 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 508352 | PILGRIM'S REST REC | 509688 |  | Upgrade terminal equipment at Pilgrim's Rest REC 69 kV substation for Ckt 1 toward Cathey 69 kV
220974 | 95221 | 171438 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | Pilgrim's Rest REC (Williamson-Ziegler) 69 kV Ckt 1 Terminal Upgrade toward AEP-Alba 69 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 508352 | PILGRIM'S REST REC | 508334 | ALBA | Upgrade terminal equipment at Pilgrim's Rest REC 69 kV substation for Ckt 1 toward AEP-Alba 69 kV
220974 | 95221 | 171439 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | Pilgrim's Rest REC (Williamson-Ziegler) 69 kV Ckt 1 Terminal Upgrade toward AEP-Westwood 69 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 508352 | PILGRIM'S REST REC | 508354 | WESTWOOD | Upgrade terminal equipment at Pilgrim's Rest REC 69 kV substation for Ckt 1 toward AEP-Westwood 69 kV
220974 | 95221 | 171440 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | Nichols 69 kV Ckt 1 Terminal Upgrade toward EO Brown 69 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509684 |  | 509685 |  | Upgrade terminal equipment at Nichols 69 kV substation for Ckt 1 toward EO Brown 69 kV
220974 | 95221 | 171441 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | Nichols 69 kV Ckt 1 Terminal Upgrade toward E Benton 69 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509684 |  | 509683 |  | Upgrade terminal equipment at Nichols 69 kV substation for Ckt 1 toward E Benton 69 kV
220974 | 95221 | 171442 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | Nichols 69 kV Ckt NO Terminal Upgrade toward Hill-Wilson 69 kV (2) | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509684 |  | 509687 |  | Upgrade terminal equipment at Nichols 69 kV substation for Ckt NO toward Hill-Wilson 69 kV
220974 | 95221 | 171443 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | J.G. Walker 69 kV Ckt 1 Terminal Upgrade toward EO Brown 69 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509686 |  | 509685 |  | Upgrade terminal equipment at J.G. Walker 69 kV substation for Ckt 1 toward EO Brown 69 kV
220974 | 95221 | 171444 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | Cathey 69 kV Ckt 1 Terminal Upgrade toward Pilgrim's Rest REC (Williamson-Ziegler) 69 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509688 |  | 508352 | PILGRIM'S REST REC | Upgrade terminal equipment at Cathey 69 kV substation for Ckt 1 toward Pilgrim's Rest REC (Williamson-Ziegler) 69 kV
220974 | 95221 | 171445 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | EO Brown 69 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 4050000 |  | NTC - Commitment Window | 509685 |  |  |  | Add motor-operated air-break switches with SCADA control at EO Brown 69 kV
220974 | 95221 | 171446 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | EO Brown 69 kV Ckt 1 Terminal Upgrade toward JG Walker 69 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509685 |  | 509686 |  | Upgrade terminal equipment at EO Brown 69 kV substation for Ckt 1 toward JG Walker 69 kV
220974 | 95221 | 171447 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | EO Brown 69 kV Ckt 1 Terminal Upgrade toward Nichols 69 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509685 |  | 509684 |  | Upgrade terminal equipment at EO Brown 69 kV substation for Ckt 1 toward Nichols 69 kV
220974 | 95221 | 171448 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | E Benton 69 kV Substation Expansion or Rebuild | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 3460000 |  | NTC - Commitment Window | 509683 |  |  |  | Add motor-operated air-break switches with SCADA control at E Benton 69 kV
220974 | 95221 | 171449 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | E Benton 69 kV Ckt 1 Terminal Upgrade toward Quitman 69 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509683 |  | 508353 | QUITMAN | Upgrade terminal equipment at E Benton 69 kV substation for Ckt 1 toward Quitman 69 kV
220974 | 95221 | 171450 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | E Benton 69 kV Ckt 1 Terminal Upgrade toward Nichols 69 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 509683 |  | 509684 |  | Upgrade terminal equipment at E Benton 69 kV substation for Ckt 1 toward Nichols 69 kV
220974 | 95221 | 171451 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | Quitman 69 kV Substation Upgrades | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 880000 |  | NTC - Commitment Window | 508353 | QUITMAN |  |  | Upgrade or reconfigure Quitman 69 kV substation
220974 | 95221 | 171452 | ETEC | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | Quitman 69 kV Ckt 1 Terminal Upgrade toward E Benton 69 kV | Zonal Reliability |  | 2033-04-01 | 2025-11-21 | 2025 ITP |  |  | 0 | 0 |  | NTC - Commitment Window | 508353 | QUITMAN | 509683 |  | Upgrade terminal equipment at Quitman 69 kV substation for Ckt 1 toward E Benton 69 kV
220971 | 95192 | 171957 | WAPA | ND | Line - Belfield - Roundup 345 kV New Line | Belfield 2 345 kV Terminal Upgrade | Economic | 2033-07-01 | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 4200000 |  | NTC-C Project Estimate Window |  |  |  |  | Install any necessary terminal equipment at Belfield 2 substation to support a new tie-line from Belfield 345 kV substation to Belfield 2 345 kV substation if needed that meets or exceeds a summer emergency rating of 1792 MVA
220971 | 95192 | 171958 | WAPA | ND | Line - Belfield - Roundup 345 kV New Line | Belfield 345 kV Terminal Upgrade | Economic | 2033-07-01 | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 4200000 |  | NTC-C Project Estimate Window |  |  |  |  | Install any necessary terminal equipment at Belfield substation to support a new tie-line from Belfield 345 kV substation to Belfield 2 345 kV substation if needed that meets or exceeds a summer emergency rating of 1792 MVA
220971 | 95192 | 171959 | WAPA | ND | Line - Belfield - Roundup 345 kV New Line | Belfield to Belfield 2 345 kV Ckt 1 New Line | Economic | 2033-07-01 | 2032-01-01 | 2025-11-13 | 2025 ITP |  |  | 0 | 2000000 |  | NTC-C Project Estimate Window |  |  |  |  | Build a new 345 kV tie-line from Belfield 345 kV substation to Belfield 2 345 kV substation if necessary that meets or exceeds a summer emergency rating of 1792 MVA.
220965 | 95142 | 171960 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Horseshoe Lake 138 kV Ckt 1 Terminal Upgrade toward Green Pastures 138 kV | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 4000000 |  | NTC - Commitment Window |  |  |  |  | Upgrade terminal equipment at Horseshoe Lake 138 kV substation for Ckt 1 toward Green Pastures 138 kV
220965 | 95142 | 171961 | OGE | OK | Multi - Horseshoe Lake Reconfiguration | Reno 138 kV Ckt 1 Terminal Upgrade toward NE 30th 138 kV | Regional Reliability |  | 2029-06-01 | 2025-11-11 | 2025 ITP |  |  | 0 | 2500000 |  | NTC - Commitment Window |  |  |  |  | Upgrade terminal equipment at Reno 138 kV substation for Ckt 1 toward NE 30th 138 kV
220950 | 95150 | 171964 | AEP | TX | Multi - Buford - DeKalb 69 kV Line Tap | South Dekalb Switch Station 69 kV New Substation (AEP) | Zonal Reliability |  | 2031-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 5237500 |  | NTC - Commitment Window | 509660 |  |  |  | Install 69 kV substation at South Dekalb
220950 | 95149 | 171965 | AEP | TX | Multi - FARMRAC - Ripley - Argo 69 kV, Rebuild Chapel Hill - Adora Closed Loop | Chapel Hill 138 kV Substation Expansion or Rebuild (AEP) | Zonal Reliability |  | 2031-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 4410000 |  | NTC - Commitment Window | 509664 |  |  |  | Expand or rebuild Chapel Hill 138 kV substation (Four terminal station)
220956 | 95177 | 171966 | MRES | SD | Multi - Aurora 115 kV New Lines, White 345/115 kV New Transformer | Aurora Industrial - BMU East 115 kV Ckt 1 New Line (MRES) | Regional Reliability |  | 2025-11-18 | 2025-11-10 | 2025 ITP |  |  | 0 | 2950000 |  | NTC - Commitment Window | 655379 |  | 658156 |  | Build a 3.96-mile 115 kV Ckt 1 line from Aurora Industrial to BMU East |  | 3.96
220950 | 95221 | 171967 | AEP | TX | Multi - J.G. Walker - Cathey 69 kV Close Normally Open Line, Nichols 69 kV New Capacitor | Pilgrim's Rest REC (Williamson-Ziegler) 69 kV Substation Reconfiguration (AEP) | Zonal Reliability |  | 2033-04-01 | 2025-11-07 | 2025 ITP |  |  | 0 | 5485000 |  | NTC - Commitment Window | 508311 | PILGRIM'S PRIDE |  |  | Reconfigure the Pilgrim's Rest REC 69 kV substation to 4 or 5 breaker ring bus design